## SRRC-SfB-Decommision Schedule
SRRC Decommison of on-premises Skype for Business environment
Step | Day | Time | Duration | Task | Resource | Status | Comment | Reference
1 | Wednesday |  |  | Complete Audio Conference | SRRC RMT | Completed | Awaiting Mark to confirm new Brisbane number as default meeting dial-in number for all users. | Set-CsOnlineDialInConferencingUser (SkypeForBusiness) ¦ Microsoft Learn
2 |  |  |  | Redirect 5959 to new phone number |  | Completed
3 |  |  |  | Review items not migrated from SfB to Teams | SRRC | Completed | Spreadsheet shared has current state
4 |  |  |  | Move any further users identified | RMT | Completed | As identified in Spreadsheet | Move users to the cloud - Skype for Business Hybrid ¦ Microsoft Learn
5 | Friday |  |  | Disable Hybrid environment | RMT | In Progress |  | Disable hybrid to complete migration to Teams Only - Skype for Business Hybrid ¦ Microsoft Learn
6 | Friday |  |  | A. Update DNS records to point to Microsoft 365 | RMT/SRRC | External Done - Internal doing last
7 | Friday |  |  | B. Change coexistence mode to organization to Teams Only | RMT | Completed
8 | Friday |  |  | C. Disable Shared sip address space (also known as "split domain") in the Microsoft 365 organization | RMT | Completed
9 | Friday |  |  | D. Disable communication between on-premises and Microsoft 365 | RMT | Completed
10 | Friday |  |  | Migrate hybrid application endpoints from on-premisie to online - NOT REQUIRED | - | Completed | NOT REQUIRED as CentrePal has replaced SfB Contact Centre.
11 | Monday | Evening |  | Remove your on-promises Skype for Business deployment | RMT | In Progress |  | Decommission Skype for Business Server - Skype for Business Hybrid ¦ Microsoft Learn
12 |  |  |  | Review and agree completion | SRRC RMT | TBA
13
14 |  |  |  | Decommision Servers | SRRC Anthony | Planning | Shutdown servers. After 1 week or whne happy reimiage/deleted servers
15
16

## AudioConfLog
PS C:\WINDOWS\system32> get-CsOnlineDialInConferencingUser ¦ Select DisplayName, SipAddress, DefaultTollNumber ¦ Sort-Object -property SipAddress ¦ FT
DisplayName SipAddress DefaultTollNumber
----------- ---------- -----------------
Adam Jordan sip:adam.j@scenicrim.qld.gov.au 61272084711
Adam Maskelyne sip:adam.ma@scenicrim.qld.gov.au 61272084711
Adrian Chan sip:adrian.c@scenicrim.qld.gov.au 61272084711
Adrienne Jeuda sip:adrienne.j@scenicrim.qld.gov.au 61272084711
Alana Bellamy sip:alana.b@scenicrim.qld.gov.au 61272084711
Alisa Totenhofer sip:alisa.t@scenicrim.qld.gov.au 61272084711
Alisha Pettit sip:alisha.p@scenicrim.qld.gov.au 61272084711
Allen Naidoo sip:allen.n@scenicrim.qld.gov.au 61272084711
Allyson Hundy sip:allyson.h@scenicrim.qld.gov.au 61272084711
Amanda Duncan sip:amanda.d@scenicrim.qld.gov.au 61272084711
Amanda Fogg sip:amanda.f@scenicrim.qld.gov.au 61272084711
Cr Amanda Hay sip:amanda.h@scenicrim.qld.gov.au 61272084711
Amanda Lewis sip:amanda.l@scenicrim.qld.gov.au 61272084711
Amanda Vinson sip:amanda.v@scenicrim.qld.gov.au 61272084711
Amelia Jibson sip:amelia.j@scenicrim.qld.gov.au 61272084711
Amie Prince sip:amie.p@scenicrim.qld.gov.au 61272084711
Amy Rogers sip:amy.r@scenicrim.qld.gov.au 61272084711
Amy Wilson sip:amy.w@scenicrim.qld.gov.au 61272084711
Anastasia Roche sip:anastasia.r@scenicrim.qld.gov.au 61272084711
Andrew Clews sip:andrew.c@scenicrim.qld.gov.au 61272084711
Andrew Cumming sip:andrew.cu@scenicrim.qld.gov.au 61272084711
Andrew Hewitt sip:andrew.h@scenicrim.qld.gov.au 61272084711
Andrew May sip:andrew.ma@scenicrim.qld.gov.au 61272084711
Andrew Richter sip:andrew.r@scenicrim.qld.gov.au 61272084711
Andrew Staines sip:andrew.s@scenicrim.qld.gov.au 61272084711
Ann Greaves sip:ann.g@scenicrim.qld.gov.au 61272084711
Anna Shera sip:anna.s@scenicrim.qld.gov.au 61272084711
Anne Baxter sip:anne.b@scenicrim.qld.gov.au 61272084711
Ann-Marie Williamson sip:annmarie.w@scenicrim.qld.gov.au 61272084711
Anthony Marshall sip:anthony.m@scenicrim.qld.gov.au 61272084711
Asiful Alam sip:asiful.a@scenicrim.qld.gov.au 61272084711
Beaudesert Cultural Centre 5051 sip:bcc5051@scenicrim.qld.gov.au 61272084711
Beaudesert Cultural Centre 5060 sip:bcc5060@srrc.onmicrosoft.com 61272084711
Belinda Jacklyn sip:belinda.j@scenicrim.qld.gov.au 61272084711
Ben Oppermann sip:ben.o@scenicrim.qld.gov.au 61272084711
Bill Kellaway sip:bill.k@scenicrim.qld.gov.au 61272084711
Billie Procter sip:billie.p@scenicrim.qld.gov.au 61272084711
Blake Bolz Brown sip:blake.b@scenicrim.qld.gov.au 61272084711
Blake Hunton sip:blake.h@scenicrim.qld.gov.au 61272084711
Boonah local Government - 3042 sip:boonah.frontdesk1@srrc.onmicrosoft.com 61272084711
Boonah Front Desk 2 3035 sip:boonah.frontdesk2@srrc.onmicrosoft.com 61272084711
Brad Freeman sip:brad.f@scenicrim.qld.gov.au 61272084711
Brad Warneminde sip:brad.w@scenicrim.qld.gov.au 61272084711
Brenda Walker sip:brenda.w@scenicrim.qld.gov.au 61272084711
Brett Fletcher sip:brett.f@scenicrim.qld.gov.au 61272084711
Brian Antcliff sip:brian.a@scenicrim.qld.gov.au 61272084711
Bridget Ponting sip:bridget.p@scenicrim.qld.gov.au 61272084711
Brittany Hawken sip:brittany.h@scenicrim.qld.gov.au 61272084711
Bronwyn Cairns sip:bronwyn.c@scenicrim.qld.gov.au 61272084711
Byron Struck sip:byron.s@scenicrim.qld.gov.au 61272084711
Cameron Thomas sip:cameron.t@scenicrim.qld.gov.au 61272084711
Carleen Orr sip:carleen.o@scenicrim.qld.gov.au 61272084711
Carly Linnertson sip:carly.l@scenicrim.qld.gov.au 61272084711
Carmel Dunn sip:carmel.d@scenicrim.qld.gov.au 61272084711
Carmen Hawken sip:carmen.h@scenicrim.qld.gov.au 61272084711
Carolann Barnwell sip:carolann.b@scenicrim.qld.gov.au 61272084711
Caroline McMahon sip:caroline.m@scenicrim.qld.gov.au 61272084711
Carolyn Gorrill sip:carolyn.g@scenicrim.qld.gov.au 61272084711
Cassandra Newsham sip:cassandra.n@scenicrim.qld.gov.au 61272084711
Catherine Kahler sip:catherine.k@scenicrim.qld.gov.au 61272084711
Catherine Madden sip:catherine.m@scenicrim.qld.gov.au 61272084711
Chantal Birt sip:chantal.b@scenicrim.qld.gov.au 61272084711
Charlie Wilson sip:charlie.w@scenicrim.qld.gov.au 61272084711
Cherece Jackson sip:cherece.j@scenicrim.qld.gov.au 61272084711
Cheryl Henderson sip:cheryl.h@scenicrim.qld.gov.au 61272084711
Chloe Elliott sip:chloe.e@scenicrim.qld.gov.au 61272084711
Chris Castle sip:chris.c@scenicrim.qld.gov.au 61272084711
Christopher Gray sip:christopher.g@scenicrim.qld.gov.au 61272084711
Christy Schloss sip:christy.s@scenicrim.qld.gov.au 61272084711
Cindy Weber sip:cindy.w@scenicrim.qld.gov.au 61272084711
Claire Dolereit sip:claire.d@scenicrim.qld.gov.au 61272084711
Clare Newland sip:clare.n@scenicrim.qld.gov.au 61272084711
Clyde Powys sip:clyde.p@scenicrim.qld.gov.au 61272084711
Colin Mackie sip:colin.m@scenicrim.qld.gov.au 61272084711
Craig Heck sip:craig.h@scenicrim.qld.gov.au 61272084711
Craig Herron sip:craig.he@scenicrim.qld.gov.au 61272084711
Craig McDougall sip:craig.mc@scenicrim.qld.gov.au 61272084711
Craig Piltz sip:craig.p@scenicrim.qld.gov.au 61272084711
Planning Business Support sip:daadmin@scenicrim.qld.gov.au 61272084711
Damian Topp sip:damian.t@scenicrim.qld.gov.au 61272084711
Daniel McNamara sip:daniel.mc@scenicrim.qld.gov.au 61272084711
Daniel Samphier sip:daniel.s@scenicrim.qld.gov.au 61272084711
Daniel Smith sip:daniel.sm@scenicrim.qld.gov.au 61272084711
Danni Moore sip:danni.m@scenicrim.qld.gov.au 61272084711
Darren Laegel sip:darren.l@scenicrim.qld.gov.au 61272084711
David Adamson sip:david.a@scenicrim.qld.gov.au 61272084711
David Keenan sip:david.k@scenicrim.qld.gov.au 61272084711
David Richards sip:david.r@scenicrim.qld.gov.au 61272084711
Dean Kibble sip:dean.k@scenicrim.qld.gov.au 61272084711
Dean Walkley sip:dean.w@scenicrim.qld.gov.au 61272084711
Deanna Fenech sip:deanna.f@scenicrim.qld.gov.au 61272084711
Debbie Salem sip:debbie.s@scenicrim.qld.gov.au 61272084711
Debra Howe sip:debra.h@scenicrim.qld.gov.au 61272084711
Debra Turnbull sip:debra.t@scenicrim.qld.gov.au 61272084711
Dee Crotty sip:dee.c@scenicrim.qld.gov.au 61272084711
Deeanne Tracey sip:deeanne.t@scenicrim.qld.gov.au 61272084711
Desley Agnoletto sip:desley.a@scenicrim.qld.gov.au 61272084711
Donna Chatfield sip:donna.c@scenicrim.qld.gov.au 61272084711
Donna Robinson sip:donna.r@scenicrim.qld.gov.au 61272084711
Donnalee Olive sip:donnalee.o@scenicrim.qld.gov.au 61272084711
Doug Hatch sip:doug.h@scenicrim.qld.gov.au 61272084711
Drift Ishter sip:drift.i@scenicrim.qld.gov.au 61272084711
Cr Duncan McInnes sip:duncan.m@scenicrim.qld.gov.au 61272084711
Ellie Barnes sip:ellie.b@scenicrim.qld.gov.au 61272084711
Elva Sykes sip:elva.s@scenicrim.qld.gov.au 61272084711
Emily Barry sip:emily.b@scenicrim.qld.gov.au 61272084711
Emma Thomson sip:emma.th@scenicrim.qld.gov.au 61272084711
Erin Powyer sip:erin.p@scenicrim.qld.gov.au 61272084711
Frank Andrews sip:frank.a@scenicrim.qld.gov.au 61272084711
Gail Keeler sip:gail.k@scenicrim.qld.gov.au 61272084711
Gavin Gotke sip:gavin.g@scenicrim.qld.gov.au 61272084711
Gayanne Kroll sip:gayanne.k@scenicrim.qld.gov.au 61272084711
Genevieve Larsen sip:genevieve.l@scenicrim.qld.gov.au 61272084711
Georgina Williams sip:georgina.w@scenicrim.qld.gov.au 61272084711
Gerald Parker sip:gerald.p@scenicrim.qld.gov.au 61272084711
Grace Roberts sip:grace.r@scenicrim.qld.gov.au 61272084711
Graham Andrews sip:graham.a@scenicrim.qld.gov.au 61272084711
Cr Greg Christensen sip:greg.c@scenicrim.qld.gov.au 61272084711
Greg Harmer sip:greg.h@scenicrim.qld.gov.au 61272084711
Hazel Malone sip:hazel.m@scenicrim.qld.gov.au 61272084711
Heather Nelson sip:heather.n@scenicrim.qld.gov.au 61272084711
Heerah Kanayar sip:heerah.k@scenicrim.qld.gov.au 61272084711
Helen Rizvi sip:helen.r@scenicrim.qld.gov.au 61272084711
Hera Li sip:hera.l@scenicrim.qld.gov.au 61272084711
Hiral Patel sip:hiral.p@scenicrim.qld.gov.au 61272084711
Holly Honey sip:holly.h@scenicrim.qld.gov.au 61272084711
HR sip:hr@scenicrim.qld.gov.au 61272084711
Ian McCarthy sip:ian.m@scenicrim.qld.gov.au 61272084711
India Breen sip:india.b@scenicrim.qld.gov.au 61272084711
Info_Moogerah sip:info_moogerah@scenicrim.qld.gov.au 61272084711
Ingrid Lawrance sip:ingrid.l@scenicrim.qld.gov.au 61272084711
insync sip:insync@scenicrim.qld.gov.au 61272084711
Integrity (Governance) sip:integrity@scenicrim.qld.gov.au 61272084711
Irene Girsch-Danby sip:irene.g@scenicrim.qld.gov.au 61272084711
Isabel Fitzgerald sip:isabel.f@scenicrim.qld.gov.au 61272084711
Jackie Lynch sip:jackie.l@scenicrim.qld.gov.au 61272084711
Jacob Okesene sip:jacob.o@scenicrim.qld.gov.au 61272084711
Jaime McLachlan sip:jaime.m@scenicrim.qld.gov.au 61272084711
Jairo Cadena sip:jairo.c@scenicrim.qld.gov.au 61272084711
James Douyere sip:james.do@scenicrim.qld.gov.au 61272084711
James O'Kane sip:james.ok@scenicrim.qld.gov.au 61272084711
James Wong sip:james.w@scenicrim.qld.gov.au 61272084711
Jamie Baker sip:jamie.b@scenicrim.qld.gov.au 61272084711
Jan Harradine sip:jan.h@scenicrim.qld.gov.au 61272084711
Jane Gough sip:jane.g@scenicrim.qld.gov.au 61272084711
Jane Skimmings sip:jane.s@scenicrim.qld.gov.au 61272084711
Jared Kranz sip:jared.k@scenicrim.qld.gov.au 61272084711
Jarrod Hunter sip:jarrod.h@scenicrim.qld.gov.au 61272084711
Jasmine Scholz sip:jasmine.s@scenicrim.qld.gov.au 61272084711
Jason Callon sip:jason.ca@scenicrim.qld.gov.au 61272084711
Jason Grimsey sip:jason.g@scenicrim.qld.gov.au 61272084711
Jason Hans sip:jason.h@scenicrim.qld.gov.au 61272084711
Jason Taylor sip:jason.t@scenicrim.qld.gov.au 61272084711
Jason Young sip:jason.y@scenicrim.qld.gov.au 61272084711
Jeff Baguley sip:jeff.b@scenicrim.qld.gov.au 61272084711
Cr Jeff McConnell sip:jeff.m@scenicrim.qld.gov.au 61272084711
Jenna Turnbull sip:jenna.t@scenicrim.qld.gov.au 61272084711
Jennifer Stockman sip:jennifer.st@scenicrim.qld.gov.au 61272084711
Jeremey Rose sip:jeremey.r@scenicrim.qld.gov.au 61272084711
Jeremy Patten sip:jeremy.p@scenicrim.qld.gov.au 61272084711
Jessica Dawes sip:jessica.d@scenicrim.qld.gov.au 61272084711
Jo Jones sip:jo.j@scenicrim.qld.gov.au 61272084711
Jo Jordan sip:jo.jo@scenicrim.qld.gov.au 61272084711
Jo-Ann Atkinson sip:jo-ann.a@scenicrim.qld.gov.au 61272084711
Joanne Downes sip:joanne.d@scenicrim.qld.gov.au 61272084711
Joanne Hayselden sip:joanne.h@scenicrim.qld.gov.au 61272084711
Joanne Morecroft sip:joanne.m@scenicrim.qld.gov.au 61272084711
Jodi Wynne sip:jodi.w@scenicrim.qld.gov.au 61272084711
Jodie McPhail sip:jodie.m@scenicrim.qld.gov.au 61272084711
Jodie Marschke sip:jodie.ma@scenicrim.qld.gov.au 61272084711
Jodie Smith sip:jodie.s@scenicrim.qld.gov.au 61272084711
Jodie Vanstone sip:jodie.v@scenicrim.qld.gov.au 61272084711
Joel Stumer sip:joel.s@scenicrim.qld.gov.au 61272084711
John Kearns sip:john.ke@scenicrim.qld.gov.au 61272084711
John Langton sip:john.l@scenicrim.qld.gov.au 61272084711
John Murphy sip:john.m@scenicrim.qld.gov.au 61272084711
John Pukallus sip:john.p@scenicrim.qld.gov.au 61272084711
Jon Rutledge sip:jon.r@scenicrim.qld.gov.au 61272084711
Jordan Tandy-Spooner sip:jordan.t@scenicrim.qld.gov.au 61272084711
Joseph Kirkwood sip:joseph.k@scenicrim.qld.gov.au 61272084711
Judith Hampson sip:judith.h@scenicrim.qld.gov.au 61272084711
Judy Jenner sip:judy.j@scenicrim.qld.gov.au 61272084711
Julia Krawitz sip:julia.k@scenicrim.qld.gov.au 61272084711
Julia Moore sip:julia.m@scenicrim.qld.gov.au 61272084711
Julie O'Neill sip:julie.o@scenicrim.qld.gov.au 61272084711
Julie Schmidt sip:julie.s@scenicrim.qld.gov.au 61272084711
Julien Parrot sip:julien.p@scenicrim.qld.gov.au 61272084711
Justin Auld sip:justin.a@scenicrim.qld.gov.au 61272084711
Justin Knudson sip:justin.k@scenicrim.qld.gov.au 61272084711
Justin Shera sip:justin.s@scenicrim.qld.gov.au 61272084711
Justin Sinnamon sip:justin.si@scenicrim.qld.gov.au 61272084711
Justin Storey sip:justin.st@scenicrim.qld.gov.au 61272084711
Karen Brooker sip:karen.br@scenicrim.qld.gov.au 61272084711
Kate Cleto sip:kate.c@scenicrim.qld.gov.au 61272084711
Kate Jones sip:kate.jo@scenicrim.qld.gov.au 61272084711
Kathy Forrest sip:kathy.f@scenicrim.qld.gov.au 61272084711
Katie Newlove sip:katie.n@scenicrim.qld.gov.au 61272084711
Katrina Childs sip:katrina.c@scenicrim.qld.gov.au 61272084711
Katrina Richter sip:katrina.r@scenicrim.qld.gov.au 61272084711
Kelli Rabbitt sip:kelli.r@scenicrim.qld.gov.au 61272084711
Kelly Locksley sip:kelly.l@scenicrim.qld.gov.au 61272084711
Kelly Richardson sip:kelly.r@scenicrim.qld.gov.au 61272084711
Kelmeny Fraser sip:kelmeny.f@scenicrim.qld.gov.au 61272084711
Kevin Domjahn sip:kevin.d@scenicrim.qld.gov.au 61272084711
Kirby McDonald sip:kirby.m@scenicrim.qld.gov.au 61272084711
Kobi Lane sip:kobi.l@scenicrim.qld.gov.au 61272084711
Kris Van der Borgh sip:kris.v@scenicrim.qld.gov.au 61272084711
Krystal Bardell sip:krystal.b@scenicrim.qld.gov.au 61272084711
Kuda Pfidze sip:kuda.p@scenicrim.qld.gov.au 61272084711
Kyle Richards sip:kyle.r@scenicrim.qld.gov.au 61272084711
Kylee Mallinson sip:kylee.m@scenicrim.qld.gov.au 61272084711
Kylie Addy sip:kylie.a@scenicrim.qld.gov.au 61272084711
Kym Lancaster sip:kym.l@scenicrim.qld.gov.au 61272084711
Lacey Sawtell sip:lacey.s@scenicrim.qld.gov.au 61272084711
Lana Lockett sip:lana.l@scenicrim.qld.gov.au 61272084711
Lara Solyma sip:lara.s@scenicrim.qld.gov.au 61272084711
Lau Chean-Piau sip:lau.c@scenicrim.qld.gov.au 61272084711
Laura Mollinger sip:laura.m@scenicrim.qld.gov.au 61272084711
Lauren Berg sip:lauren.b@scenicrim.qld.gov.au 61272084711
Local Disaster Coordinator sip:ldc@scenicrim.qld.gov.au 61272084711
LDCC Admin sip:ldccadmin@scenicrim.qld.gov.au 61272084711
LDCC Logistics sip:ldcclogistics@scenicrim.qld.gov.au 61272084711
LDCC Media sip:ldccmedia@scenicrim.qld.gov.au 61272084711
LDCC Operations sip:ldccoperations@scenicrim.qld.gov.au 61272084711
LDCC Planning sip:ldccplanning@scenicrim.qld.gov.au 61272084711
LDCC Planning 1 sip:ldccplanning1@scenicrim.qld.gov.au 61272084711
LDCC Room Manager sip:ldccroommanager@scenicrim.qld.gov.au 61272084711
Lea Schuster sip:lea.s@scenicrim.qld.gov.au 61272084711
Leah Slater sip:leah.s@scenicrim.qld.gov.au 61272084711
Leanne Burnett sip:leanne.bu@scenicrim.qld.gov.au 61272084711
Leanne Smith sip:leanne.s@scenicrim.qld.gov.au 61272084711
Leisa Ferguson sip:leisa.f@scenicrim.qld.gov.au 61272084711
Liam Cahill sip:liam.c@scenicrim.qld.gov.au 61272084711
Libby Murphy sip:libby.m@scenicrim.qld.gov.au 61272084711
Lily McArthur sip:lily.m@scenicrim.qld.gov.au 61272084711
Linda Kraat sip:linda.k@scenicrim.qld.gov.au 61272084711
Linda Phillips sip:linda.p@scenicrim.qld.gov.au 61272084711
Linda Roderick sip:linda.r@scenicrim.qld.gov.au 61272084711
Lisa Caruana sip:lisa.c@scenicrim.qld.gov.au 61272084711
Lisa Hearn sip:lisa.h@scenicrim.qld.gov.au 61272084711
Lisa Kerrison sip:lisa.ke@scenicrim.qld.gov.au 61272084711
Lisa Stubbs sip:lisa.s@scenicrim.qld.gov.au 61272084711
Liz Roberts sip:liz.r@scenicrim.qld.gov.au 61272084711
Luchia Willows-Keetley sip:luchia.w@scenicrim.qld.gov.au 61272084711
Luke Anthony sip:luke.a@scenicrim.qld.gov.au 61272084711
Luke Cadwallader sip:luke.c@scenicrim.qld.gov.au 61272084711
Luke Vogler sip:luke.v@scenicrim.qld.gov.au 61272084711
Lyle Venz sip:lyle.v@scenicrim.qld.gov.au 61272084711
Lyndal Coote sip:lyndal.c@scenicrim.qld.gov.au 61272084711
Lynne Bell sip:lynne.b@scenicrim.qld.gov.au 61272084711
Madi Law sip:madi.l@scenicrim.qld.gov.au 61272084711
Malav Patel sip:malav.p@scenicrim.qld.gov.au 61272084711
Margie Jackson sip:margie.j@scenicrim.qld.gov.au 61272084711
Marie Scott sip:marie.s@scenicrim.qld.gov.au 61272084711
Marisa Parker sip:marisa.p@scenicrim.qld.gov.au 61272084711
Mark Carter sip:mark.c@scenicrim.qld.gov.au 61272084711
Mark Duncan sip:mark.d@scenicrim.qld.gov.au 61272084711
Mark Lohmann sip:mark.l@scenicrim.qld.gov.au 61272084711
Mark Ludwig sip:mark.lu@scenicrim.qld.gov.au 61272084711
Mark Paddick sip:mark.pa@scenicrim.qld.gov.au 61272084711
Mark Slingo sip:mark.sl@scenicrim.qld.gov.au 61272084711
Mark Stevens sip:mark.st@scenicrim.qld.gov.au 61272084711
Marnie Young sip:marnie.y@scenicrim.qld.gov.au 61272084711
Cr Marshall Chalk sip:marshall.c@scenicrim.qld.gov.au 61272084711
Matt Arnold sip:matt.a@scenicrim.qld.gov.au 61272084711
Matthew Blane sip:matthew.b@scenicrim.qld.gov.au 61272084711
Matthew Creedy sip:matthew.c@scenicrim.qld.gov.au 61272084711
Matthew Funnell sip:matthew.f@scenicrim.qld.gov.au 61272084711
Maverick Wells sip:maverick.w@scenicrim.qld.gov.au 61272084711
Megan Gilloway sip:megan.g@scenicrim.qld.gov.au 61272084711
Melanie Beach sip:melanie.b@scenicrim.qld.gov.au 61272084711
Melissa Connerty sip:melissa.c@scenicrim.qld.gov.au 61272084711
Melissa MacPherson sip:melissa.m@scenicrim.qld.gov.au 61272084711
Melissa Messina sip:melissa.me@scenicrim.qld.gov.au 61272084711
Melissa Quast sip:melissa.q@scenicrim.qld.gov.au 61272084711
Melissa Ryan sip:melissa.r@scenicrim.qld.gov.au 61272084711
Cr Michael Enright sip:michael.e@scenicrim.qld.gov.au 61272084711
Michael Gill sip:michael.g@scenicrim.qld.gov.au 61272084711
Michael Wolf sip:michael.wo@scenicrim.qld.gov.au 61272084711
Minh-Man Nguyen sip:minh-man.n@scenicrim.qld.gov.au 61272084711
Miranda Collins sip:miranda.c@scenicrim.qld.gov.au 61272084711
Miriam Nyrene sip:miriam.n@scenicrim.qld.gov.au 61272084711
Monica Massey sip:monica.m@scenicrim.qld.gov.au 61272084711
MR Teams Test sip:mrteamstest@scenicrim.qld.gov.au 61272084711
Nada Mallinson sip:nada.m@scenicrim.qld.gov.au 61272084711
Narendra Singh sip:narendra.s@scenicrim.qld.gov.au 61272084711
Natika Dendle sip:natika.d@scenicrim.qld.gov.au 61272084711
Nichole Matheson sip:nichole.m@scenicrim.qld.gov.au 61272084711
Nick Payne sip:nick.p@scenicrim.qld.gov.au 61272084711
Nicky Hannigan sip:nicky.h@scenicrim.qld.gov.au 61272084711
Nicole Azzopardi sip:nicole.a@scenicrim.qld.gov.au 61272084711
Nicole Williams sip:nicole.w@scenicrim.qld.gov.au 61272084711
Nikki Blyton sip:nikki.b@scenicrim.qld.gov.au 61272084711
Noel Todd sip:noel.t@scenicrim.qld.gov.au 61272084711
Noni Howells sip:noni.h@scenicrim.qld.gov.au 61272084711
Oliver Pring sip:oliver.p@scenicrim.qld.gov.au 61272084711
Olivia Pennell sip:olivia.p@scenicrim.qld.gov.au 61272084711
Ormnorth Ly sip:ormnorth.l@scenicrim.qld.gov.au 61272084711
Owen Sweeney sip:owen.s@scenicrim.qld.gov.au 61272084711
Patricia Ryan sip:patricia.r@scenicrim.qld.gov.au 61272084711
Paul Gillen sip:paul.g@scenicrim.qld.gov.au 61272084711
Paula Leigh sip:paula.l@scenicrim.qld.gov.au 61272084711
Pedro Pascon Da Paz sip:pedro.p@scenicrim.qld.gov.au 61272084711
Peter Allan sip:peter.a@scenicrim.qld.gov.au 61272084711
Peter Blyton sip:peter.b@scenicrim.qld.gov.au 61272084711
Peter Kropp sip:peter.k@scenicrim.qld.gov.au 61272084711
Phil Day sip:phil.d@scenicrim.qld.gov.au 61272084711
Pauline Wimmer sip:polly.w@scenicrim.qld.gov.au 61272084711
Pravin Menon sip:pravin.m@scenicrim.qld.gov.au 61272084711
Racheal McNiven sip:racheal.m@scenicrim.qld.gov.au 61272084711
Rachel Baldwin sip:rachel.b@scenicrim.qld.gov.au 61272084711
Ray King sip:ray.k@scenicrim.qld.gov.au 61272084711
Rayhan Shabbir sip:rayhan.s@scenicrim.qld.gov.au 61272084711
Raylene Jensen sip:raylene.j@scenicrim.qld.gov.au 61272084711
Rebecca Dalton sip:rebecca.d@scenicrim.qld.gov.au 61272084711
Rebecca Fitzpatrick sip:rebecca.f@scenicrim.qld.gov.au 61272084711
Rebecca Reilly sip:rebecca.r@scenicrim.qld.gov.au 61272084711
Renaee Johns sip:renaee.j@scenicrim.qld.gov.au 61272084711
Renee Wallace sip:renee.wa@scenicrim.qld.gov.au 61272084711
Rhiannon Taylor sip:rhiannon.t@scenicrim.qld.gov.au 61272084711
Richard Hancock sip:richard.h@scenicrim.qld.gov.au 61272084711
Richard Seddon sip:richard.s@scenicrim.qld.gov.au 61272084711
Rick Hotz sip:rick.h@scenicrim.qld.gov.au 61272084711
Robyn Cahill sip:robyn.c@scenicrim.qld.gov.au 61272084711
Robyn Fortescue sip:robyn.f@scenicrim.qld.gov.au 61272084711
Robyn Ryan sip:robyn.r@scenicrim.qld.gov.au 61272084711
Ross Kroll sip:ross.k@scenicrim.qld.gov.au 61272084711
Rylie Appleyard sip:rylie.a@scenicrim.qld.gov.au 61272084711
Santosh K C sip:santosh.kc@scenicrim.qld.gov.au 61272084711
Sarah Berg sip:sarah.b@scenicrim.qld.gov.au 61272084711
Sarah Foley sip:sarah.f@scenicrim.qld.gov.au 61272084711
Sarah Tracey sip:sarah.t@scenicrim.qld.gov.au 61272084711
Sarita King sip:sarita.k@scenicrim.qld.gov.au 61272084711
Scott Osman sip:scott.o@scenicrim.qld.gov.au 61272084711
Scott Oberle sip:scott.ob@scenicrim.qld.gov.au 61272084711
Scott Williams sip:scott.w@scenicrim.qld.gov.au 61272084711
SESEOC2 sip:seseoc2@scenicrim.qld.gov.au 61272084711
SES Local Controller sip:seslocalcontroller@scenicrim.qld.gov.au 61272084711
Shane Gillett sip:shane.g@scenicrim.qld.gov.au 61272084711
Shane Marks sip:shane.m@scenicrim.qld.gov.au 61272084711
Shane Rooks sip:shane.r@scenicrim.qld.gov.au 61272084711
Shantel Turner sip:shantel.t@scenicrim.qld.gov.au 61272084711
Sharyn Keepence sip:sharyn.k@scenicrim.qld.gov.au 61272084711
Shaun Anderson sip:shaun.a@scenicrim.qld.gov.au 61272084711
Shaun Coleman sip:shaun.c@scenicrim.qld.gov.au 61272084711
Shaun White sip:shaun.w@scenicrim.qld.gov.au 61272084711
Shaun Wrigley sip:shaun.wr@scenicrim.qld.gov.au 61272084711
Shona Vines sip:shona.v@scenicrim.qld.gov.au 61272084711
Simon Hitchins sip:simon.h@scenicrim.qld.gov.au 61272084711
Skype Test sip:skype.t@scenicrim.qld.gov.au 61721399723
Sonja Roots sip:sonja.r@scenicrim.qld.gov.au 61272084711
Stephen Boyd sip:stephen.b@scenicrim.qld.gov.au 61272084711
Stephen Bell sip:stephen.be@scenicrim.qld.gov.au 61721399723
Stephen McCauley sip:stephen.m@scenicrim.qld.gov.au 61272084711
Steve Aird sip:steve.a@scenicrim.qld.gov.au 61272084711
Sudheer Payyapatt sip:sudheer.p@scenicrim.qld.gov.au 61272084711
Susan Packer sip:susan.p@scenicrim.qld.gov.au 61272084711
Susan Wynne sip:susan.w@scenicrim.qld.gov.au 61272084711
Sylvia Swalling sip:sylvia.s@scenicrim.qld.gov.au 61272084711
Tara McManus sip:tara.m@scenicrim.qld.gov.au 61272084711
Tara Wallace sip:tara.w@scenicrim.qld.gov.au 61272084711
Taylor Kirkwood sip:taylor.k@scenicrim.qld.gov.au 61272084711
Tegan Smith sip:tegan.s@scenicrim.qld.gov.au 61272084711
Terence Harvey sip:terence.h@scenicrim.qld.gov.au 61272084711
Terry Hotz sip:terry.h@scenicrim.qld.gov.au 61272084711
Terrance Richter sip:terry.r@scenicrim.qld.gov.au 61272084711
Tia Bun sip:tia.b@scenicrim.qld.gov.au 61272084711
Tickets BD sip:tickets.bd@scenicrim.qld.gov.au 61272084711
Boonah Cultural Centre - 3068 sip:tickets.bh@scenicrim.qld.gov.au 61272084711
Timothy Bewert sip:timothy.b@scenicrim.qld.gov.au 61272084711
Timothy Sutcliffe sip:timothy.s@scenicrim.qld.gov.au 61272084711
Tamborine Mountain Front Desk 3 5473 sip:tmfd5473@scenicrim.qld.gov.au 61272084711
Tony Stanfield sip:tony.s@scenicrim.qld.gov.au 61272084711
Trevor Draude sip:trevor.d@scenicrim.qld.gov.au 61272084711
Velda Matthews sip:velda.m@scenicrim.qld.gov.au 61272084711
Vili Masibilo sip:vili.m@scenicrim.qld.gov.au 61272084711
Viral Patel sip:viral.p@scenicrim.qld.gov.au 61272084711
Cr Virginia West sip:virginia.w@scenicrim.qld.gov.au 61272084711
Vivienne Musch sip:vivienne.m@scenicrim.qld.gov.au 61272084711
Warren Neinert sip:warren.n@scenicrim.qld.gov.au 61272084711
Wayne Mahoney sip:wayne.ma@scenicrim.qld.gov.au 61272084711
Workplace Health and Safety sip:whs@scenicrim.qld.gov.au 61721399723
Yoni Rankin sip:yoni.r@scenicrim.qld.gov.au 61272084711
Zane Bettridge sip:zane.b@scenicrim.qld.gov.au 61272084711
PS C:\WINDOWS\system32> #Set all Audio Conference user's
Set-CsOnlineDialInConferencingUser -ServiceNumber 61721399723
# To see result
get-CsOnlineDialInConferencingUser ¦ Select DisplayName, SipAddress, DefaultTollNumber ¦ Sort-Object -property SipAddress ¦ FT
cmdlet Set-CsOdcUser at command pipeline position 1
Supply values for the following parameters:
Identity:
PS C:\WINDOWS\system32> get-CsOnlineDialInConferencingUser ¦ Where-Object {$_.servicenumber -eq 61272084711} ¦ %{Set-CsOnlineDialInConferencingUser -identity $_.sipaddress.substring(4) -ServiceNumber 61721399723}
#Set-CsOnlineDialInConferencingUser -ServiceNumber 61721399723
# To see result
get-CsOnlineDialInConferencingUser ¦ Select DisplayName, SipAddress, DefaultTollNumber ¦ Sort-Object -property SipAddress ¦ FT
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : eaf43ff3-a943-41d3-8bb2-c3b309065aa4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:dean.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 625dc158-78f5-4800-b873-86dae263d3bc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:luke.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7b8d5005-a170-4214-9fda-08bc5cf15f01
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jennifer.st@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : dccbf8fb-6ffc-42ac-93df-de750f23137f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shaun.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 61f976bc-4d3b-4ca3-b252-3b29fca1a9b1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:christopher.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a5e362fb-fc13-4b47-8a89-f98e3830413d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:oliver.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c4e331ad-baeb-4ae7-8220-2ce2ad371b0e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:debra.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b32a8e63-c6f5-4c6f-b9ef-ab82fc85b9c3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sharyn.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a64348e4-5631-4703-b0f6-d3dbee8460cc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:caroline.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7c110a23-2725-443f-bdb2-ac948b6ff3b7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:dee.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4c4226ba-b428-4bc8-8c14-a1dc14fb1ea5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:linda.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 62085fb8-aea1-4325-b934-4b2ea854de8b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:james.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9c246908-9c0d-421b-99bf-74e2b8ae9dda
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melissa.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7eb5dc79-f454-4336-964c-014cff43250f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kate.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1adf0127-a0b7-4c4f-8405-ade6fa3da34d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:natika.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f954c436-2838-425c-9999-4b7d0dbf389f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:alana.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4e540b4f-1189-404f-9657-cf659504ed53
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:joel.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cd12ca0f-eb3c-4c4f-9ed8-5d6b67c0e687
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jon.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3bfaec2c-1763-41d0-9c66-503035f1f7d7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:julie.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2561e79c-33b9-4d1d-bb88-fcb4902b9752
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jo-ann.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3df408c5-5df8-4cc7-aa38-01794e4169ea
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jamie.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a49f7d1a-b337-43dc-97a1-59c77afd332c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carolyn.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 73ec19e1-2dd1-41d5-a094-a2c8954e2dd6
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:billie.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 67c956b9-a13f-4c71-ae0f-1aa1dea52eea
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:santosh.kc@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1735bd63-5096-419e-9fdf-6d6d5a6467ce
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:grace.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 187afc70-4bdc-4197-b56b-948b50cc72a0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jaime.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7f1c6a29-e6db-4507-81e4-f32571c4fe1b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shaun.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 316920f5-5a36-407d-9bb6-20074c5fe4e5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carleen.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e5af8482-865f-492b-8b62-16f6f7d61ecd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carly.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 469efbe3-febb-40d3-b111-28fb416f140a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:holly.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 38c5058c-3176-4c88-8800-6ce73276047a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:matthew.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6b4f8510-bc1c-4bf2-bc9e-4ecd1159dbc1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lana.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f727fd63-dda7-485a-ad83-9242bf221feb
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:vili.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5818e720-b445-471b-8424-07816bfa999f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:allen.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8857f726-9943-47cd-9d90-4447be11f256
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tara.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0068bf0b-c6e6-4b37-8ec0-f19bc433d061
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:leah.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : dd6aef71-ab62-4cf1-891f-43ef30b11584
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rebecca.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f5b69331-d832-4f3d-bda7-c8df90d2ce65
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:hazel.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1d6d5bad-3a5a-4994-98d1-4548da565ba1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shantel.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7f1a00d3-cb4c-412e-9112-6331917ffe5c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jacob.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b2320f73-6971-4eb4-bd5d-fc464d9e39af
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:pravin.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : aa18562c-c454-46cb-ab38-356849136861
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:monica.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 10621fea-09ec-4235-9d2b-01e508b4228f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:laura.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0f598334-3229-49e1-8d89-3abc6f816c1e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lara.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ab1c5c10-dfef-471a-9d36-a0dd9110fe8a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:craig.mc@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : db6fc0e8-7f48-4596-9063-cbbacfdd8a7e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:donna.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e836c03e-3721-495f-8dda-28dd13c0cefa
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:hera.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 99444143-0939-46ed-906f-5b5d6c06b6e9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:frank.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 23cb5927-a45c-46a3-b92a-b8f501e2a12e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:byron.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a0281570-d916-4760-9bac-2748021346ce
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kirby.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 434a5866-8700-4370-afeb-27dd13eed4ad
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.ma@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b69fec7c-a495-4b21-bd35-4f8d6f66db4f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jo.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1e1d8b4a-1135-43f9-8ea2-537d1b2af5e6
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tara.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7b203cad-3042-47dd-88c1-dec30fdb0735
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:simon.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6df76f5a-72d3-47e0-9588-8ad869ca3697
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:adrian.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 02b0b1cf-ecc6-4360-9368-3bb619f3f9dd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:robyn.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 94adde5f-111e-4c4c-8dac-c3307255f262
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nada.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 67e1e695-ca70-4a83-9590-93c8ddd8e180
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:linda.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2b6f5dce-e110-45a6-a4aa-c002b514b2fe
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:velda.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5b8ae25d-157d-4fd2-9f54-9d84735b4f5f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:minh-man.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d4c29c37-e352-4a7a-837c-26092681383d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nicole.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 55bc8192-3b5a-4412-8409-e0ea2fd508c8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:john.ke@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9d902f69-84b7-40fa-8873-b6022279cee3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:alisha.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e95c9d8d-9848-4f35-8cdc-d734932ee4f1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:viral.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 923ba962-912c-49ab-9922-6624f11d99be
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:david.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d6934c0a-afd9-4afc-9a19-78a0c783baa8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ellie.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : eb288580-1d7d-4ec7-9445-2f89dd60653f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:noni.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 180605c9-f1b1-479a-a4e5-19304efd3ed5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kelli.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 17f068dd-9219-4b13-aed2-8d2a06c25464
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:marie.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1b8cb73c-58c0-4cb1-8504-e33abf35bf18
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:susan.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1747076f-e40c-4a9d-aa4f-1b86a023f37b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:robyn.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 15306f97-d4d0-431c-913c-4ad2b8a3d448
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jeff.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1bb5abd9-8f90-42ca-82bb-4121112a8af5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sarita.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1de3151e-ef0b-42a1-8f31-97b64cebe36b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ingrid.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 178bbf0d-bded-48c3-a402-454687506a46
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:india.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 149e3754-2fb5-4739-83df-296db459c66a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jodie.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 11a39c50-b1af-472b-87cb-6370f18a4df6
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:deanna.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1887ddfd-2f76-42f2-9765-f14b289d58aa
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lacey.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 17e0ca0f-72dc-4028-8a0f-e37277aa1151
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:bcc5060@srrc.onmicrosoft.com
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1bef6361-51bb-48a9-90db-0526e92cc38a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:greg.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1220ed2f-9fac-40ea-a707-23e07e9d01f9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jarrod.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 24ccaadb-25ee-4e22-9dd0-1985e9c3b915
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:krystal.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2d3a8137-57aa-4231-8e28-073807e494b9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:peter.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 287a8d07-d12f-4866-8076-d469265157d2
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:noel.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 27b2f8f7-38ca-4a45-aace-19064aba2233
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:donnalee.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 20674bee-88f2-4e29-bc6b-3ea82be6c508
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:doug.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 212c2f20-d007-45a7-832f-458856c3a251
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:paula.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2ca29c6e-041e-48c2-b84e-e1a4a0405321
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:catherine.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2ef8f43e-4c11-4a07-82be-5e86d4e69329
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rhiannon.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2ffc99a6-c9de-4449-90d9-a40a1c16072b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 280d807f-ec4c-4e1d-ba13-fa292baea8c2
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:seslocalcontroller@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2da7fa01-f7a5-4a2b-8261-546456d9174f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:luchia.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2ff5cd1e-9bc6-4430-a6cd-5aa04a31be88
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:damian.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 27c8fc26-03c1-4582-95ed-e514d420a848
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:debbie.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 24b761ee-8499-49a5-9925-baa44c5bc602
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:maverick.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 386ebab8-4603-464d-95d2-56c3aa634aff
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brad.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3d43a993-a048-4e8d-be1f-ebcc474a186a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.pa@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 32114e6d-070d-4418-9eb0-287e733f43bc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:isabel.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3c585292-6e28-4e0f-b85a-5df23b634b08
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jeremy.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 37b44ea2-0b67-459c-810a-df6f0440e412
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:phil.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3f319e89-a0d3-4922-a681-8f54aeae1cf5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:duncan.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3e36dbb9-d753-42bc-bd5d-9cdd012d455e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:hr@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 301aca46-32a8-45b0-9a5f-b03c0797dfc0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:steve.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 311c0f1e-0f93-46c1-9647-157cc1b9df55
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brenda.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 32ef4911-aa18-47f5-b7b0-7a3114b4947d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:renaee.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 351e329b-f13e-4afc-9fb4-6403e7ff8a96
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shane.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 376dc2b9-8474-4d79-849f-0b53f3701379
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:darren.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3b81c4f4-3709-4569-861e-3bcee8d71c66
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carmel.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3cd7bfff-5d65-41fd-b323-3b86b67e66a0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nick.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 31f17932-2c92-414b-a0c0-6f4f94e73b19
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:danni.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 30b4c0b4-cb09-4717-9a6f-48bb89b5b469
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jodie.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 38e0cc02-2118-48a7-81f4-ab28a94d0278
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lyndal.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 57e808bb-f217-4fdd-bc2b-b00393d89753
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:chantal.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 43f13dac-ec39-47bd-8da2-5e8f61108471
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:vivienne.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 43e4c563-c908-40d5-801f-8361734475ad
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brian.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 44081fc0-9bab-474b-b27b-2809523c0bab
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:julia.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4ad3bfbc-9b00-4cf9-b120-eeea3e970fe3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:adrienne.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4a088eba-7b1a-408a-b3e4-f6cbb5ca267a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lisa.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 448bebd7-8848-4066-a262-9415300e2dbe
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:joanne.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4e9696ba-e819-4b7d-8879-108fdcae3349
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jodie.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4452ce5c-53ec-49bf-bd7c-7325fbf9eed8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jared.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4ef3f73c-7fef-4150-a402-b049f291b14e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:leisa.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4b074740-7a58-40e5-ae7d-29e3aa92ea4b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccadmin@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5fad5bd7-a904-413f-b599-88b9412479f9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kevin.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5398403a-380f-4bd9-bf3b-3faf79837f51
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:craig.he@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 561244b0-a27a-42fa-a56b-7d76eb5c9589
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:christy.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 529af107-609c-4bcf-98f4-cb29f28a7778
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:julien.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5d0e7938-1713-4471-853a-9a0350a23913
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kylee.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 527ca847-5969-4eb4-9bcf-cc4667b90f21
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rachel.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5cea2a77-ab99-4e56-8828-a3e8cc5706dc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jeremey.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5a201024-dc2c-4497-9950-345e93c4084a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:terence.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5862e864-0436-49bf-85d9-79e06cc81965
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rebecca.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 59453873-ee7e-4ef8-8a68-eb30a628f18e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:bcc5051@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5d8727c7-fac5-4589-a2e7-7de255b0d198
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:heather.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 52f98667-93de-40a2-b25a-b6619fcafd2a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:david.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 513afda8-b3a3-4ee0-afea-2187b5cc110c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:joanne.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 50a4d148-d1e1-4430-bd81-40871e2149bd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sarah.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6afde13d-2109-4d08-b314-5c7b4dff0eab
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:michael.e@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 694fc0c6-e799-4a2f-b70d-ca73b41666b5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tickets.bd@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 63706fb0-2176-4e33-9952-f27f26dfe964
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:warren.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 67250e05-c4d5-4c48-90dc-1f7868b49ad7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lyle.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6c0fc292-d98d-4814-9d10-d40132514ff0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:boonah.frontdesk1@srrc.onmicrosoft.com
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 69ea5e31-24d8-4123-8013-2caecd4c9a9f
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jackie.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6ae7e9ed-949b-4a29-9b1d-12ceb34f27cc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:desley.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6afff8c2-b38a-47be-8da6-ec11e860dcc1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:stephen.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6a0800d4-a4cc-4585-9535-99953bb3ba8d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sarah.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6e953361-cc11-4d2f-963c-405bc022bdb8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:donna.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 63ebf30d-c5d1-499e-b82e-4b9b16558c24
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:daniel.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 61e50850-858f-441b-906b-b72c1aa1e581
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:zane.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 6aebbec7-cabb-4f64-9f81-26783f26b6e5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:marshall.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 656b42c6-562a-462f-b7da-3e74f1dfda16
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nicole.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 666a7775-989d-4a96-ae4d-eed8812dce1b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:gail.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 68d0314f-5b2c-4e40-a411-1260a3d5e3d5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:catherine.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 75063bd8-5bcb-4278-baa9-198bd40c389a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:emma.th@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 74f46820-deeb-4857-8964-6861da921124
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brett.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7ed75e83-1fa6-4f24-b1a8-4c49ee5b7b2d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rick.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 788b09a5-9c58-4a25-81a1-17078effdf02
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccroommanager@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 71edbfed-ebc0-463f-8d7b-989e2690f716
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tickets.bh@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 72085730-61fc-4830-a85d-a8983e7ded38
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 71431d96-e71f-4a57-bf7f-63563f8f7dce
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jan.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7f9f0848-48b9-484c-9eca-c7f5c0e68e98
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tia.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 73cde434-7bed-4101-bd53-5ea617974a6b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccoperations@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7943c2ef-d37f-4c1a-be94-9bf78f4d2a18
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:julie.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7b0bce07-6178-40db-bd31-ada29ed55bcd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:craig.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 71b12814-272b-4cd8-8bad-aa615bc815f6
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.lu@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7125cca1-ebc3-4d26-948d-bcdd1794d202
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:dean.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7decdcce-d643-4cf6-ad68-97c4f949c669
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carmen.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 718319f6-1433-4a6f-9f51-ead4cb653965
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:judy.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7ab0c3ea-f267-486f-ae9d-8c0ee34d0962
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jessica.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 880aa536-58ec-43c5-b64b-2f87ee19c3f8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:wayne.ma@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9edea709-c2b6-434a-9fe7-039028b3e6fc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:justin.si@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 88906ce8-187d-40a8-b0d1-a9989a140770
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kobi.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 81ae8c7d-ee6b-433b-b6a6-503747112cb7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:scott.ob@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8eac4f66-7458-4014-b1aa-78bb35dc5329
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rylie.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8e653ec2-feac-4784-b6e6-6d2f7ad0c46d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ray.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 80f51377-d038-41ff-a244-cf9fc2727b2a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lisa.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 882c17f2-d50a-4644-bf15-41bf5a376360
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lauren.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8915e633-92fc-492e-ba12-254a6c5ba4ca
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jason.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8db35b91-a98a-4faa-95c6-f53380bd6c68
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:racheal.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8a17afc9-dbc0-4a9b-b5cc-6d0c43c05802
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:margie.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 845d1649-c455-4b1f-a5fe-8dbddac0046d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:robyn.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 85e15f28-2645-42a5-b4d1-9d17a66df303
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amanda.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8454af82-46b7-4c1a-941d-7f685159c4cc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:liz.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 865aa341-c211-4432-be74-9062ce135b76
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:graham.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8a0414f3-1b33-43d3-86a1-12b815975a93
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:linda.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8424ff33-c89a-40a8-838a-0a954bbac59a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shaun.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8915f87a-1c71-43a9-808f-a3b7fe3e4ba4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:bronwyn.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 85567984-ea88-43e0-8e74-01cd3a7a6437
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jason.y@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 82407ed1-4b5b-43cf-a52d-a4c030471509
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldc@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b18cd901-c8f0-4d71-b368-b2f62e60be44
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sarah.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9aeaceab-178b-44ff-af96-3ac1e73345e7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ormnorth.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 971bda61-869f-48ff-8afa-3a562f3321ce
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.cu@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9e8c7e48-8a80-4884-acf8-7ce095113e07
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:adam.ma@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 94b439d5-b644-4ac9-80ed-dd6bf99e623c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amanda.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 99544cfc-9342-421e-93f1-f60e422fc358
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ben.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 971f1a26-66a0-478b-9160-f4b82d725793
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lynne.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 98b8d8d1-525d-4394-a46d-ba9e6cd2b9db
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:justin.st@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9c6efc83-d521-4e29-905d-5ff897b7b5c7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:terry.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 9c8aac45-b1cb-4f50-acdb-fbc3e32dd621
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kathy.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 94ab5186-d893-4619-9ddf-295a75a8342d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:georgina.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0f4f76ff-532b-454a-bfbb-6369a418fbb0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:claire.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0e1b6edb-d298-4465-98b3-e686f410c94c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:justin.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 036bf567-48af-40af-a03c-1e8dfb74dc26
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:alisa.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0713e7d8-f786-4bb9-9baf-718554362b26
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amanda.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0377f58a-3049-4020-8c30-857d78fc35b0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jeff.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 012fe637-d4f6-4d33-9dfa-9963af5ddf80
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:timothy.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0463f5a1-30b1-47df-a689-ba2263231e17
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:karen.br@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0bc78846-203f-47ab-abd4-1232bacafe15
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sonja.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0321a783-eb5c-4f19-b3b8-001ea46653dc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jane.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0de833ff-6c14-40ef-a6f6-2cfff2b70fb7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:libby.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0f7fe906-0c8f-4bee-aade-f0727dd80d19
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0083e095-d136-492d-ba24-9d1cb5e9c159
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:cindy.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0f1369a1-34c0-4342-94c8-578425022d82
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:madi.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 077c4087-f414-4b2a-b548-83b05dad1314
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melissa.me@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 042c4f6a-8fd7-4df1-88c4-84719d3ff60a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 02caa1f4-56a9-44d4-a9f4-482a2028271a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nicky.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0c2e28d9-4de0-4cce-a349-ee12c3c3ce59
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccplanning@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0445a97b-2848-4f54-ad82-4418b1dd302e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:owen.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 05aa04c2-f6e6-4766-aaef-fda1abb99472
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:terry.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0a6bf67a-8782-4cd3-afd9-5dab30300e30
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:insync@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0cf15867-5b86-4994-9988-78009662d2aa
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:katrina.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0a335fce-779c-4844-a824-b4fab1754dda
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lisa.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 09d0a436-a4f0-4dbb-8025-003ea4524e9a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:timothy.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 00425226-c805-43cd-a093-e4aa928f7f78
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:elva.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 04bb3576-1a84-4ca6-ad79-13744065689a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:anastasia.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a543b96b-6d28-42d4-a58c-08a8d14ef340
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jairo.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a87831c0-d137-4618-98c4-d0968b7c5bf2
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:narendra.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a62e4971-0e1f-4c26-8298-ffa57f330364
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kelly.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a958fa06-f2e0-4d85-9659-e455dbd79bac
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:charlie.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ab094781-40eb-4efd-b71f-d54070723ad4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:chris.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a18c44cf-124f-4ae4-89ba-678b331ea9ae
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:gerald.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a1f88a66-a24e-4d19-a31f-2c1a940e7e40
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:irene.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a9668c36-90f7-4c08-a5c0-607beaed36d4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lea.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a6545ab1-cc17-4b5c-b7d1-d8a1d1866e80
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:debra.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ae414260-b6bd-4a53-ba57-8303986eea02
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:cheryl.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ab55d2ab-d32c-4310-90d1-429b484977bf
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amy.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : abe46580-f952-40a5-bd7d-77b9b3ec436b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kylie.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a77baec9-e3f1-4d12-861e-c211d7a1eb0a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shane.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a5af802f-7c02-4000-ae06-36d75d9d91a9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:blake.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : abeada68-9da4-4b92-b47b-9503fadb3934
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:liam.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ae00fc65-26d8-4721-a00f-2483320a4fae
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:greg.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a2394b3f-b364-41ac-ac97-819167addc06
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melissa.q@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ae7ac31f-fac0-4a94-baf3-064e1dc235d5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:stephen.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ae2f0179-f49a-47da-9de7-81051f2b9f6a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:deeanne.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a4a06601-18fc-41d5-bb35-e6ef058eae91
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:john.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b235b4c4-cb38-4fbe-bd50-e1690743593a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:matthew.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b6f86c73-1b47-4aed-8a67-7dc7ee44ace0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lisa.ke@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ba09b2f2-2d51-47f8-8d57-667c95ff8845
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:katie.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b3f4e2d0-805c-4cf8-82c7-51edb4c5584d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:miriam.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b623b9d0-1a45-446c-8bb5-c3d6f9f701c6
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kris.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b0817bf7-be24-4ad4-94e2-ee3a71eff4ab
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nikki.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b5e15f31-0351-470d-814a-ea583f31ef3d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:daadmin@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b6ace75a-e637-443b-b88b-0ade710616d0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:gayanne.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : bcc1ea48-a5a9-4fe0-b638-ec2eb8787676
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:james.ok@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : bac3db8a-d1cf-49be-93be-fa944f319732
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:joanne.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b2796fd6-aa2a-4369-8c16-ce77e10f18d2
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:luke.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b50deecf-5494-4870-8aa6-6d8ed6b3526c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:clare.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b820cc5b-e6d9-4d75-8b70-dbc2166f593d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shaun.wr@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b5543b44-e570-4c86-b348-7ce684e95782
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:leanne.bu@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b99be0ac-432c-47d4-bd54-a794652f288a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:joseph.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ba9f0b32-ca1c-4649-ae44-0831a24f59aa
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brittany.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ce8924bf-a1cd-4b17-9997-3b19d2e9f3f4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:nichole.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c0d9356d-a19c-4d73-90e6-9934b5a814a5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:anne.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c315f580-9073-45e4-be1d-77fcc62d798a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:anthony.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c3401fe2-a2b7-47b2-87eb-33ff76e1425d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:gavin.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cc4a15cd-124e-405a-9ab8-b5135529155b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccplanning1@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c6557454-8f70-4944-a1a6-42391f869996
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldccmedia@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c21496b1-9c71-4260-99e9-afbe0f3af312
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sudheer.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cdcdd392-7722-4efa-bde6-efb592632509
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:daniel.sm@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c88ef749-94a3-432f-b3df-ab1a14711823
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:carolann.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c8069a0a-1336-4a5d-b055-e4d10b3c646d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:justin.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c6a58947-7f62-473d-991f-c25bd2529443
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tony.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ce7a8538-258a-48bb-9951-d50f9ef1a64a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:virginia.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ce0ec7b2-635f-4b91-bcaa-fb4b11088644
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:raylene.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c9624e2b-a2dd-446c-a57f-de25646f27cc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:annmarie.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cff0670b-f37f-4a8c-b7f7-f0c51cd91e5a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jodie.ma@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c7da9457-96a1-432f-bda6-7d6f3ac4c2a4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:boonah.frontdesk2@srrc.onmicrosoft.com
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c55290a5-2928-4c71-ac81-9c27e083cdcc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:james.do@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ccd71c45-220c-4a34-916c-388e989b9bf0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:scott.o@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c3cbe965-238b-4b41-99ef-f5686f657f3a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tmfd5473@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c39712ff-a22f-4b08-b209-f8e4334c80fc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:bill.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cf8b4d6e-9d08-4724-8318-01c345cb55c3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:cherece.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : cc6363dc-525f-48c9-99fc-f3f6be384e27
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:leanne.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c7ea13e9-9722-4c86-8810-66e0409a2a6d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:david.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d6a0b2ad-7f5b-4fd6-b1a6-98f9eca8180c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ross.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d1fe1def-0a50-46a8-9c02-d6befb25d676
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:matt.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d0e22b1a-3b9a-4ee9-a1e4-0ff4a54d61aa
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:cameron.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d93f9897-736c-4bda-a7aa-01d345cbca83
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jenna.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d5d2d378-996f-4660-8676-613ac4df4165
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:john.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : defe7621-59a3-4ea4-8bfe-2f43bf393838
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:cassandra.n@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d8267cdc-0c28-41ae-9522-d96c69736d72
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:pedro.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : dfd5b39a-f9b6-4498-bf61-c92c6f9fdfde
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ldcclogistics@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d182a6d0-c980-43c1-969c-9c3925b93543
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:susan.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d4db133d-ed8f-41fe-a423-46f6fca5e340
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kyle.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : daa05163-052a-4aff-948b-ec7ab024ae92
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jason.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : df66fa9b-37bc-4862-bc02-bff19abf82fc
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:miranda.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : daf18eec-15b7-478b-84c7-d79ad58f444d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:anna.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e1c42c02-f380-4e0a-a763-b2ae2be91dc9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melissa.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e3e22640-f2c3-4796-95c3-e9f6636601a2
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amanda.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e1fff859-eefa-46e5-b7e6-3cb6b61ebb50
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:integrity@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e2803ca0-4a02-406f-8987-99a03fd2b434
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e743c09b-a11b-45a3-881f-3435e5ab9c9c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:judith.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ebff8fe4-bd02-42c0-87a4-4f1710dd414c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:brad.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e6ca051f-fd8a-4ef2-a1c6-0f200baf04f0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:marisa.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e10ac5a0-1c62-47f7-9bfd-ad0f785726cf
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:olivia.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ee7008b5-8838-46e9-9482-569b954b10dd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:tegan.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e00a8431-4fd6-4b54-8271-95227318a350
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:polly.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ec48b2d3-d89b-42e2-8da1-6fd2303f18d8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.st@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : ee0e44cf-0533-4371-b203-11b821ff788a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melanie.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f4af7a53-4169-4895-b595-d2513f84316a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:julia.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fb947e42-2f3c-471d-b36d-98c4c9c9e6bf
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:bridget.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f983b456-c970-4905-8fe8-5d41f63a1131
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:info_moogerah@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fe910d7b-1a17-45c4-9415-f00bec243417
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:richard.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f6b849fe-c932-497c-9aec-58e0e3fd94f3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:craig.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fba87be8-50e8-4cfa-ad62-7a0219e5f780
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:john.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f45f9cf3-1d78-4e75-8891-4ed40dc226e3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:colin.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f2440d40-5710-4816-8b7b-0622555b4d0b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kelly.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : faa1888d-3c42-4b5a-a752-4294c4ede18e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fe67bdf4-102c-4b0b-91b0-75c1b62b3562
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:andrew.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fc6732c3-fd39-4222-a061-1a0a4df7d8fb
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:michael.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f6797562-737a-4f56-a018-fc3487e1a91d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:seseoc2@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f067060e-b484-4996-a0e0-35722124c727
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:megan.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f1f19e30-cef4-4062-945b-d410f5e21af7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jordan.t@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fb743c4a-7bd1-4c8c-879d-2ebf35d37362
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:richard.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fef0ca58-613c-4ddd-9d28-eb0b70fd2c0d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:peter.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f990cb93-6cea-4b06-9fd9-77506d2891d4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:scott.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : fa7ce4db-b534-4ef0-933b-6c3c3d9cf170
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:matthew.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c3622f3c-4522-4d98-a1b9-72f39cf70f47
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:justin.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 46731aaf-25f1-40a1-8616-9df53093970d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:michael.wo@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e6282bf6-72d0-4ce1-81d5-d81ee0e6aa27
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lau.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 29de5c19-ea6a-47d1-a527-8cf078f7a853
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:hiral.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1900fda6-55c9-48af-bc34-c2d579416da8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:clyde.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5ad5cd73-7d27-43c1-8112-55fda91810f8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:genevieve.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5119a926-4c03-4e6d-97ee-95de5917ad1e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:trevor.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8a36abff-f272-43ee-9cd8-fe261f696e38
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jason.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 29fb1a04-97b8-41c6-ac47-bd850bffaffd
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:blake.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 86c31e92-4219-486f-ae38-17754980cab8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shona.v@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4b3a71d5-add8-44e1-a736-f9d40a6aee71
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:chloe.e@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 348ca21a-2fb8-4cc4-883a-8a907b489df5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jodi.w@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 51611801-3df3-4b9c-a548-2c19884256d4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amanda.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : c15a042f-af61-4ac3-a871-f38f4e030e45
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amelia.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : bb8b6084-ca2d-4876-8830-3d87cd097e20
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jo.jo@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e88974e9-8032-43f2-81ba-8833ec03f135
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mark.sl@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 5df4fe68-8492-472b-bbc1-dfe1a9ff564b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:lily.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f1b21712-e4ce-49a7-87d1-1b9db3f49ae3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:asiful.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 65e16321-a51c-473a-848f-34a79121ef55
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:malav.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 8a82f80e-f9ce-4b67-a19f-a4b85017918b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jason.ca@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 2ed9078a-bdd2-4135-a989-05f566d24e0b
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:belinda.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 62340650-e9e1-49ae-8902-28d7a1db75c5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:patricia.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1141289f-3262-49b4-8d45-43be16ea18a0
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:mrteamstest@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f7af5e51-9abf-4384-b352-154d27241901
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:paul.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 52474e98-da74-4c9a-85d1-647b35176140
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:heerah.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1bd890d5-3a86-44b5-8d44-d082a0b3fded
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:peter.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3b0a98ab-d202-48e8-9e6d-59376aa55a8c
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kate.jo@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a41b2b07-839e-4711-ac23-3b65700c53ec
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:sylvia.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f0e8e1c2-e076-49df-95d7-aff7596e7da5
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:allyson.h@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0d64ee02-c777-4102-af82-7c80dae6fd21
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:marnie.y@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : edbeb4bc-7830-4e5a-97a2-cbdd30d23da8
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:katrina.c@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3a01c5fb-3892-4e6f-9186-3c646bad4998
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:melissa.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 96400c03-fa26-4c2c-a300-fd0e71c457f4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:adam.j@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 7c61f1de-939d-4618-8e3b-859f5c4870e9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kelmeny.f@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 552eabda-e962-46f8-83e4-b6abce286086
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:erin.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 671da79f-1c3e-42f3-b280-b74b4ae01ac4
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rebecca.d@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1daa7547-677e-4c66-841e-7a626f984077
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:drift.i@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 3ed0c461-55f0-4756-a88a-8d56efd63819
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:daniel.mc@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : df503581-0048-485c-86e5-75116ec30717
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:rayhan.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 880fce33-cb13-455e-98b3-a7d7bdd289c7
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:luke.a@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : a5bb406a-15bf-4679-8f89-0e79fad524d1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:helen.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : e4c21821-4e36-4a12-9cba-4962fd7e6b6d
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:taylor.k@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 258e58f4-c997-46ad-aee6-4006e310a321
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:shane.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 4a9fe914-5df2-41e1-aa44-03cf132510f1
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ian.m@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 81cf656d-9fad-45eb-a14e-d0344fe7ec37
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:renee.wa@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 23e59e56-f1a1-4df7-ae9f-8a3d9bf6c40a
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:yoni.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 44901b66-824f-4e97-92ce-94581bd5524e
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jane.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : f15a579d-7487-4574-804b-2e1250980706
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kym.l@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1d3860ff-9a0b-48dc-aa91-0e35cc559cf3
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:emily.b@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : d0b29982-66ca-4b9e-a202-53a18ad3e508
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:jasmine.s@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 78619969-107f-4680-bf8b-5b9e934236b9
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:kuda.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 0cfb4ae9-0bb7-4c4f-82f1-433fae206826
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amie.p@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : b30738ed-24ac-46ba-a646-bb47e6c46325
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:amy.r@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
AllowPstnOnlyMeeting :
AllowTollFreeDialIn : True
BridgeId : d8dec4e1-aee8-4e57-b8ba-948e8de3e8a9
BridgeName : Conference Bridge
ConferenceId :
DefaultTollFreeNumber :
DefaultTollNumber :
DisplayName :
Identity : 1a3fed46-f9b8-4239-8af7-016a240683de
LeaderPin : *****
ServiceNumber : 61721399723
SipAddress : sip:ann.g@scenicrim.qld.gov.au
TenantId : a2b76b3b-b366-4f97-8997-31aee9bc8618
TollFreeServiceNumber :
DisplayName SipAddress DefaultTollNumber
----------- ---------- -----------------
Adam Jordan sip:adam.j@scenicrim.qld.gov.au 61721399723
Adam Maskelyne sip:adam.ma@scenicrim.qld.gov.au 61721399723
Adrian Chan sip:adrian.c@scenicrim.qld.gov.au 61721399723
Adrienne Jeuda sip:adrienne.j@scenicrim.qld.gov.au 61721399723
Alana Bellamy sip:alana.b@scenicrim.qld.gov.au 61721399723
Alisa Totenhofer sip:alisa.t@scenicrim.qld.gov.au 61721399723
Alisha Pettit sip:alisha.p@scenicrim.qld.gov.au 61721399723
Allen Naidoo sip:allen.n@scenicrim.qld.gov.au 61721399723
Allyson Hundy sip:allyson.h@scenicrim.qld.gov.au 61721399723
Amanda Duncan sip:amanda.d@scenicrim.qld.gov.au 61721399723
Amanda Fogg sip:amanda.f@scenicrim.qld.gov.au 61721399723
Cr Amanda Hay sip:amanda.h@scenicrim.qld.gov.au 61721399723
Amanda Lewis sip:amanda.l@scenicrim.qld.gov.au 61721399723
Amanda Vinson sip:amanda.v@scenicrim.qld.gov.au 61721399723
Amelia Jibson sip:amelia.j@scenicrim.qld.gov.au 61721399723
Amie Prince sip:amie.p@scenicrim.qld.gov.au 61721399723
Amy Rogers sip:amy.r@scenicrim.qld.gov.au 61721399723
Amy Wilson sip:amy.w@scenicrim.qld.gov.au 61721399723
Anastasia Roche sip:anastasia.r@scenicrim.qld.gov.au 61721399723
Andrew Clews sip:andrew.c@scenicrim.qld.gov.au 61721399723
Andrew Cumming sip:andrew.cu@scenicrim.qld.gov.au 61721399723
Andrew Hewitt sip:andrew.h@scenicrim.qld.gov.au 61721399723
Andrew May sip:andrew.ma@scenicrim.qld.gov.au 61721399723
Andrew Richter sip:andrew.r@scenicrim.qld.gov.au 61721399723
Andrew Staines sip:andrew.s@scenicrim.qld.gov.au 61721399723
Ann Greaves sip:ann.g@scenicrim.qld.gov.au 61721399723
Anna Shera sip:anna.s@scenicrim.qld.gov.au 61721399723
Anne Baxter sip:anne.b@scenicrim.qld.gov.au 61721399723
Ann-Marie Williamson sip:annmarie.w@scenicrim.qld.gov.au 61721399723
Anthony Marshall sip:anthony.m@scenicrim.qld.gov.au 61721399723
Asiful Alam sip:asiful.a@scenicrim.qld.gov.au 61721399723
Beaudesert Cultural Centre 5051 sip:bcc5051@scenicrim.qld.gov.au 61721399723
Beaudesert Cultural Centre 5060 sip:bcc5060@srrc.onmicrosoft.com 61721399723
Belinda Jacklyn sip:belinda.j@scenicrim.qld.gov.au 61721399723
Ben Oppermann sip:ben.o@scenicrim.qld.gov.au 61721399723
Bill Kellaway sip:bill.k@scenicrim.qld.gov.au 61721399723
Billie Procter sip:billie.p@scenicrim.qld.gov.au 61721399723
Blake Bolz Brown sip:blake.b@scenicrim.qld.gov.au 61721399723
Blake Hunton sip:blake.h@scenicrim.qld.gov.au 61721399723
Boonah local Government - 3042 sip:boonah.frontdesk1@srrc.onmicrosoft.com 61721399723
Boonah Front Desk 2 3035 sip:boonah.frontdesk2@srrc.onmicrosoft.com 61721399723
Brad Freeman sip:brad.f@scenicrim.qld.gov.au 61721399723
Brad Warneminde sip:brad.w@scenicrim.qld.gov.au 61721399723
Brenda Walker sip:brenda.w@scenicrim.qld.gov.au 61721399723
Brett Fletcher sip:brett.f@scenicrim.qld.gov.au 61721399723
Brian Antcliff sip:brian.a@scenicrim.qld.gov.au 61721399723
Bridget Ponting sip:bridget.p@scenicrim.qld.gov.au 61721399723
Brittany Hawken sip:brittany.h@scenicrim.qld.gov.au 61721399723
Bronwyn Cairns sip:bronwyn.c@scenicrim.qld.gov.au 61721399723
Byron Struck sip:byron.s@scenicrim.qld.gov.au 61721399723
Cameron Thomas sip:cameron.t@scenicrim.qld.gov.au 61721399723
Carleen Orr sip:carleen.o@scenicrim.qld.gov.au 61721399723
Carly Linnertson sip:carly.l@scenicrim.qld.gov.au 61721399723
Carmel Dunn sip:carmel.d@scenicrim.qld.gov.au 61721399723
Carmen Hawken sip:carmen.h@scenicrim.qld.gov.au 61721399723
Carolann Barnwell sip:carolann.b@scenicrim.qld.gov.au 61721399723
Caroline McMahon sip:caroline.m@scenicrim.qld.gov.au 61721399723
Carolyn Gorrill sip:carolyn.g@scenicrim.qld.gov.au 61721399723
Cassandra Newsham sip:cassandra.n@scenicrim.qld.gov.au 61721399723
Catherine Kahler sip:catherine.k@scenicrim.qld.gov.au 61721399723
Catherine Madden sip:catherine.m@scenicrim.qld.gov.au 61721399723
Chantal Birt sip:chantal.b@scenicrim.qld.gov.au 61721399723
Charlie Wilson sip:charlie.w@scenicrim.qld.gov.au 61721399723
Cherece Jackson sip:cherece.j@scenicrim.qld.gov.au 61721399723
Cheryl Henderson sip:cheryl.h@scenicrim.qld.gov.au 61721399723
Chloe Elliott sip:chloe.e@scenicrim.qld.gov.au 61721399723
Chris Castle sip:chris.c@scenicrim.qld.gov.au 61721399723
Christopher Gray sip:christopher.g@scenicrim.qld.gov.au 61721399723
Christy Schloss sip:christy.s@scenicrim.qld.gov.au 61721399723
Cindy Weber sip:cindy.w@scenicrim.qld.gov.au 61721399723
Claire Dolereit sip:claire.d@scenicrim.qld.gov.au 61721399723
Clare Newland sip:clare.n@scenicrim.qld.gov.au 61721399723
Clyde Powys sip:clyde.p@scenicrim.qld.gov.au 61721399723
Colin Mackie sip:colin.m@scenicrim.qld.gov.au 61721399723
Craig Heck sip:craig.h@scenicrim.qld.gov.au 61721399723
Craig Herron sip:craig.he@scenicrim.qld.gov.au 61721399723
Craig McDougall sip:craig.mc@scenicrim.qld.gov.au 61721399723
Craig Piltz sip:craig.p@scenicrim.qld.gov.au 61721399723
Planning Business Support sip:daadmin@scenicrim.qld.gov.au 61721399723
Damian Topp sip:damian.t@scenicrim.qld.gov.au 61721399723
Daniel McNamara sip:daniel.mc@scenicrim.qld.gov.au 61721399723
Daniel Samphier sip:daniel.s@scenicrim.qld.gov.au 61721399723
Daniel Smith sip:daniel.sm@scenicrim.qld.gov.au 61721399723
Danni Moore sip:danni.m@scenicrim.qld.gov.au 61721399723
Darren Laegel sip:darren.l@scenicrim.qld.gov.au 61721399723
David Adamson sip:david.a@scenicrim.qld.gov.au 61721399723
David Keenan sip:david.k@scenicrim.qld.gov.au 61721399723
David Richards sip:david.r@scenicrim.qld.gov.au 61721399723
Dean Kibble sip:dean.k@scenicrim.qld.gov.au 61721399723
Dean Walkley sip:dean.w@scenicrim.qld.gov.au 61721399723
Deanna Fenech sip:deanna.f@scenicrim.qld.gov.au 61721399723
Debbie Salem sip:debbie.s@scenicrim.qld.gov.au 61721399723
Debra Howe sip:debra.h@scenicrim.qld.gov.au 61721399723
Debra Turnbull sip:debra.t@scenicrim.qld.gov.au 61721399723
Dee Crotty sip:dee.c@scenicrim.qld.gov.au 61721399723
Deeanne Tracey sip:deeanne.t@scenicrim.qld.gov.au 61721399723
Desley Agnoletto sip:desley.a@scenicrim.qld.gov.au 61721399723
Donna Chatfield sip:donna.c@scenicrim.qld.gov.au 61721399723
Donna Robinson sip:donna.r@scenicrim.qld.gov.au 61721399723
Donnalee Olive sip:donnalee.o@scenicrim.qld.gov.au 61721399723
Doug Hatch sip:doug.h@scenicrim.qld.gov.au 61721399723
Drift Ishter sip:drift.i@scenicrim.qld.gov.au 61721399723
Cr Duncan McInnes sip:duncan.m@scenicrim.qld.gov.au 61721399723
Ellie Barnes sip:ellie.b@scenicrim.qld.gov.au 61721399723
Elva Sykes sip:elva.s@scenicrim.qld.gov.au 61721399723
Emily Barry sip:emily.b@scenicrim.qld.gov.au 61721399723
Emma Thomson sip:emma.th@scenicrim.qld.gov.au 61721399723
Erin Powyer sip:erin.p@scenicrim.qld.gov.au 61721399723
Frank Andrews sip:frank.a@scenicrim.qld.gov.au 61721399723
Gail Keeler sip:gail.k@scenicrim.qld.gov.au 61721399723
Gavin Gotke sip:gavin.g@scenicrim.qld.gov.au 61721399723
Gayanne Kroll sip:gayanne.k@scenicrim.qld.gov.au 61721399723
Genevieve Larsen sip:genevieve.l@scenicrim.qld.gov.au 61721399723
Georgina Williams sip:georgina.w@scenicrim.qld.gov.au 61721399723
Gerald Parker sip:gerald.p@scenicrim.qld.gov.au 61721399723
Grace Roberts sip:grace.r@scenicrim.qld.gov.au 61721399723
Graham Andrews sip:graham.a@scenicrim.qld.gov.au 61721399723
Cr Greg Christensen sip:greg.c@scenicrim.qld.gov.au 61721399723
Greg Harmer sip:greg.h@scenicrim.qld.gov.au 61721399723
Hazel Malone sip:hazel.m@scenicrim.qld.gov.au 61721399723
Heather Nelson sip:heather.n@scenicrim.qld.gov.au 61721399723
Heerah Kanayar sip:heerah.k@scenicrim.qld.gov.au 61721399723
Helen Rizvi sip:helen.r@scenicrim.qld.gov.au 61721399723
Hera Li sip:hera.l@scenicrim.qld.gov.au 61721399723
Hiral Patel sip:hiral.p@scenicrim.qld.gov.au 61721399723
Holly Honey sip:holly.h@scenicrim.qld.gov.au 61721399723
HR sip:hr@scenicrim.qld.gov.au 61721399723
Ian McCarthy sip:ian.m@scenicrim.qld.gov.au 61721399723
India Breen sip:india.b@scenicrim.qld.gov.au 61721399723
Info_Moogerah sip:info_moogerah@scenicrim.qld.gov.au 61721399723
Ingrid Lawrance sip:ingrid.l@scenicrim.qld.gov.au 61721399723
insync sip:insync@scenicrim.qld.gov.au 61721399723
Integrity (Governance) sip:integrity@scenicrim.qld.gov.au 61721399723
Irene Girsch-Danby sip:irene.g@scenicrim.qld.gov.au 61721399723
Isabel Fitzgerald sip:isabel.f@scenicrim.qld.gov.au 61721399723
Jackie Lynch sip:jackie.l@scenicrim.qld.gov.au 61721399723
Jacob Okesene sip:jacob.o@scenicrim.qld.gov.au 61721399723
Jaime McLachlan sip:jaime.m@scenicrim.qld.gov.au 61721399723
Jairo Cadena sip:jairo.c@scenicrim.qld.gov.au 61721399723
James Douyere sip:james.do@scenicrim.qld.gov.au 61721399723
James O'Kane sip:james.ok@scenicrim.qld.gov.au 61721399723
James Wong sip:james.w@scenicrim.qld.gov.au 61721399723
Jamie Baker sip:jamie.b@scenicrim.qld.gov.au 61721399723
Jan Harradine sip:jan.h@scenicrim.qld.gov.au 61721399723
Jane Gough sip:jane.g@scenicrim.qld.gov.au 61721399723
Jane Skimmings sip:jane.s@scenicrim.qld.gov.au 61721399723
Jared Kranz sip:jared.k@scenicrim.qld.gov.au 61721399723
Jarrod Hunter sip:jarrod.h@scenicrim.qld.gov.au 61721399723
Jasmine Scholz sip:jasmine.s@scenicrim.qld.gov.au 61721399723
Jason Callon sip:jason.ca@scenicrim.qld.gov.au 61721399723
Jason Grimsey sip:jason.g@scenicrim.qld.gov.au 61721399723
Jason Hans sip:jason.h@scenicrim.qld.gov.au 61721399723
Jason Taylor sip:jason.t@scenicrim.qld.gov.au 61721399723
Jason Young sip:jason.y@scenicrim.qld.gov.au 61721399723
Jeff Baguley sip:jeff.b@scenicrim.qld.gov.au 61721399723
Cr Jeff McConnell sip:jeff.m@scenicrim.qld.gov.au 61721399723
Jenna Turnbull sip:jenna.t@scenicrim.qld.gov.au 61721399723
Jennifer Stockman sip:jennifer.st@scenicrim.qld.gov.au 61721399723
Jeremey Rose sip:jeremey.r@scenicrim.qld.gov.au 61721399723
Jeremy Patten sip:jeremy.p@scenicrim.qld.gov.au 61721399723
Jessica Dawes sip:jessica.d@scenicrim.qld.gov.au 61721399723
Jo Jones sip:jo.j@scenicrim.qld.gov.au 61721399723
Jo Jordan sip:jo.jo@scenicrim.qld.gov.au 61721399723
Jo-Ann Atkinson sip:jo-ann.a@scenicrim.qld.gov.au 61721399723
Joanne Downes sip:joanne.d@scenicrim.qld.gov.au 61721399723
Joanne Hayselden sip:joanne.h@scenicrim.qld.gov.au 61721399723
Joanne Morecroft sip:joanne.m@scenicrim.qld.gov.au 61721399723
Jodi Wynne sip:jodi.w@scenicrim.qld.gov.au 61721399723
Jodie McPhail sip:jodie.m@scenicrim.qld.gov.au 61721399723
Jodie Marschke sip:jodie.ma@scenicrim.qld.gov.au 61721399723
Jodie Smith sip:jodie.s@scenicrim.qld.gov.au 61721399723
Jodie Vanstone sip:jodie.v@scenicrim.qld.gov.au 61721399723
Joel Stumer sip:joel.s@scenicrim.qld.gov.au 61721399723
John Kearns sip:john.ke@scenicrim.qld.gov.au 61721399723
John Langton sip:john.l@scenicrim.qld.gov.au 61721399723
John Murphy sip:john.m@scenicrim.qld.gov.au 61721399723
John Pukallus sip:john.p@scenicrim.qld.gov.au 61721399723
Jon Rutledge sip:jon.r@scenicrim.qld.gov.au 61721399723
Jordan Tandy-Spooner sip:jordan.t@scenicrim.qld.gov.au 61721399723
Joseph Kirkwood sip:joseph.k@scenicrim.qld.gov.au 61721399723
Judith Hampson sip:judith.h@scenicrim.qld.gov.au 61721399723
Judy Jenner sip:judy.j@scenicrim.qld.gov.au 61721399723
Julia Krawitz sip:julia.k@scenicrim.qld.gov.au 61721399723
Julia Moore sip:julia.m@scenicrim.qld.gov.au 61721399723
Julie O'Neill sip:julie.o@scenicrim.qld.gov.au 61721399723
Julie Schmidt sip:julie.s@scenicrim.qld.gov.au 61721399723
Julien Parrot sip:julien.p@scenicrim.qld.gov.au 61721399723
Justin Auld sip:justin.a@scenicrim.qld.gov.au 61721399723
Justin Knudson sip:justin.k@scenicrim.qld.gov.au 61721399723
Justin Shera sip:justin.s@scenicrim.qld.gov.au 61721399723
Justin Sinnamon sip:justin.si@scenicrim.qld.gov.au 61721399723
Justin Storey sip:justin.st@scenicrim.qld.gov.au 61721399723
Karen Brooker sip:karen.br@scenicrim.qld.gov.au 61721399723
Kate Cleto sip:kate.c@scenicrim.qld.gov.au 61721399723
Kate Jones sip:kate.jo@scenicrim.qld.gov.au 61721399723
Kathy Forrest sip:kathy.f@scenicrim.qld.gov.au 61721399723
Katie Newlove sip:katie.n@scenicrim.qld.gov.au 61721399723
Katrina Childs sip:katrina.c@scenicrim.qld.gov.au 61721399723
Katrina Richter sip:katrina.r@scenicrim.qld.gov.au 61721399723
Kelli Rabbitt sip:kelli.r@scenicrim.qld.gov.au 61721399723
Kelly Locksley sip:kelly.l@scenicrim.qld.gov.au 61721399723
Kelly Richardson sip:kelly.r@scenicrim.qld.gov.au 61721399723
Kelmeny Fraser sip:kelmeny.f@scenicrim.qld.gov.au 61721399723
Kevin Domjahn sip:kevin.d@scenicrim.qld.gov.au 61721399723
Kirby McDonald sip:kirby.m@scenicrim.qld.gov.au 61721399723
Kobi Lane sip:kobi.l@scenicrim.qld.gov.au 61721399723
Kris Van der Borgh sip:kris.v@scenicrim.qld.gov.au 61721399723
Krystal Bardell sip:krystal.b@scenicrim.qld.gov.au 61721399723
Kuda Pfidze sip:kuda.p@scenicrim.qld.gov.au 61721399723
Kyle Richards sip:kyle.r@scenicrim.qld.gov.au 61721399723
Kylee Mallinson sip:kylee.m@scenicrim.qld.gov.au 61721399723
Kylie Addy sip:kylie.a@scenicrim.qld.gov.au 61721399723
Kym Lancaster sip:kym.l@scenicrim.qld.gov.au 61721399723
Lacey Sawtell sip:lacey.s@scenicrim.qld.gov.au 61721399723
Lana Lockett sip:lana.l@scenicrim.qld.gov.au 61721399723
Lara Solyma sip:lara.s@scenicrim.qld.gov.au 61721399723
Lau Chean-Piau sip:lau.c@scenicrim.qld.gov.au 61721399723
Laura Mollinger sip:laura.m@scenicrim.qld.gov.au 61721399723
Lauren Berg sip:lauren.b@scenicrim.qld.gov.au 61721399723
Local Disaster Coordinator sip:ldc@scenicrim.qld.gov.au 61721399723
LDCC Admin sip:ldccadmin@scenicrim.qld.gov.au 61721399723
LDCC Logistics sip:ldcclogistics@scenicrim.qld.gov.au 61721399723
LDCC Media sip:ldccmedia@scenicrim.qld.gov.au 61721399723
LDCC Operations sip:ldccoperations@scenicrim.qld.gov.au 61721399723
LDCC Planning sip:ldccplanning@scenicrim.qld.gov.au 61721399723
LDCC Planning 1 sip:ldccplanning1@scenicrim.qld.gov.au 61721399723
LDCC Room Manager sip:ldccroommanager@scenicrim.qld.gov.au 61721399723
Lea Schuster sip:lea.s@scenicrim.qld.gov.au 61721399723
Leah Slater sip:leah.s@scenicrim.qld.gov.au 61721399723
Leanne Burnett sip:leanne.bu@scenicrim.qld.gov.au 61721399723
Leanne Smith sip:leanne.s@scenicrim.qld.gov.au 61721399723
Leisa Ferguson sip:leisa.f@scenicrim.qld.gov.au 61721399723
Liam Cahill sip:liam.c@scenicrim.qld.gov.au 61721399723
Libby Murphy sip:libby.m@scenicrim.qld.gov.au 61721399723
Lily McArthur sip:lily.m@scenicrim.qld.gov.au 61721399723
Linda Kraat sip:linda.k@scenicrim.qld.gov.au 61721399723
Linda Phillips sip:linda.p@scenicrim.qld.gov.au 61721399723
Linda Roderick sip:linda.r@scenicrim.qld.gov.au 61721399723
Lisa Caruana sip:lisa.c@scenicrim.qld.gov.au 61721399723
Lisa Hearn sip:lisa.h@scenicrim.qld.gov.au 61721399723
Lisa Kerrison sip:lisa.ke@scenicrim.qld.gov.au 61721399723
Lisa Stubbs sip:lisa.s@scenicrim.qld.gov.au 61721399723
Liz Roberts sip:liz.r@scenicrim.qld.gov.au 61721399723
Luchia Willows-Keetley sip:luchia.w@scenicrim.qld.gov.au 61721399723
Luke Anthony sip:luke.a@scenicrim.qld.gov.au 61721399723
Luke Cadwallader sip:luke.c@scenicrim.qld.gov.au 61721399723
Luke Vogler sip:luke.v@scenicrim.qld.gov.au 61721399723
Lyle Venz sip:lyle.v@scenicrim.qld.gov.au 61721399723
Lyndal Coote sip:lyndal.c@scenicrim.qld.gov.au 61721399723
Lynne Bell sip:lynne.b@scenicrim.qld.gov.au 61721399723
Madi Law sip:madi.l@scenicrim.qld.gov.au 61721399723
Malav Patel sip:malav.p@scenicrim.qld.gov.au 61721399723
Margie Jackson sip:margie.j@scenicrim.qld.gov.au 61721399723
Marie Scott sip:marie.s@scenicrim.qld.gov.au 61721399723
Marisa Parker sip:marisa.p@scenicrim.qld.gov.au 61721399723
Mark Carter sip:mark.c@scenicrim.qld.gov.au 61721399723
Mark Duncan sip:mark.d@scenicrim.qld.gov.au 61721399723
Mark Lohmann sip:mark.l@scenicrim.qld.gov.au 61721399723
Mark Ludwig sip:mark.lu@scenicrim.qld.gov.au 61721399723
Mark Paddick sip:mark.pa@scenicrim.qld.gov.au 61721399723
Mark Slingo sip:mark.sl@scenicrim.qld.gov.au 61721399723
Mark Stevens sip:mark.st@scenicrim.qld.gov.au 61721399723
Marnie Young sip:marnie.y@scenicrim.qld.gov.au 61721399723
Cr Marshall Chalk sip:marshall.c@scenicrim.qld.gov.au 61721399723
Matt Arnold sip:matt.a@scenicrim.qld.gov.au 61721399723
Matthew Blane sip:matthew.b@scenicrim.qld.gov.au 61721399723
Matthew Creedy sip:matthew.c@scenicrim.qld.gov.au 61721399723
Matthew Funnell sip:matthew.f@scenicrim.qld.gov.au 61721399723
Maverick Wells sip:maverick.w@scenicrim.qld.gov.au 61721399723
Megan Gilloway sip:megan.g@scenicrim.qld.gov.au 61721399723
Melanie Beach sip:melanie.b@scenicrim.qld.gov.au 61721399723
Melissa Connerty sip:melissa.c@scenicrim.qld.gov.au 61721399723
Melissa MacPherson sip:melissa.m@scenicrim.qld.gov.au 61721399723
Melissa Messina sip:melissa.me@scenicrim.qld.gov.au 61721399723
Melissa Quast sip:melissa.q@scenicrim.qld.gov.au 61721399723
Melissa Ryan sip:melissa.r@scenicrim.qld.gov.au 61721399723
Cr Michael Enright sip:michael.e@scenicrim.qld.gov.au 61721399723
Michael Gill sip:michael.g@scenicrim.qld.gov.au 61721399723
Michael Wolf sip:michael.wo@scenicrim.qld.gov.au 61721399723
Minh-Man Nguyen sip:minh-man.n@scenicrim.qld.gov.au 61721399723
Miranda Collins sip:miranda.c@scenicrim.qld.gov.au 61721399723
Miriam Nyrene sip:miriam.n@scenicrim.qld.gov.au 61721399723
Monica Massey sip:monica.m@scenicrim.qld.gov.au 61721399723
MR Teams Test sip:mrteamstest@scenicrim.qld.gov.au 61721399723
Nada Mallinson sip:nada.m@scenicrim.qld.gov.au 61721399723
Narendra Singh sip:narendra.s@scenicrim.qld.gov.au 61721399723
Natika Dendle sip:natika.d@scenicrim.qld.gov.au 61721399723
Nichole Matheson sip:nichole.m@scenicrim.qld.gov.au 61721399723
Nick Payne sip:nick.p@scenicrim.qld.gov.au 61721399723
Nicky Hannigan sip:nicky.h@scenicrim.qld.gov.au 61721399723
Nicole Azzopardi sip:nicole.a@scenicrim.qld.gov.au 61721399723
Nicole Williams sip:nicole.w@scenicrim.qld.gov.au 61721399723
Nikki Blyton sip:nikki.b@scenicrim.qld.gov.au 61721399723
Noel Todd sip:noel.t@scenicrim.qld.gov.au 61721399723
Noni Howells sip:noni.h@scenicrim.qld.gov.au 61721399723
Oliver Pring sip:oliver.p@scenicrim.qld.gov.au 61721399723
Olivia Pennell sip:olivia.p@scenicrim.qld.gov.au 61721399723
Ormnorth Ly sip:ormnorth.l@scenicrim.qld.gov.au 61721399723
Owen Sweeney sip:owen.s@scenicrim.qld.gov.au 61721399723
Patricia Ryan sip:patricia.r@scenicrim.qld.gov.au 61721399723
Paul Gillen sip:paul.g@scenicrim.qld.gov.au 61721399723
Paula Leigh sip:paula.l@scenicrim.qld.gov.au 61721399723
Pedro Pascon Da Paz sip:pedro.p@scenicrim.qld.gov.au 61721399723
Peter Allan sip:peter.a@scenicrim.qld.gov.au 61721399723
Peter Blyton sip:peter.b@scenicrim.qld.gov.au 61721399723
Peter Kropp sip:peter.k@scenicrim.qld.gov.au 61721399723
Phil Day sip:phil.d@scenicrim.qld.gov.au 61721399723
Pauline Wimmer sip:polly.w@scenicrim.qld.gov.au 61721399723
Pravin Menon sip:pravin.m@scenicrim.qld.gov.au 61721399723
Racheal McNiven sip:racheal.m@scenicrim.qld.gov.au 61721399723
Rachel Baldwin sip:rachel.b@scenicrim.qld.gov.au 61721399723
Ray King sip:ray.k@scenicrim.qld.gov.au 61721399723
Rayhan Shabbir sip:rayhan.s@scenicrim.qld.gov.au 61721399723
Raylene Jensen sip:raylene.j@scenicrim.qld.gov.au 61721399723
Rebecca Dalton sip:rebecca.d@scenicrim.qld.gov.au 61721399723
Rebecca Fitzpatrick sip:rebecca.f@scenicrim.qld.gov.au 61721399723
Rebecca Reilly sip:rebecca.r@scenicrim.qld.gov.au 61721399723
Renaee Johns sip:renaee.j@scenicrim.qld.gov.au 61721399723
Renee Wallace sip:renee.wa@scenicrim.qld.gov.au 61721399723
Rhiannon Taylor sip:rhiannon.t@scenicrim.qld.gov.au 61721399723
Richard Hancock sip:richard.h@scenicrim.qld.gov.au 61721399723
Richard Seddon sip:richard.s@scenicrim.qld.gov.au 61721399723
Rick Hotz sip:rick.h@scenicrim.qld.gov.au 61721399723
Robyn Cahill sip:robyn.c@scenicrim.qld.gov.au 61721399723
Robyn Fortescue sip:robyn.f@scenicrim.qld.gov.au 61721399723
Robyn Ryan sip:robyn.r@scenicrim.qld.gov.au 61721399723
Ross Kroll sip:ross.k@scenicrim.qld.gov.au 61721399723
Rylie Appleyard sip:rylie.a@scenicrim.qld.gov.au 61721399723
Santosh K C sip:santosh.kc@scenicrim.qld.gov.au 61721399723
Sarah Berg sip:sarah.b@scenicrim.qld.gov.au 61721399723
Sarah Foley sip:sarah.f@scenicrim.qld.gov.au 61721399723
Sarah Tracey sip:sarah.t@scenicrim.qld.gov.au 61721399723
Sarita King sip:sarita.k@scenicrim.qld.gov.au 61721399723
Scott Osman sip:scott.o@scenicrim.qld.gov.au 61721399723
Scott Oberle sip:scott.ob@scenicrim.qld.gov.au 61721399723
Scott Williams sip:scott.w@scenicrim.qld.gov.au 61721399723
SESEOC2 sip:seseoc2@scenicrim.qld.gov.au 61721399723
SES Local Controller sip:seslocalcontroller@scenicrim.qld.gov.au 61721399723
Shane Gillett sip:shane.g@scenicrim.qld.gov.au 61721399723
Shane Marks sip:shane.m@scenicrim.qld.gov.au 61721399723
Shane Rooks sip:shane.r@scenicrim.qld.gov.au 61721399723
Shantel Turner sip:shantel.t@scenicrim.qld.gov.au 61721399723
Sharyn Keepence sip:sharyn.k@scenicrim.qld.gov.au 61721399723
Shaun Anderson sip:shaun.a@scenicrim.qld.gov.au 61721399723
Shaun Coleman sip:shaun.c@scenicrim.qld.gov.au 61721399723
Shaun White sip:shaun.w@scenicrim.qld.gov.au 61721399723
Shaun Wrigley sip:shaun.wr@scenicrim.qld.gov.au 61721399723
Shona Vines sip:shona.v@scenicrim.qld.gov.au 61721399723
Simon Hitchins sip:simon.h@scenicrim.qld.gov.au 61721399723
Skype Test sip:skype.t@scenicrim.qld.gov.au 61721399723
Sonja Roots sip:sonja.r@scenicrim.qld.gov.au 61721399723
Stephen Boyd sip:stephen.b@scenicrim.qld.gov.au 61721399723
Stephen Bell sip:stephen.be@scenicrim.qld.gov.au 61721399723
Stephen McCauley sip:stephen.m@scenicrim.qld.gov.au 61721399723
Steve Aird sip:steve.a@scenicrim.qld.gov.au 61721399723
Sudheer Payyapatt sip:sudheer.p@scenicrim.qld.gov.au 61721399723
Susan Packer sip:susan.p@scenicrim.qld.gov.au 61721399723
Susan Wynne sip:susan.w@scenicrim.qld.gov.au 61721399723
Sylvia Swalling sip:sylvia.s@scenicrim.qld.gov.au 61721399723
Tara McManus sip:tara.m@scenicrim.qld.gov.au 61721399723
Tara Wallace sip:tara.w@scenicrim.qld.gov.au 61721399723
Taylor Kirkwood sip:taylor.k@scenicrim.qld.gov.au 61721399723
Tegan Smith sip:tegan.s@scenicrim.qld.gov.au 61721399723
Terence Harvey sip:terence.h@scenicrim.qld.gov.au 61721399723
Terry Hotz sip:terry.h@scenicrim.qld.gov.au 61721399723
Terrance Richter sip:terry.r@scenicrim.qld.gov.au 61721399723
Tia Bun sip:tia.b@scenicrim.qld.gov.au 61721399723
Tickets BD sip:tickets.bd@scenicrim.qld.gov.au 61721399723
Boonah Cultural Centre - 3068 sip:tickets.bh@scenicrim.qld.gov.au 61721399723
Timothy Bewert sip:timothy.b@scenicrim.qld.gov.au 61721399723
Timothy Sutcliffe sip:timothy.s@scenicrim.qld.gov.au 61721399723
Tamborine Mountain Front Desk 3 5473 sip:tmfd5473@scenicrim.qld.gov.au 61721399723
Tony Stanfield sip:tony.s@scenicrim.qld.gov.au 61721399723
Trevor Draude sip:trevor.d@scenicrim.qld.gov.au 61721399723
Velda Matthews sip:velda.m@scenicrim.qld.gov.au 61721399723
Vili Masibilo sip:vili.m@scenicrim.qld.gov.au 61721399723
Viral Patel sip:viral.p@scenicrim.qld.gov.au 61721399723
Cr Virginia West sip:virginia.w@scenicrim.qld.gov.au 61721399723
Vivienne Musch sip:vivienne.m@scenicrim.qld.gov.au 61721399723
Warren Neinert sip:warren.n@scenicrim.qld.gov.au 61721399723
Wayne Mahoney sip:wayne.ma@scenicrim.qld.gov.au 61721399723
Workplace Health and Safety sip:whs@scenicrim.qld.gov.au 61721399723
Yoni Rankin sip:yoni.r@scenicrim.qld.gov.au 61721399723
Zane Bettridge sip:zane.b@scenicrim.qld.gov.au 61721399723

## SRRC-Cutover Schedule
SRRC SfB to Microsoft Teams migration with Telstra port as carrier via Operator Connect - Procedure
Step | Day | Time | Duration | Task | Resource | Status | Comment
1 | Friday | 16:30 | . | Backup users' skype settings to file (Get-CsUser) | RMT | Completed
2 | Friday | 16:30 | 45-75 mins (Could be less, or, more if Tesltra encounter challenges) | 5PM Cutover starts - Telstra Engineer makes contact and seeks confirmation to proceed with Port... | RMT Telstra SRRC | Progressing… | Proceed unless SRRC communicate otherwise before 4:30PM
3 | Friday | 16:30 | 15 mins | Switch all AA/CQ/AE Resource Account numbers to permanent numbers in preparation for Port finish and testing. All ranges are already uploaded to Teams from Telstra Adaptive Collaboration portal. | RMT/Mark | Progressing… | Mark has offered to help do this
| Friday |  | 15 mins | Assign all users getting PSTN # MS Teams Phone Std license |  | Completed | 383
| Friday |  | 15 mins | Assign all users getting PSTN # MS Audio Conference license |  | Completed | Mark acquired 500 pack
4 | Friday | 16:45 | +/- 60 mins | Move user(s) via PowerShell (Move-CsUser) on SfB server ds-sfb-01 from SfB to Teams (400+ users to process) | RMT | Completed
5 | Friday | 17:30 |  | Port Completion - between carriers could take up to an hour (sometimes less sometime more if they encounter challenges) | RMT | Completed
6 | Friday | 17:30 | 15 Mins | Once port completed - Test inbound calls to Contact Centre. | SRRC | Completed | Contact Centre in After hours mode so just a connectivity test as functionality tested in pilot.
7 | Friday | 17:45 | 15 Mins | Once port completed - Test inbound calls to AA/CQs with external PSTN number assigned | SRRC | Completed | Contact Centre in After hours mode so just a connectivity test as functionality tested in pilot.
8 | Friday | 18:00 |  | Once user migrated to Teams, Disable Skype user (this removes SfB PSTN #) | RMT | Completed
9 | Friday | 18:30 | 15 mins | Once SfB users disabled. Delta sync AAD Connect on Server az-aadcv2 (ensuring Skype # no longer showing and user now in Teams Only mode in Teams Admin centre) | RMT | Completed
10 | Friday | 18:15 | 15-30 Mins | Assign Operator Connect number(s) to users via PowerShell script and/or Teams Admin Centre GUI, | RMT | Completed
11 | Friday | 19:00 | 30 Mins | Once port completed and users migrated - Test User numbers. A. Make a successful outbound test call via Teams app to mobile. B. Make a successful inbound call from mobile to users Teams number. | SRRC | Completed | Just a connectivity test as functionality tested in pilot. SRRC to test as many endpoints as required to ensure they are happy and ready for Monday morning.
12 | Friday | 7:00 | 5 mins | Inform Tesltra of testing outcome and Rolback if required | SRRC/RMT | Completed
13 | Saturday |  |  | Further testing at remote sites | SRRC | Completed
14 | Sunday |  |  | Any further testing? |  | Completed
15 | Monday | 8:00 |  | All hands on Deck to assist users with any FAQs, Troubleshooting, etc | SRRC | Completed
16 | Monday | 8:00 |  | RMT nurture support for escalation | RMT
Rollback procedure (If required):
1 |  |  | 90 mins | Telstra Rollback Port | Telstra
2 |  |  | 15 mins | Re-Assign pilot numbers to AA/CQ/Aes | RMT
3 |  |  | 15 mins | Test CentrePal and AA/CQs | SRRC
4 |  |  | 30 mins | Unassign Operator connect number(s) via Teams Admin Centre | RMT
5 |  |  | 60 mins | Move user(s) via PowerShell (Move-CsUser) on SFB server ds-sfb-01 back from Teams to SfB | RMT
6 |  |  | 30-60 mins | Assign back SfB Direct route number via SfB 2015 Control Panel on server ds-sfb-01 | RMT
7 |  |  | 15 mins | Make a successful SfB call via SfB app. | RMT/SRRC
8 |  |  | 60 mins | Check SfB user setting against backup file | RMT

## SRRC-MSTeamsPhoneStdUsers
UPN | Number
adam.j@scenicrim.qld.gov.au | 61755405350
adam.l@scenicrim.qld.gov.au | 61755405987
adam.ma@scenicrim.qld.gov.au | 61755405610
Adrian.C@scenicrim.qld.gov.au | 61755405134
adrienne.j@scenicrim.qld.gov.au | 61755405614
Alana.B@scenicrim.qld.gov.au | 61755405233
alisa.t@scenicrim.qld.gov.au | 61755405604
alisha.p@scenicrim.qld.gov.au | 61755405927
Allen.N@scenicrim.qld.gov.au | 61755405432
Allyson.H@scenicrim.qld.gov.au | 61755405499
amanda.d@scenicrim.qld.gov.au | 61755405650
amanda.f@scenicrim.qld.gov.au | 61755405912
amanda.h@scenicrim.qld.gov.au | 61755405401
amanda.l@scenicrim.qld.gov.au | 61755405329
amanda.v@scenicrim.qld.gov.au | 61755405905
Amelia.J@scenicrim.qld.gov.au | 61755405686
Amie.P@scenicrim.qld.gov.au | 61755405299
amy.f@scenicrim.qld.gov.au | 61755405668
Amy.R@scenicrim.qld.gov.au | 61755405274
amy.w@scenicrim.qld.gov.au | 61755405658
Anastasia.R@scenicrim.qld.gov.au | 61755405295
andrew.c@scenicrim.qld.gov.au | New number
andrew.cu@scenicrim.qld.gov.au | 61755405290
andrew.h@scenicrim.qld.gov.au | 61755405328
Andrew.Ma@scenicrim.qld.gov.au | 61755405320
andrew.r@scenicrim.qld.gov.au | 61755405991
andrew.s@scenicrim.qld.gov.au | 61755405209
ann.g@scenicrim.qld.gov.au | 61755405151
anna.s@scenicrim.qld.gov.au | 61755405968
anne.b@scenicrim.qld.gov.au | 61755405913
annmarie.w@scenicrim.qld.gov.au | 61755405199
anthony.m@scenicrim.qld.gov.au | 61755405423
asiful.a@scenicrim.qld.gov.au | 61755405939
bcc5051@scenicrim.qld.gov.au | 61755405051
bcc5060@srrc.qld.gov.au | 61755405060
bdl5142@scenicrim.qld.gov.au | 61755405142
bdsl5286@srrc.qld.gov.au | 61755405286
Belinda.J@scenicrim.qld.gov.au | 61755405313
Ben.O@scenicrim.qld.gov.au | 61755405392
bill.k@scenicrim.qld.gov.au | 61755405696
billie.p@scenicrim.qld.gov.au | 61755405319
Blake.B@scenicrim.qld.gov.au | 61755405605
Blake.H@scenicrim.qld.gov.au | 61755405117
Boonah.FrontDesk1@srrc.qld.gov.au | 61754633042
Boonah.FrontDesk2@srrc.qld.gov.au | 61754633035
brad.f@scenicrim.qld.gov.au | 61755405173
brad.w@scenicrim.qld.gov.au | 61755405625
brenda.w@scenicrim.qld.gov.au | 61755405660
Brett.F@scenicrim.qld.gov.au | 61755405459
brian.a@scenicrim.qld.gov.au | 61755405188
bridget.p@scenicrim.qld.gov.au | 61755405166
Brittany.H@scenicrim.qld.gov.au | 61755405410
bronwyn.c@scenicrim.qld.gov.au | 61755405601
byron.s@scenicrim.qld.gov.au | 61755405692
cameron.t@scenicrim.qld.gov.au | 61755405474
Carleen.O@scenicrim.qld.gov.au | 61755405163
Carly.L@scenicrim.qld.gov.au | 61755405695
carmel.d@scenicrim.qld.gov.au | 61755405229
carmen.h@scenicrim.qld.gov.au | 61755405281
carolann.b@scenicrim.qld.gov.au | 61755405920
caroline.m@scenicrim.qld.gov.au | 61755405980
Carolyn.G@scenicrim.qld.gov.au | 61755405236
cassandra.n@scenicrim.qld.gov.au | 61755405434
catherine.k@scenicrim.qld.gov.au | 61755405681
Catherine.M@scenicrim.qld.gov.au | 61755405289
chantal.b@scenicrim.qld.gov.au | 61755405243
charlie.w@scenicrim.qld.gov.au | 61754633058
cherece.j@scenicrim.qld.gov.au | 61755405661
cheryl.h@scenicrim.qld.gov.au | 61755405160
Chloe.E@scenicrim.qld.gov.au | 61755405204
Chris.C@scenicrim.qld.gov.au | 61755405698
Christopher.G@scenicrim.qld.gov.au | 61755405494
christy.s@scenicrim.qld.gov.au | 61755405399
cindy.w@scenicrim.qld.gov.au | 61755405254
claire.d@scenicrim.qld.gov.au | 61755405662
clare.n@scenicrim.qld.gov.au | 61755405261
Clyde.P@scenicrim.qld.gov.au | 61755405080
colin.m@scenicrim.qld.gov.au | 61755405246
craig.h@scenicrim.qld.gov.au | 61755405420
craig.he@scenicrim.qld.gov.au | 61755405489
craig.mc@scenicrim.qld.gov.au | 61755405956
craig.p@scenicrim.qld.gov.au | 61754633047
CRP5302@srrc.onmicrosoft.com | 61755405302
daadmin@scenicrim.qld.gov.au | 61755405158
damian.t@scenicrim.qld.gov.au | 61755405628
daniel.mc@scenicrim.qld.gov.au | 61755405331
daniel.s@scenicrim.qld.gov.au | 61755405979
daniel.sm@scenicrim.qld.gov.au | 61755405486
danni.m@scenicrim.qld.gov.au | 61755405641
darren.l@scenicrim.qld.gov.au | 61754633057
David.A@scenicrim.qld.gov.au | 61755405951
david.k@scenicrim.qld.gov.au | 61755405100
david.r@scenicrim.qld.gov.au | 61755405191
Dean.K@scenicrim.qld.gov.au | 61755405114
dean.w@scenicrim.qld.gov.au | 61755405377
Deanna.F@scenicrim.qld.gov.au | 61755405317
Debbie.S@scenicrim.qld.gov.au | 61755405690
debra.h@scenicrim.qld.gov.au | 61755405255
debra.t@scenicrim.qld.gov.au | 61754633060
dee.c@scenicrim.qld.gov.au | 61755405308
Deeanne.T@scenicrim.qld.gov.au | 61755405606
desley.a@scenicrim.qld.gov.au | 61755405914
Donna.C@scenicrim.qld.gov.au | 61755405076
donna.r@scenicrim.qld.gov.au | 61755405348
donnalee.o@scenicrim.qld.gov.au | 61755405608
doug.h@scenicrim.qld.gov.au | 61755405902
drift.i@scenicrim.qld.gov.au | 61755405330
duncan.m@scenicrim.qld.gov.au | 61755405406
Ellie.B@scenicrim.qld.gov.au | 61755405309
elva.s@scenicrim.qld.gov.au | 61755405276
emily.b@scenicrim.qld.gov.au | 61755405985
emma.th@scenicrim.qld.gov.au | 61755405172
erin.p@scenicrim.qld.gov.au | 61755405316
frank.a@scenicrim.qld.gov.au | 61755405347
Gail.K@scenicrim.qld.gov.au | 61755405271
gavin.g@scenicrim.qld.gov.au | 61755405198
gayanne.k@scenicrim.qld.gov.au | 61755405288
Genevieve.L@scenicrim.qld.gov.au | 61755405143
georgina.w@scenicrim.qld.gov.au | 61755405923
gerald.p@scenicrim.qld.gov.au | 61755405970
Grace.R@scenicrim.qld.gov.au | 61755405426
graham.a@scenicrim.qld.gov.au | 61755405190
Grant.M@scenicrim.qld.gov.au | 61755405109
greg.c@scenicrim.qld.gov.au | 61755405105
greg.h@scenicrim.qld.gov.au | 61755405186
Hazel.M@scenicrim.qld.gov.au | 61755405162
heather.n@scenicrim.qld.gov.au | 61755405205
Heerah.K@scenicrim.qld.gov.au | 61755405602
Helen.R@scenicrim.qld.gov.au | 61755405458
Hera.L@scenicrim.qld.gov.au | 61755405074
Hiral.P@scenicrim.qld.gov.au | 61755405953
Holly.H@scenicrim.qld.gov.au | 61755405206
hr@scenicrim.qld.gov.au | 61755405613
Ian.M@scenicrim.qld.gov.au | 61755405942
india.b@scenicrim.qld.gov.au | 61755405298
info_moogerah@scenicrim.qld.gov.au | 61755405600
ingrid.l@scenicrim.qld.gov.au | 61754633061
insync.onprem@scenicrim.qld.gov.au | 61755405338
insync@scenicrim.qld.gov.au | 61755405337
integrity@scenicrim.qld.gov.au | No number required
irene.g@scenicrim.qld.gov.au | 61755405055
isabel.f@scenicrim.qld.gov.au | 61755405909
jackie.l@scenicrim.qld.gov.au | 61755405655
Jacob.O@scenicrim.qld.gov.au | 61755405622
Jaime.M@scenicrim.qld.gov.au | 61755405073
jairo.c@scenicrim.qld.gov.au | 61755405061
james.do@scenicrim.qld.gov.au | 61755405643
James.OK@scenicrim.qld.gov.au | 61755405656
james.w@scenicrim.qld.gov.au | 61755405938
Jamie.B@scenicrim.qld.gov.au | 61755405368
jan.h@scenicrim.qld.gov.au | 61755405684
jane.g@scenicrim.qld.gov.au | 61755405667
Jane.S@scenicrim.qld.gov.au | 61755405972
jared.k@scenicrim.qld.gov.au | 61755405345
jarrod.h@scenicrim.qld.gov.au | 61755405917
Jasmine.S@scenicrim.qld.gov.au | 61755405272
Jason.Ca@scenicrim.qld.gov.au | 61755405273
Jason.G@scenicrim.qld.gov.au | 61755405043
jason.h@scenicrim.qld.gov.au | 61755405639
jason.t@scenicrim.qld.gov.au | 61755405483
Jason.Y@scenicrim.qld.gov.au | 61755405270
jeff.b@scenicrim.qld.gov.au | 61755405164
jeff.d@scenicrim.qld.gov.au | 61755405385
jeff.m@scenicrim.qld.gov.au | 61755405402
jenna.t@scenicrim.qld.gov.au | 61755405398
Jennifer.St@scenicrim.qld.gov.au | 61755405219
jeremey.r@scenicrim.qld.gov.au | 61755405693
jeremy.p@scenicrim.qld.gov.au | 61755405235
Jessica.D@scenicrim.qld.gov.au | 61755405370
Jo.J@scenicrim.qld.gov.au | 61755405425
Jo.Jo@scenicrim.qld.gov.au | 61755405984
Jo-Ann.A@scenicrim.qld.gov.au | 61755405478
joanne.d@scenicrim.qld.gov.au | 61755405342
Joanne.H@scenicrim.qld.gov.au | 61755405691
Joanne.M@scenicrim.qld.gov.au | 61755405631
Joanne.R@scenicrim.qld.gov.au | 61755405621
Jodi.W@scenicrim.qld.gov.au | 61755405245
jodie.m@scenicrim.qld.gov.au | 61755405360
jodie.ma@scenicrim.qld.gov.au | 61754633084
jodie.s@scenicrim.qld.gov.au | 61755405925
jodie.v@scenicrim.qld.gov.au | 61755405452
Joel.S@scenicrim.qld.gov.au | 61755405171
john.ke@scenicrim.qld.gov.au | 61755405193
John.L@scenicrim.qld.gov.au | 61755405627
john.m@scenicrim.qld.gov.au | 61755405427
john.p@scenicrim.qld.gov.au | 61755405283
jon.r@scenicrim.qld.gov.au | 61755405336
jordan.t@scenicrim.qld.gov.au | 61755405346
Joseph.K@scenicrim.qld.gov.au | 61755405153
judith.h@scenicrim.qld.gov.au | 61755405645
Judy.J@scenicrim.qld.gov.au | 61755405252
Julia.K@scenicrim.qld.gov.au | 61755405994
julia.m@scenicrim.qld.gov.au | 61755405118
julie.o@scenicrim.qld.gov.au | 61755405922
Julie.S@scenicrim.qld.gov.au | 61755405152
Julien.P@scenicrim.qld.gov.au | 61755405056
justin.a@scenicrim.qld.gov.au | 61755405262
justin.k@scenicrim.qld.gov.au | 61755405981
justin.s@scenicrim.qld.gov.au | 61755405282
justin.si@scenicrim.qld.gov.au | 61755405989
justin.st@scenicrim.qld.gov.au | 61755405456
Karen.Br@scenicrim.qld.gov.au | 61755405140
Kate.C@scenicrim.qld.gov.au | 61755405428
kate.jo@scenicrim.qld.gov.au | 61755405129
kathy.f@scenicrim.qld.gov.au | 61755405015
katie.n@scenicrim.qld.gov.au | 61755405910
Katrina.C@scenicrim.qld.gov.au | 61755405603
katrina.r@scenicrim.qld.gov.au | 61755405358
kelli.r@scenicrim.qld.gov.au | 61755405263
kelly.l@scenicrim.qld.gov.au | 61755405966
kelly.r@scenicrim.qld.gov.au | 61755405911
kelmeny.f@scenicrim.qld.gov.au | 61755405315
kevin.d@scenicrim.qld.gov.au | 61755405277
Kirby.M@scenicrim.qld.gov.au | 61755405394
Kobi.L@scenicrim.qld.gov.au | 61755405380
kris.v@scenicrim.qld.gov.au | 61755405928
krystal.b@scenicrim.qld.gov.au | 61755405962
Kuda.P@scenicrim.qld.gov.au | 61755405332
kyle.r@scenicrim.qld.gov.au | 61755405485
kylee.m@scenicrim.qld.gov.au | 61755405115
kylie.a@scenicrim.qld.gov.au | 61755405247
Kym.L@scenicrim.qld.gov.au | 61755405293
lacey.s@scenicrim.qld.gov.au | 61755405014
Lana.L@scenicrim.qld.gov.au | 61755405224
Lara.S@scenicrim.qld.gov.au | 61755405075
Lau.c@scenicrim.qld.gov.au | 61755405094
Laura.M@scenicrim.qld.gov.au | 61755405130
lauren.b@scenicrim.qld.gov.au | 61755405632
ldc@scenicrim.qld.gov.au | 61755405940
ldccadmin@scenicrim.qld.gov.au | 61755405934
ldccadmin1@scenicrim.qld.gov.au | 61755405935
ldcclogistics@scenicrim.qld.gov.au | 61755405936
ldcclogistics1@scenicrim.qld.gov.au | 61755405937
ldccmedia@scenicrim.qld.gov.au | 61755405941
ldccoperations@scenicrim.qld.gov.au | 61755405943
ldccoperations1@scenicrim.qld.gov.au | 61755405944
ldccplanning@scenicrim.qld.gov.au | 61755405946
ldccplanning1@scenicrim.qld.gov.au | 61755405947
ldccplanning2@scenicrim.qld.gov.au | 61755405948
ldccroommanager@scenicrim.qld.gov.au | 61755405633
lea.s@scenicrim.qld.gov.au | 61755405053
Leah.S@scenicrim.qld.gov.au | 61755405343
leanne.bu@scenicrim.qld.gov.au | 61755405617
Leanne.S@scenicrim.qld.gov.au | 61755405256
leisa.f@scenicrim.qld.gov.au | 61755405448
liam.c@scenicrim.qld.gov.au | 61755405253
libby.m@scenicrim.qld.gov.au | 61755405132
Lily.M@scenicrim.qld.gov.au | 61755405901
linda.k@scenicrim.qld.gov.au | 61755405441
linda.p@scenicrim.qld.gov.au | 61755405978
linda.r@scenicrim.qld.gov.au | 61755405303
lisa.c@scenicrim.qld.gov.au | 61755405699
lisa.h@scenicrim.qld.gov.au | 61755405974
lisa.ke@scenicrim.qld.gov.au | 61755405127
lisa.s@scenicrim.qld.gov.au | 61755405986
liz.r@scenicrim.qld.gov.au | 61755405071
luchia.w@scenicrim.qld.gov.au | 61755405430
Lucy.S@scenicrim.qld.gov.au | 61755405971
Luke.A@scenicrim.qld.gov.au | 61755405612
Luke.C@scenicrim.qld.gov.au | 61755405107
luke.v@scenicrim.qld.gov.au | 61755405296
lyle.v@scenicrim.qld.gov.au | 61755405123
Lyndal.C@scenicrim.qld.gov.au | 61755405146
lynne.b@scenicrim.qld.gov.au | 61755405218
Madi.L@scenicrim.qld.gov.au | 61755405697
Malav.P@scenicrim.qld.gov.au | 61755405988
margie.j@scenicrim.qld.gov.au | 61755405196
marie.s@scenicrim.qld.gov.au | 61755405321
marisa.p@scenicrim.qld.gov.au | 61755405493
mark.c@scenicrim.qld.gov.au | 61755405419
mark.d@scenicrim.qld.gov.au | 61755405327
mark.l@scenicrim.qld.gov.au | 61755405241
mark.lu@scenicrim.qld.gov.au | 61755405630
mark.pa@scenicrim.qld.gov.au | 61755405351
Mark.Sl@scenicrim.qld.gov.au | 61755405907
mark.st@scenicrim.qld.gov.au | 61755405278
Marnie.Y@scenicrim.qld.gov.au | 61755405611
marshall.c@scenicrim.qld.gov.au | 61755405405
matt.a@scenicrim.qld.gov.au | 61755405653
Matthew.B@scenicrim.qld.gov.au | 61755405475
matthew.c@scenicrim.qld.gov.au | 61755405169
Matthew.F@scenicrim.qld.gov.au | 61755405231
Maverick.w@scenicrim.qld.gov.au | 61755405361
megan.g@scenicrim.qld.gov.au | 61755405179
Melanie.B@scenicrim.qld.gov.au | 61755405257
melissa.c@scenicrim.qld.gov.au | 61755405916
melissa.m@scenicrim.qld.gov.au | 61755405168
melissa.me@scenicrim.qld.gov.au | 61755405182
melissa.q@scenicrim.qld.gov.au | 61755405220
Melissa.R@scenicrim.qld.gov.au | 61755405180
michael.e@scenicrim.qld.gov.au | 61755405404
michael.g@scenicrim.qld.gov.au | 61755405975
Michael.Wo@scenicrim.qld.gov.au | 61755405016
Minh-Man.N@scenicrim.qld.gov.au | 61755405072
Miranda.C@scenicrim.qld.gov.au | 61755405259
miriam.n@scenicrim.qld.gov.au | 61755405436
Monica.M@scenicrim.qld.gov.au | 61755405202
MR3D@scenicrim.qld.gov.au | 61755405424
Nada.M@scenicrim.qld.gov.au | 61755405344
Narendra.s@scenicrim.qld.gov.au | 61755405264
Natika.D@scenicrim.qld.gov.au | 61755405213
nichole.m@scenicrim.qld.gov.au | 61755405670
nick.p@scenicrim.qld.gov.au | 61755405487
nicky.h@scenicrim.qld.gov.au | 61755405126
nicole.a@scenicrim.qld.gov.au | 61755405904
nicole.w@scenicrim.qld.gov.au | 61755405659
nikki.b@scenicrim.qld.gov.au | 61755405139
noel.t@scenicrim.qld.gov.au | 61755405301
Noni.H@scenicrim.qld.gov.au | 61755405093
oliver.p@scenicrim.qld.gov.au | 61755405125
Olivia.P@scenicrim.qld.gov.au | 61755405688
ormnorth.l@scenicrim.qld.gov.au | 61755405957
owen.s@scenicrim.qld.gov.au | 61755405663
patricia.r@scenicrim.qld.gov.au | 61755405294
paul.g@scenicrim.qld.gov.au | 61755405949
Paula.H@scenicrim.qld.gov.au | 61755405950
paula.l@scenicrim.qld.gov.au | 61755405455
Pedro.P@scenicrim.qld.gov.au | 61755405249
peter.a@scenicrim.qld.gov.au | 61755405683
peter.b@scenicrim.qld.gov.au | 61755405238
peter.k@scenicrim.qld.gov.au | 61755405265
phil.d@scenicrim.qld.gov.au | 61755405431
polly.w@scenicrim.qld.gov.au | 61755405226
Pravin.M@scenicrim.qld.gov.au | 61755405133
racheal.m@scenicrim.qld.gov.au | 61754633066
rachel.b@scenicrim.qld.gov.au | 61755405921
Raj.K@scenicrim.qld.gov.au | 61755405176
Ray.K@scenicrim.qld.gov.au | 61755405216
Rayhan.S@scenicrim.qld.gov.au | 61755405496
raylene.j@scenicrim.qld.gov.au | 61755405472
rebecca.d@scenicrim.qld.gov.au | 61755405318
Rebecca.f@scenicrim.qld.gov.au | 61755405609
rebecca.r@scenicrim.qld.gov.au | 61755405963
renaee.j@scenicrim.qld.gov.au | 61755405135
Renee.Wa@scenicrim.qld.gov.au | 61755405945
rhiannon.t@scenicrim.qld.gov.au | 61755405952
richard.h@scenicrim.qld.gov.au | 61755405651
richard.s@scenicrim.qld.gov.au | 61755405266
rick.h@scenicrim.qld.gov.au | 61755405184
robyn.c@scenicrim.qld.gov.au | 61755405082
Robyn.F@scenicrim.qld.gov.au | 61755405396
robyn.r@scenicrim.qld.gov.au | 61755405607
ross.k@scenicrim.qld.gov.au | 61755405138
rylie.a@scenicrim.qld.gov.au | 61755405623
Santosh.KC@scenicrim.qld.gov.au | 61755405310
sarah.b@scenicrim.qld.gov.au | 61755405635
Sarah.F@scenicrim.qld.gov.au | 61755405421
Sarah.T@scenicrim.qld.gov.au | 61755405376
sarita.k@scenicrim.qld.gov.au | 61755405694
scott.o@scenicrim.qld.gov.au | 61755405439
scott.ob@scenicrim.qld.gov.au | 61755405223
scott.w@scenicrim.qld.gov.au | 61755405279
SESEOC1@scenicrim.qld.gov.au | 61755405137
SESEOC2@scenicrim.qld.gov.au | 61755405131
SESEOC3@scenicrim.qld.gov.au | 61755405144
SESEOC4@scenicrim.qld.gov.au | 61755405145
SESEOC5@scenicrim.qld.gov.au | 61755405136
seslocalcontroller@scenicrim.qld.gov.au | 61755405640
Shane.G@scenicrim.qld.gov.au | 61755405429
shane.m@scenicrim.qld.gov.au | 61755405362
shane.r@scenicrim.qld.gov.au | 61755405359
Shantel.T@scenicrim.qld.gov.au | 61755405267
Sharon.P@scenicrim.qld.gov.au | 61755405648
sharyn.k@scenicrim.qld.gov.au | 61755405284
shaun.a@scenicrim.qld.gov.au | 61755405177
Shaun.C@scenicrim.qld.gov.au | 61755405422
shaun.w@scenicrim.qld.gov.au | 61755405973
shaun.wr@scenicrim.qld.gov.au | 61755405664
Shona.V@scenicrim.qld.gov.au | 61755405159
Simon.H@scenicrim.qld.gov.au | 61755405349
skype.t@scenicrim.qld.gov.au | 61755405689
sonja.r@scenicrim.qld.gov.au | 61755405976
srrcaudio@scenicrim.qld.gov.au | 61755405113
stephen.b@scenicrim.qld.gov.au | 61755405915
stephen.m@scenicrim.qld.gov.au | 61755405438
steve.a@scenicrim.qld.gov.au | 61755405453
Sudheer.P@scenicrim.qld.gov.au | 61755405647
Susan.P@scenicrim.qld.gov.au | 61755405225
susan.w@scenicrim.qld.gov.au | 61755405251
sylvia.s@scenicrim.qld.gov.au | 61755405372
Tara.M@scenicrim.qld.gov.au | 61755405234
Tara.W@scenicrim.qld.gov.au | 61755405418
Taylor.K@scenicrim.qld.gov.au | 61755405477
tegan.s@scenicrim.qld.gov.au | 61755405481
terence.h@scenicrim.qld.gov.au | 61755405969
terry.h@scenicrim.qld.gov.au | 61755405665
terry.r@scenicrim.qld.gov.au | 61755405187
tia.b@scenicrim.qld.gov.au | 61755405239
tickets.bd@scenicrim.qld.gov.au | 61755405965
tickets.bh@scenicrim.qld.gov.au | No number required
timothy.b@scenicrim.qld.gov.au | 61755405644
Timothy.S@scenicrim.qld.gov.au | 61755405498
tmfd5473@scenicrim.qld.gov.au | 61755405473
tony.s@scenicrim.qld.gov.au | 61755405629
training1@scenicrim.qld.gov.au | 61755405671
training10@scenicrim.qld.gov.au | 61755405680
training2@scenicrim.qld.gov.au | 61755405672
training3@scenicrim.qld.gov.au | 61755405673
training4@scenicrim.qld.gov.au | 61755405674
training5@scenicrim.qld.gov.au | 61755405675
training6@scenicrim.qld.gov.au | 61755405676
training7@scenicrim.qld.gov.au | 61755405677
training8@scenicrim.qld.gov.au | 61755405678
training9@scenicrim.qld.gov.au | 61755405679
Trevor.D@scenicrim.qld.gov.au | 61755405141
vannessa.m@scenicrim.qld.gov.au | 61755405620
Velda.M@scenicrim.qld.gov.au | 61755405156
vili.m@scenicrim.qld.gov.au | 61755405185
Viral.P@scenicrim.qld.gov.au | 61755405903
virginia.w@scenicrim.qld.gov.au | 61755405403
vivienne.m@scenicrim.qld.gov.au | 61755405634
warren.n@scenicrim.qld.gov.au | 61755405469
Wayne.ma@scenicrim.qld.gov.au | 61755405388
Yoni.R@scenicrim.qld.gov.au | 61755405954
zane.b@scenicrim.qld.gov.au | 61755405268

## Move-CsUser.csv
UPN | Number
bcc5060@srrc.onmicrosoft.com | 61755405060
Blake.B@scenicrim.qld.gov.au | 61755405605
Boonah.FrontDesk1@srrc.onmicrosoft.com | 61754633042
Boonah.FrontDesk2@srrc.onmicrosoft.com | 61754633035
jordan.t@scenicrim.qld.gov.au | 61755405346
justin.k@scenicrim.qld.gov.au | 61755405981
Ray.K@scenicrim.qld.gov.au | 61755405216
SESEOC2@scenicrim.qld.gov.au | 61755405131
seslocalcontroller@scenicrim.qld.gov.au | 61755405640
adam.j@scenicrim.qld.gov.au | 61755405350
adam.ma@scenicrim.qld.gov.au | 61755405610
Adrian.C@scenicrim.qld.gov.au | 61755405134
adrienne.j@scenicrim.qld.gov.au | 61755405614
Alana.B@scenicrim.qld.gov.au | 61755405233
alisa.t@scenicrim.qld.gov.au | 61755405604
alisha.p@scenicrim.qld.gov.au | 61755405927
Allen.N@scenicrim.qld.gov.au | 61755405432
Allyson.H@scenicrim.qld.gov.au | 61755405499
amanda.d@scenicrim.qld.gov.au | 61755405650
amanda.f@scenicrim.qld.gov.au | 61755405912
amanda.h@scenicrim.qld.gov.au | 61755405401
amanda.l@scenicrim.qld.gov.au | 61755405329
amanda.v@scenicrim.qld.gov.au | 61755405905
Amelia.J@scenicrim.qld.gov.au | 61755405686
Amie.P@scenicrim.qld.gov.au | 61755405299
Amy.R@scenicrim.qld.gov.au | 61755405274
amy.w@scenicrim.qld.gov.au | 61755405658
Anastasia.R@scenicrim.qld.gov.au | 61755405295
andrew.c@scenicrim.qld.gov.au
andrew.cu@scenicrim.qld.gov.au | 61755405290
andrew.h@scenicrim.qld.gov.au | 61755405328
Andrew.Ma@scenicrim.qld.gov.au | 61755405320
andrew.r@scenicrim.qld.gov.au | 61755405991
andrew.s@scenicrim.qld.gov.au | 61755405209
ann.g@scenicrim.qld.gov.au | 61755405151
anna.s@scenicrim.qld.gov.au | 61755405968
anne.b@scenicrim.qld.gov.au | 61755405913
annmarie.w@scenicrim.qld.gov.au | 61755405199
anthony.m@scenicrim.qld.gov.au | 61755405423
asiful.a@scenicrim.qld.gov.au | 61755405939
bcc5051@scenicrim.qld.gov.au | 61755405051
Belinda.J@scenicrim.qld.gov.au | 61755405313
Ben.O@scenicrim.qld.gov.au | 61755405392
bill.k@scenicrim.qld.gov.au | 61755405696
billie.p@scenicrim.qld.gov.au | 61755405319
Blake.H@scenicrim.qld.gov.au | 61755405117
brad.f@scenicrim.qld.gov.au | 61755405173
brad.w@scenicrim.qld.gov.au | 61755405625
brenda.w@scenicrim.qld.gov.au | 61755405660
Brett.F@scenicrim.qld.gov.au | 61755405459
brian.a@scenicrim.qld.gov.au | 61755405188
bridget.p@scenicrim.qld.gov.au | 61755405166
Brittany.H@scenicrim.qld.gov.au | 61755405410
bronwyn.c@scenicrim.qld.gov.au | 61755405601
byron.s@scenicrim.qld.gov.au | 61755405692
cameron.t@scenicrim.qld.gov.au | 61755405474
Carleen.O@scenicrim.qld.gov.au | 61755405163
Carly.L@scenicrim.qld.gov.au | 61755405695
carmel.d@scenicrim.qld.gov.au | 61755405229
carmen.h@scenicrim.qld.gov.au | 61755405281
carolann.b@scenicrim.qld.gov.au | 61755405920
caroline.m@scenicrim.qld.gov.au | 61755405980
Carolyn.G@scenicrim.qld.gov.au | 61755405236
cassandra.n@scenicrim.qld.gov.au | 61755405434
catherine.k@scenicrim.qld.gov.au | 61755405681
Catherine.M@scenicrim.qld.gov.au | 61755405289
chantal.b@scenicrim.qld.gov.au | 61755405243
charlie.w@scenicrim.qld.gov.au | 61754633058
cherece.j@scenicrim.qld.gov.au | 61755405661
cheryl.h@scenicrim.qld.gov.au | 61755405160
Chloe.E@scenicrim.qld.gov.au | 61755405204
Chris.C@scenicrim.qld.gov.au | 61755405698
Christopher.G@scenicrim.qld.gov.au | 61755405494
christy.s@scenicrim.qld.gov.au | 61755405399
cindy.w@scenicrim.qld.gov.au | 61755405254
claire.d@scenicrim.qld.gov.au | 61755405662
clare.n@scenicrim.qld.gov.au | 61755405261
Clyde.P@scenicrim.qld.gov.au | 61755405080
colin.m@scenicrim.qld.gov.au | 61755405246
craig.h@scenicrim.qld.gov.au | 61755405420
craig.he@scenicrim.qld.gov.au | 61755405489
craig.mc@scenicrim.qld.gov.au | 61755405956
craig.p@scenicrim.qld.gov.au | 61754633047
daadmin@scenicrim.qld.gov.au | 61755405158
damian.t@scenicrim.qld.gov.au | 61755405628
daniel.mc@scenicrim.qld.gov.au | 61755405331
daniel.s@scenicrim.qld.gov.au | 61755405979
daniel.sm@scenicrim.qld.gov.au | 61755405486
danni.m@scenicrim.qld.gov.au | 61755405641
darren.l@scenicrim.qld.gov.au | 61754633057
David.A@scenicrim.qld.gov.au | 61755405951
david.k@scenicrim.qld.gov.au | 61755405100
david.r@scenicrim.qld.gov.au | 61755405191
Dean.K@scenicrim.qld.gov.au | 61755405114
dean.w@scenicrim.qld.gov.au | 61755405377
Deanna.F@scenicrim.qld.gov.au | 61755405317
Debbie.S@scenicrim.qld.gov.au | 61755405690
debra.h@scenicrim.qld.gov.au | 61755405255
debra.t@scenicrim.qld.gov.au | 61754633060
dee.c@scenicrim.qld.gov.au | 61755405308
Deeanne.T@scenicrim.qld.gov.au | 61755405606
desley.a@scenicrim.qld.gov.au | 61755405914
Donna.C@scenicrim.qld.gov.au | 61755405076
donna.r@scenicrim.qld.gov.au | 61755405348
donnalee.o@scenicrim.qld.gov.au | 61755405608
doug.h@scenicrim.qld.gov.au | 61755405902
drift.i@scenicrim.qld.gov.au | 61755405330
duncan.m@scenicrim.qld.gov.au | 61755405406
Ellie.B@scenicrim.qld.gov.au | 61755405309
elva.s@scenicrim.qld.gov.au | 61755405276
emily.b@scenicrim.qld.gov.au | 61755405985
emma.th@scenicrim.qld.gov.au | 61755405172
erin.p@scenicrim.qld.gov.au | 61755405316
frank.a@scenicrim.qld.gov.au | 61755405347
Gail.K@scenicrim.qld.gov.au | 61755405271
gavin.g@scenicrim.qld.gov.au | 61755405198
gayanne.k@scenicrim.qld.gov.au | 61755405288
Genevieve.L@scenicrim.qld.gov.au | 61755405143
georgina.w@scenicrim.qld.gov.au | 61755405923
gerald.p@scenicrim.qld.gov.au | 61755405970
Grace.R@scenicrim.qld.gov.au | 61755405426
graham.a@scenicrim.qld.gov.au | 61755405190
greg.c@scenicrim.qld.gov.au | 61755405105
greg.h@scenicrim.qld.gov.au | 61755405186
Hazel.M@scenicrim.qld.gov.au | 61755405162
heather.n@scenicrim.qld.gov.au | 61755405205
Heerah.K@scenicrim.qld.gov.au | 61755405602
Helen.R@scenicrim.qld.gov.au | 61755405458
Hera.L@scenicrim.qld.gov.au | 61755405074
Hiral.P@scenicrim.qld.gov.au | 61755405953
Holly.H@scenicrim.qld.gov.au | 61755405206
hr@scenicrim.qld.gov.au | 61755405613
Ian.M@scenicrim.qld.gov.au | 61755405942
india.b@scenicrim.qld.gov.au | 61755405298
info_moogerah@scenicrim.qld.gov.au | 61755405600
ingrid.l@scenicrim.qld.gov.au | 61754633061
insync@scenicrim.qld.gov.au | 61755405337
integrity@scenicrim.qld.gov.au
irene.g@scenicrim.qld.gov.au | 61755405055
isabel.f@scenicrim.qld.gov.au | 61755405909
jackie.l@scenicrim.qld.gov.au | 61755405655
Jacob.O@scenicrim.qld.gov.au | 61755405622
Jaime.M@scenicrim.qld.gov.au | 61755405073
jairo.c@scenicrim.qld.gov.au | 61755405061
james.do@scenicrim.qld.gov.au | 61755405643
James.OK@scenicrim.qld.gov.au | 61755405656
james.w@scenicrim.qld.gov.au | 61755405938
Jamie.B@scenicrim.qld.gov.au | 61755405368
jan.h@scenicrim.qld.gov.au | 61755405684
jane.g@scenicrim.qld.gov.au | 61755405667
Jane.S@scenicrim.qld.gov.au | 61755405972
jared.k@scenicrim.qld.gov.au | 61755405345
jarrod.h@scenicrim.qld.gov.au | 61755405917
Jasmine.S@scenicrim.qld.gov.au | 61755405272
Jason.Ca@scenicrim.qld.gov.au | 61755405273
Jason.G@scenicrim.qld.gov.au | 61755405043
jason.h@scenicrim.qld.gov.au | 61755405639
jason.t@scenicrim.qld.gov.au | 61755405483
Jason.Y@scenicrim.qld.gov.au | 61755405270
jeff.b@scenicrim.qld.gov.au | 61755405164
jeff.m@scenicrim.qld.gov.au | 61755405402
jenna.t@scenicrim.qld.gov.au | 61755405398
Jennifer.St@scenicrim.qld.gov.au | 61755405219
jeremey.r@scenicrim.qld.gov.au | 61755405693
jeremy.p@scenicrim.qld.gov.au | 61755405235
Jessica.D@scenicrim.qld.gov.au | 61755405370
Jo.J@scenicrim.qld.gov.au | 61755405425
Jo.Jo@scenicrim.qld.gov.au | 61755405984
Jo-Ann.A@scenicrim.qld.gov.au | 61755405478
joanne.d@scenicrim.qld.gov.au | 61755405342
Joanne.H@scenicrim.qld.gov.au | 61755405691
Joanne.M@scenicrim.qld.gov.au | 61755405631
Jodi.W@scenicrim.qld.gov.au | 61755405245
jodie.m@scenicrim.qld.gov.au | 61755405360
jodie.ma@scenicrim.qld.gov.au | 61754633084
jodie.s@scenicrim.qld.gov.au | 61755405925
jodie.v@scenicrim.qld.gov.au | 61755405452
Joel.S@scenicrim.qld.gov.au | 61755405171
john.ke@scenicrim.qld.gov.au | 61755405193
John.L@scenicrim.qld.gov.au | 61755405627
john.m@scenicrim.qld.gov.au | 61755405427
john.p@scenicrim.qld.gov.au | 61755405283
jon.r@scenicrim.qld.gov.au | 61755405336
Joseph.K@scenicrim.qld.gov.au | 61755405153
judith.h@scenicrim.qld.gov.au | 61755405645
Judy.J@scenicrim.qld.gov.au | 61755405252
Julia.K@scenicrim.qld.gov.au | 61755405994
julia.m@scenicrim.qld.gov.au | 61755405118
julie.o@scenicrim.qld.gov.au | 61755405922
Julie.S@scenicrim.qld.gov.au | 61755405152
Julien.P@scenicrim.qld.gov.au | 61755405056
justin.a@scenicrim.qld.gov.au | 61755405262
justin.s@scenicrim.qld.gov.au | 61755405282
justin.si@scenicrim.qld.gov.au | 61755405989
justin.st@scenicrim.qld.gov.au | 61755405456
Karen.Br@scenicrim.qld.gov.au | 61755405140
Kate.C@scenicrim.qld.gov.au | 61755405428
kate.jo@scenicrim.qld.gov.au | 61755405129
kathy.f@scenicrim.qld.gov.au | 61755405015
katie.n@scenicrim.qld.gov.au | 61755405910
Katrina.C@scenicrim.qld.gov.au | 61755405603
katrina.r@scenicrim.qld.gov.au | 61755405358
kelli.r@scenicrim.qld.gov.au | 61755405263
kelly.l@scenicrim.qld.gov.au | 61755405966
kelly.r@scenicrim.qld.gov.au | 61755405911
kelmeny.f@scenicrim.qld.gov.au | 61755405315
kevin.d@scenicrim.qld.gov.au | 61755405277
Kirby.M@scenicrim.qld.gov.au | 61755405394
Kobi.L@scenicrim.qld.gov.au | 61755405380
kris.v@scenicrim.qld.gov.au | 61755405928
krystal.b@scenicrim.qld.gov.au | 61755405962
Kuda.P@scenicrim.qld.gov.au | 61755405332
kyle.r@scenicrim.qld.gov.au | 61755405485
kylee.m@scenicrim.qld.gov.au | 61755405115
kylie.a@scenicrim.qld.gov.au | 61755405247
Kym.L@scenicrim.qld.gov.au | 61755405293
lacey.s@scenicrim.qld.gov.au | 61755405014
Lana.L@scenicrim.qld.gov.au | 61755405224
Lara.S@scenicrim.qld.gov.au | 61755405075
Lau.c@scenicrim.qld.gov.au | 61755405094
Laura.M@scenicrim.qld.gov.au | 61755405130
lauren.b@scenicrim.qld.gov.au | 61755405632
ldc@scenicrim.qld.gov.au | 61755405940
ldccadmin@scenicrim.qld.gov.au | 61755405934
ldcclogistics@scenicrim.qld.gov.au | 61755405936
ldccmedia@scenicrim.qld.gov.au | 61755405941
ldccoperations@scenicrim.qld.gov.au | 61755405943
ldccplanning@scenicrim.qld.gov.au | 61755405946
ldccplanning1@scenicrim.qld.gov.au | 61755405947
ldccroommanager@scenicrim.qld.gov.au | 61755405633
lea.s@scenicrim.qld.gov.au | 61755405053
Leah.S@scenicrim.qld.gov.au | 61755405343
leanne.bu@scenicrim.qld.gov.au | 61755405617
Leanne.S@scenicrim.qld.gov.au | 61755405256
leisa.f@scenicrim.qld.gov.au | 61755405448
liam.c@scenicrim.qld.gov.au | 61755405253
libby.m@scenicrim.qld.gov.au | 61755405132
Lily.M@scenicrim.qld.gov.au | 61755405901
linda.k@scenicrim.qld.gov.au | 61755405441
linda.p@scenicrim.qld.gov.au | 61755405978
linda.r@scenicrim.qld.gov.au | 61755405303
lisa.c@scenicrim.qld.gov.au | 61755405699
lisa.h@scenicrim.qld.gov.au | 61755405974
lisa.ke@scenicrim.qld.gov.au | 61755405127
lisa.s@scenicrim.qld.gov.au | 61755405986
liz.r@scenicrim.qld.gov.au | 61755405071
luchia.w@scenicrim.qld.gov.au | 61755405430
Luke.A@scenicrim.qld.gov.au | 61755405612
Luke.C@scenicrim.qld.gov.au | 61755405107
luke.v@scenicrim.qld.gov.au | 61755405296
lyle.v@scenicrim.qld.gov.au | 61755405123
Lyndal.C@scenicrim.qld.gov.au | 61755405146
lynne.b@scenicrim.qld.gov.au | 61755405218
Madi.L@scenicrim.qld.gov.au | 61755405697
Malav.P@scenicrim.qld.gov.au | 61755405988
margie.j@scenicrim.qld.gov.au | 61755405196
marie.s@scenicrim.qld.gov.au | 61755405321
marisa.p@scenicrim.qld.gov.au | 61755405493
mark.c@scenicrim.qld.gov.au | 61755405419
mark.d@scenicrim.qld.gov.au | 61755405327
mark.l@scenicrim.qld.gov.au | 61755405241
mark.lu@scenicrim.qld.gov.au | 61755405630
mark.pa@scenicrim.qld.gov.au | 61755405351
Mark.Sl@scenicrim.qld.gov.au | 61755405907
mark.st@scenicrim.qld.gov.au | 61755405278
Marnie.Y@scenicrim.qld.gov.au | 61755405611
marshall.c@scenicrim.qld.gov.au | 61755405405
matt.a@scenicrim.qld.gov.au | 61755405653
Matthew.B@scenicrim.qld.gov.au | 61755405475
matthew.c@scenicrim.qld.gov.au | 61755405169
Matthew.F@scenicrim.qld.gov.au | 61755405231
Maverick.w@scenicrim.qld.gov.au | 61755405361
megan.g@scenicrim.qld.gov.au | 61755405179
Melanie.B@scenicrim.qld.gov.au | 61755405257
melissa.c@scenicrim.qld.gov.au | 61755405916
melissa.m@scenicrim.qld.gov.au | 61755405168
melissa.me@scenicrim.qld.gov.au | 61755405182
melissa.q@scenicrim.qld.gov.au | 61755405220
Melissa.R@scenicrim.qld.gov.au | 61755405180
michael.e@scenicrim.qld.gov.au | 61755405404
michael.g@scenicrim.qld.gov.au | 61755405975
Michael.Wo@scenicrim.qld.gov.au | 61755405016
Minh-Man.N@scenicrim.qld.gov.au | 61755405072
Miranda.C@scenicrim.qld.gov.au | 61755405259
miriam.n@scenicrim.qld.gov.au | 61755405436
Monica.M@scenicrim.qld.gov.au | 61755405202
Nada.M@scenicrim.qld.gov.au | 61755405344
Narendra.s@scenicrim.qld.gov.au | 61755405264
Natika.D@scenicrim.qld.gov.au | 61755405213
nichole.m@scenicrim.qld.gov.au | 61755405670
nick.p@scenicrim.qld.gov.au | 61755405487
nicky.h@scenicrim.qld.gov.au | 61755405126
nicole.a@scenicrim.qld.gov.au | 61755405904
nicole.w@scenicrim.qld.gov.au | 61755405659
nikki.b@scenicrim.qld.gov.au | 61755405139
noel.t@scenicrim.qld.gov.au | 61755405301
Noni.H@scenicrim.qld.gov.au | 61755405093
oliver.p@scenicrim.qld.gov.au | 61755405125
Olivia.P@scenicrim.qld.gov.au | 61755405688
ormnorth.l@scenicrim.qld.gov.au | 61755405957
owen.s@scenicrim.qld.gov.au | 61755405663
patricia.r@scenicrim.qld.gov.au | 61755405294
paul.g@scenicrim.qld.gov.au | 61755405949
paula.l@scenicrim.qld.gov.au | 61755405455
Pedro.P@scenicrim.qld.gov.au | 61755405249
peter.a@scenicrim.qld.gov.au | 61755405683
peter.b@scenicrim.qld.gov.au | 61755405238
peter.k@scenicrim.qld.gov.au | 61755405265
phil.d@scenicrim.qld.gov.au | 61755405431
polly.w@scenicrim.qld.gov.au | 61755405226
Pravin.M@scenicrim.qld.gov.au | 61755405133
racheal.m@scenicrim.qld.gov.au | 61754633066
rachel.b@scenicrim.qld.gov.au | 61755405921
Raj.K@scenicrim.qld.gov.au | 61755405176
Rayhan.S@scenicrim.qld.gov.au | 61755405496
raylene.j@scenicrim.qld.gov.au | 61755405472
rebecca.d@scenicrim.qld.gov.au | 61755405318
Rebecca.f@scenicrim.qld.gov.au | 61755405609
rebecca.r@scenicrim.qld.gov.au | 61755405963
renaee.j@scenicrim.qld.gov.au | 61755405135
Renee.Wa@scenicrim.qld.gov.au | 61755405945
rhiannon.t@scenicrim.qld.gov.au | 61755405952
richard.h@scenicrim.qld.gov.au | 61755405651
richard.s@scenicrim.qld.gov.au | 61755405266
rick.h@scenicrim.qld.gov.au | 61755405184
robyn.c@scenicrim.qld.gov.au | 61755405082
Robyn.F@scenicrim.qld.gov.au | 61755405396
robyn.r@scenicrim.qld.gov.au | 61755405607
ross.k@scenicrim.qld.gov.au | 61755405138
rylie.a@scenicrim.qld.gov.au | 61755405623
Santosh.KC@scenicrim.qld.gov.au | 61755405310
sarah.b@scenicrim.qld.gov.au | 61755405635
Sarah.F@scenicrim.qld.gov.au | 61755405421
Sarah.T@scenicrim.qld.gov.au | 61755405376
sarita.k@scenicrim.qld.gov.au | 61755405694
scott.o@scenicrim.qld.gov.au | 61755405439
scott.ob@scenicrim.qld.gov.au | 61755405223
scott.w@scenicrim.qld.gov.au | 61755405279
Shane.G@scenicrim.qld.gov.au | 61755405429
shane.m@scenicrim.qld.gov.au | 61755405362
shane.r@scenicrim.qld.gov.au | 61755405359
Shantel.T@scenicrim.qld.gov.au | 61755405267
sharyn.k@scenicrim.qld.gov.au | 61755405284
shaun.a@scenicrim.qld.gov.au | 61755405177
Shaun.C@scenicrim.qld.gov.au | 61755405422
shaun.w@scenicrim.qld.gov.au | 61755405973
shaun.wr@scenicrim.qld.gov.au | 61755405664
Shona.V@scenicrim.qld.gov.au | 61755405159
Simon.H@scenicrim.qld.gov.au | 61755405349
skype.t@scenicrim.qld.gov.au | 61755405689
sonja.r@scenicrim.qld.gov.au | 61755405976
stephen.b@scenicrim.qld.gov.au | 61755405915
stephen.m@scenicrim.qld.gov.au | 61755405438
steve.a@scenicrim.qld.gov.au | 61755405453
Sudheer.P@scenicrim.qld.gov.au | 61755405647
Susan.P@scenicrim.qld.gov.au | 61755405225
susan.w@scenicrim.qld.gov.au | 61755405251
sylvia.s@scenicrim.qld.gov.au | 61755405372
Tara.M@scenicrim.qld.gov.au | 61755405234
Tara.W@scenicrim.qld.gov.au | 61755405418
Taylor.K@scenicrim.qld.gov.au | 61755405477
tegan.s@scenicrim.qld.gov.au | 61755405481
terence.h@scenicrim.qld.gov.au | 61755405969
terry.h@scenicrim.qld.gov.au | 61755405665
terry.r@scenicrim.qld.gov.au | 61755405187
tia.b@scenicrim.qld.gov.au | 61755405239
tickets.bd@scenicrim.qld.gov.au | 61755405965
tickets.bh@scenicrim.qld.gov.au
timothy.b@scenicrim.qld.gov.au | 61755405644
Timothy.S@scenicrim.qld.gov.au | 61755405498
tmfd5473@scenicrim.qld.gov.au | 61755405473
tony.s@scenicrim.qld.gov.au | 61755405629
Trevor.D@scenicrim.qld.gov.au | 61755405141
Velda.M@scenicrim.qld.gov.au | 61755405156
vili.m@scenicrim.qld.gov.au | 61755405185
Viral.P@scenicrim.qld.gov.au | 61755405903
virginia.w@scenicrim.qld.gov.au | 61755405403
vivienne.m@scenicrim.qld.gov.au | 61755405634
warren.n@scenicrim.qld.gov.au | 61755405469
Wayne.ma@scenicrim.qld.gov.au | 61755405388
Yoni.R@scenicrim.qld.gov.au | 61755405954
zane.b@scenicrim.qld.gov.au | 61755405268
Yoni.R@scenicrim.qld.gov.au | 61755405954
zane.b@scenicrim.qld.gov.au | 61755405268

## LogB
Bulk Move SfB users to Teams
============================
Start Time: 10/13/2023 20:37:07
Importing file: C:\temp\SRRC-Move-CsUsersB.csv
Total Users to move: 395
=========================================
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c4aca0ab-9a19-49e4-9ddf-42e2a2eb023a.csv".
User Moved Successfully: sip:Boonah.FrontDesk2@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-69b05715-f0c2-4c06-ba78-0552999022c8.csv".
User Moved Successfully: sip:Boonah.FrontDesk1@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7f68c0a6-1312-4b7d-b3ba-593c136e1214.csv".
User Moved Successfully: sip:craig.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2da25fda-c090-482f-a9dc-4806026e85d6.csv".
User Moved Successfully: sip:darren.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-424a8c6c-dd0f-4de3-ab63-76a4aa43ef52.csv".
User Moved Successfully: sip:charlie.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3a8a3f6a-7e01-44e1-a019-8e27d8b680e5.csv".
User Moved Successfully: sip:debra.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3576f03a-3b27-4d21-b016-65efeb91df1e.csv".
User Moved Successfully: sip:ingrid.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-bf7156d5-8df2-4dd1-a691-4a94a1d08b74.csv".
User Moved Successfully: sip:racheal.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-88e1b083-e54c-4290-b24c-f6346d6408d4.csv".
User Moved Successfully: sip:jodie.ma@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7785d7ac-40ab-45cb-b011-7e4e73f6d182.csv".
User Moved Successfully: sip:lacey.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2cb8b686-eb9c-4ca8-8337-abf1d39b4d55.csv".
User Moved Successfully: sip:kathy.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8fc7ca0c-2141-425a-87ca-496cb431db91.csv".
User Moved Successfully: sip:Michael.Wo@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9552f50e-7c7d-4054-a31c-52555cca9117.csv".
User Moved Successfully: sip:Jason.G@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7a8c0870-cfa8-4701-9d7d-43c88272057c.csv".
User Moved Successfully: sip:bcc5051@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-84520aa2-a25f-48b5-b2d4-7be7a80b4be8.csv".
User Moved Successfully: sip:lea.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-437a80b6-3e43-4e23-b579-a06c3b95f749.csv".
User Moved Successfully: sip:irene.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0a604f13-2a82-448c-ad42-c16e3d37cad9.csv".
User Moved Successfully: sip:Julien.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-352f9b26-85f8-4f07-bb14-b18296bf8bca.csv".
User Moved Successfully: sip:bcc5060@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d3313ca1-77ee-4d47-a3a6-89a6ed29129d.csv".
User Moved Successfully: sip:jairo.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9e1ab6b1-b431-4771-9158-9e606ad0827d.csv".
User Moved Successfully: sip:liz.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-73808377-2298-4fbb-a08d-7dacd65b9a55.csv".
User Moved Successfully: sip:Minh-Man.N@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c54c8d4c-82e6-483c-8650-147b58a95ddb.csv".
User Moved Successfully: sip:Jaime.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e1be642f-4499-4ac6-a31f-648815cd7c11.csv".
User Moved Successfully: sip:Hera.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-afabcfb5-2502-4090-b075-8e55803ecd30.csv".
User Moved Successfully: sip:Lara.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-61900b47-a025-432d-966f-a18a48e3f62d.csv".
User Moved Successfully: sip:Donna.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2d8d5c21-1968-471f-92e2-b9f3169cb2f2.csv".
User Moved Successfully: sip:Clyde.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f671625d-09ff-4b89-bd47-23ba25b2e451.csv".
User Moved Successfully: sip:robyn.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ac90df72-2225-444d-8f9b-574fc5881707.csv".
User Moved Successfully: sip:Noni.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c7101cff-5c0f-4fc3-9f12-20473048e178.csv".
User Moved Successfully: sip:Lau.c@scenicrim.qld.gov.au
Move-CsUser : Rollback from Unified Contact Store failed for user: david.k@scenicrim.qld.gov.au with exception: Failed to roll back the user from unified contact store mode as the contact list
export from Exchange failed. Contact list export from Exchange failed with reason code: .
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=David Keenan...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], RollbackException
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-01d239bc-a1c6-4b2a-9ee9-d864ce6b6339.csv".
Failed due to Rollback from Unified Contact Store failed for user: david.k@scenicrim.qld.gov.au with exception: Failed to roll back the user from unified contact store mode as the contact list expo
rt from Exchange failed. Contact list export from Exchange failed with reason code: .
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3b63a140-58c0-44d3-98fb-b5fa3332647e.csv".
User Moved Successfully: sip:greg.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a79325a7-f99a-4862-be52-36ba413f0854.csv".
User Moved Successfully: sip:Luke.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f47dd682-06d5-4706-9d35-5e2451e858c3.csv".
User Moved Successfully: sip:Dean.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fc314c9c-9a22-49bf-a540-7b5868b844f9.csv".
User Moved Successfully: sip:kylee.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ea987e26-5d5d-4908-80af-ea2c96c4aa01.csv".
User Moved Successfully: sip:Blake.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-15bea683-cd59-4a1b-b46c-a6eb7e256687.csv".
User Moved Successfully: sip:julia.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-780dbeb2-b2b6-4671-94b6-cd2fe2289b27.csv".
User Moved Successfully: sip:lyle.v@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7a8f5b5a-4af4-4633-8fc2-64b939caaeda.csv".
User Moved Successfully: sip:oliver.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d29868b5-3550-44d5-b828-1d312f1f67fc.csv".
User Moved Successfully: sip:nicky.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d6180a41-d319-459e-a966-c4a0a9b9d53b.csv".
User Moved Successfully: sip:lisa.ke@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e9422bcb-32fd-41d1-9947-836bd60af0ab.csv".
User Moved Successfully: sip:kate.jo@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f786b7ad-d53f-4a8b-9f98-ae3c4bb4a308.csv".
User Moved Successfully: sip:Laura.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2296e0ea-f443-4ea0-9579-6feed4851bd7.csv".
User Moved Successfully: sip:libby.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ec2baa81-b475-4791-8c7c-84d15eba67fe.csv".
User Moved Successfully: sip:Pravin.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c13e96da-c592-443e-8a66-f0210cc9c6a7.csv".
User Moved Successfully: sip:Adrian.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d378a995-dd77-45b2-8018-112b0c51c81a.csv".
User Moved Successfully: sip:renaee.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b32e67fc-cd19-4560-8296-56b82dd2bd78.csv".
User Moved Successfully: sip:ross.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7ad36d19-61dd-433f-9753-b05ce3f8d51f.csv".
User Moved Successfully: sip:nikki.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1100d833-d8cd-4aa3-a2cc-b805ce6881b4.csv".
User Moved Successfully: sip:Karen.Br@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-42baadaf-4491-4c4d-8515-f63082b7a95f.csv".
User Moved Successfully: sip:Trevor.D@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-edbf26b7-3409-43c4-aa99-a2637312a0ed.csv".
User Moved Successfully: sip:bdl5142@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-20307ea0-5b12-452f-b11a-978f8b0b59b5.csv".
User Moved Successfully: sip:Genevieve.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-28738f71-9e88-444c-b21c-895d664a5d12.csv".
User Moved Successfully: sip:Lyndal.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5c2f5abb-bfc4-45a0-8709-d2e7a8996dcf.csv".
User Moved Successfully: sip:ann.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3d232708-9260-44fe-81b8-4c4ee28e64ed.csv".
User Moved Successfully: sip:Julie.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c98d84e0-2013-41ee-ade3-33c3e08775ef.csv".
User Moved Successfully: sip:Joseph.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-38a3faa8-c6a9-4f13-9b3b-1e2472637c57.csv".
User Moved Successfully: sip:Velda.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-06983204-99ba-44f1-a1c6-4dff16bdc236.csv".
User Moved Successfully: sip:daadmin@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-935d5c62-e4fa-43dc-b4ae-730d8f5dbce6.csv".
User Moved Successfully: sip:Shona.V@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ee8f759a-ba20-48d3-8394-fd6f353298ee.csv".
User Moved Successfully: sip:cheryl.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ec415a44-364c-43ef-9609-2aab2a97d5e5.csv".
User Moved Successfully: sip:Hazel.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0afedf7e-d38e-482e-846a-511bda0d23b3.csv".
User Moved Successfully: sip:Carleen.O@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4a32f8b5-8041-428b-990f-033037444f7d.csv".
User Moved Successfully: sip:jeff.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cd40726a-89ec-40f1-be29-f7de6946dd6d.csv".
User Moved Successfully: sip:bridget.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-97b8bc62-b3a4-435e-a61e-9bf2e9cf4234.csv".
User Moved Successfully: sip:melissa.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3f81efa8-1cef-424a-b7c2-bce4b8e73bc9.csv".
User Moved Successfully: sip:matthew.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-49247afb-763d-4b4d-8f37-577befd81d3c.csv".
User Moved Successfully: sip:Joel.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f0c720b9-79ce-415c-ab78-4a7faacef51a.csv".
User Moved Successfully: sip:emma.th@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-980ae712-d67b-4993-a3ab-203a53772196.csv".
User Moved Successfully: sip:brad.f@scenicrim.qld.gov.au
Move-CsUser : {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to
Teams.","faultCode":5,"faultSubCode":513,"args":[]}
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=Raj Koirala,...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], Exception
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c2740f62-2e8d-4b0b-a695-edda254843a4.csv".
Failed due to {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to Teams.","faultC
ode":5,"faultSubCode":513,"args":[]}
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2d2ca9d0-4190-4cd1-bf77-51a719e805c6.csv".
User Moved Successfully: sip:shaun.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-102a16fc-3160-4069-a25f-9acea8928647.csv".
User Moved Successfully: sip:megan.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-53f5636c-d623-4312-919a-b66dc97413ac.csv".
User Moved Successfully: sip:Melissa.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a74dbe1a-bffe-43f6-9d88-d67e9635460c.csv".
User Moved Successfully: sip:melissa.me@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f6c679bf-68f6-44e9-bdf9-0061ec6ed802.csv".
User Moved Successfully: sip:rick.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d853bc90-2a4b-4167-8e7b-585e026b66bc.csv".
User Moved Successfully: sip:vili.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-37f8ac3c-a0a3-4c58-8ced-1262cbc63b91.csv".
User Moved Successfully: sip:greg.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-522bd691-2239-49a3-8608-d5ac5f3e8716.csv".
User Moved Successfully: sip:terry.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ba6f04d6-b637-4c6f-9127-60d3a8e972a1.csv".
User Moved Successfully: sip:brian.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-93aa9b49-de7d-49dd-8939-3bd058f35200.csv".
User Moved Successfully: sip:graham.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a2cda668-3476-4a58-8a27-b43895086fda.csv".
User Moved Successfully: sip:david.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2060f402-6a43-4a76-94ec-33382b04b825.csv".
User Moved Successfully: sip:john.ke@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c15b9637-f824-4bbd-bc45-5733dc9915f0.csv".
User Moved Successfully: sip:margie.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c7c23a0f-a842-4e4b-9ddb-30483737b0b4.csv".
User Moved Successfully: sip:gavin.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-dba6f950-546f-4f0d-8e89-0d5e8dae6809.csv".
User Moved Successfully: sip:annmarie.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-eee0a5e6-1ea0-491d-817f-06cc3c1b142b.csv".
User Moved Successfully: sip:Monica.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2197fd6b-9622-4ee6-9dab-b9da981e78da.csv".
User Moved Successfully: sip:Chloe.E@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f5865554-d261-40ec-85e3-d63e46c147ee.csv".
User Moved Successfully: sip:heather.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-975ac097-be65-49a9-858b-2eb7861dfb56.csv".
User Moved Successfully: sip:Holly.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-424eaf0b-64d9-40dc-80b3-7080c6663a67.csv".
User Moved Successfully: sip:andrew.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2544adac-221a-484a-aa96-30a3c431bb69.csv".
User Moved Successfully: sip:Natika.D@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e5790ead-2d28-4dbc-b2de-92dc0dcb3c1f.csv".
User Moved Successfully: sip:Ray.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d707dd15-c8f7-4797-a3f0-116251296a46.csv".
User Moved Successfully: sip:lynne.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-74bfcc54-cfbc-4c8e-8ca5-965ae6dca538.csv".
User Moved Successfully: sip:Jennifer.St@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ce85f1d9-540d-4405-aefa-1a571cf9cc2b.csv".
User Moved Successfully: sip:melissa.q@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-83570ee9-338d-4e43-9b4b-828416255e17.csv".
User Moved Successfully: sip:scott.ob@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1fe4dd92-eef0-4b79-b802-3e77168cf3f7.csv".
User Moved Successfully: sip:Lana.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9cbd6ed2-5586-46c7-bff0-de36e920d7ff.csv".
User Moved Successfully: sip:Susan.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-73eb7c4a-c8ba-44cf-84c2-f6e82b30526a.csv".
User Moved Successfully: sip:polly.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7686897a-f016-4ae9-8d3f-d4cc856d513a.csv".
User Moved Successfully: sip:carmel.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8e8c0dab-c6f7-484f-ab9b-3eaf9b39a1d3.csv".
User Moved Successfully: sip:Matthew.F@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ef36ae08-3091-4ca3-92bc-856e8b1afe5f.csv".
User Moved Successfully: sip:Alana.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a9219728-122e-4ec9-b56c-5918269018f0.csv".
User Moved Successfully: sip:Tara.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8c95b44e-08ce-4c8f-9da5-3fdb7e0f8688.csv".
User Moved Successfully: sip:jeremy.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-486c0979-7515-4e6c-bb36-76aa222d3ca3.csv".
User Moved Successfully: sip:Carolyn.G@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0488c8a9-4597-4af0-8f8e-df924dc88137.csv".
User Moved Successfully: sip:peter.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5dceaa07-d9a3-4661-94f7-1deded4e5f98.csv".
User Moved Successfully: sip:tia.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a08c1a23-5234-441b-ac4f-1b959591f498.csv".
User Moved Successfully: sip:mark.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-da744adc-7f09-49d3-ad9a-3f00e4cabb11.csv".
User Moved Successfully: sip:chantal.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-07faa8b8-9e52-42bd-8878-c931172ae6bf.csv".
User Moved Successfully: sip:Jodi.W@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-44ab4d77-1095-4797-9e07-d75d83681163.csv".
User Moved Successfully: sip:colin.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3abf5cec-5d94-47ba-8c83-9cc6263d055e.csv".
User Moved Successfully: sip:kylie.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b8411600-8e2f-4e2f-a53c-74c0144d3d8f.csv".
User Moved Successfully: sip:Pedro.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c7d8678d-07e6-489e-a37c-7438a59404c0.csv".
User Moved Successfully: sip:susan.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c7d18e14-31d9-4e6b-a201-d6cd96025be8.csv".
User Moved Successfully: sip:Judy.J@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f93342dd-8b74-4850-9e53-0a8ee8e14be2.csv".
User Moved Successfully: sip:liam.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-eeeb0f12-3e06-43f9-8d03-d4d59d6262f4.csv".
User Moved Successfully: sip:cindy.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-10fb9bc5-63b2-4558-b166-d2187465376e.csv".
User Moved Successfully: sip:debra.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f7a38b76-15f3-4719-b8e9-954492796575.csv".
User Moved Successfully: sip:Leanne.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-78c59455-889b-4f90-8fae-6f873c6cf894.csv".
User Moved Successfully: sip:Melanie.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0e97b274-baa7-462f-9f8a-9eb9ce567642.csv".
User Moved Successfully: sip:Miranda.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6c159f61-f8a7-4ea1-826a-95288a51f789.csv".
User Moved Successfully: sip:clare.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-92160744-4e5f-4347-ade1-15c55fdda3cb.csv".
User Moved Successfully: sip:justin.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a511eb31-4911-4e4b-a06e-440c0e0e0ea1.csv".
User Moved Successfully: sip:kelli.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-74e46c43-1367-44b5-bab8-6bcf67f62625.csv".
User Moved Successfully: sip:Narendra.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9904bdb8-17ab-4589-8d53-e0667742c902.csv".
User Moved Successfully: sip:peter.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-588f09c3-9dc9-4ebb-8428-264cbbf4bd50.csv".
User Moved Successfully: sip:richard.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3718f232-433e-4633-a0e9-44b6f018b5f6.csv".
User Moved Successfully: sip:Shantel.T@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-39a39b42-3d78-4137-8f6f-9ab61da4936f.csv".
User Moved Successfully: sip:zane.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e35da577-5c92-489c-8237-d4f95dc5c223.csv".
User Moved Successfully: sip:Jason.Y@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4e7b47ba-47aa-40fa-a738-51093547fa98.csv".
User Moved Successfully: sip:Gail.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9300fd08-d9bb-4d15-a694-654c923ddb83.csv".
User Moved Successfully: sip:Jasmine.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-095338ba-9ebb-4bcf-9b10-7cb10e09bbc9.csv".
User Moved Successfully: sip:Jason.Ca@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-eebe21e6-ed1d-458e-934e-e79384dc21b6.csv".
User Moved Successfully: sip:Amy.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e84c54b8-7eaa-4a97-96cf-f88b544d5bb3.csv".
User Moved Successfully: sip:elva.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-10f19e47-fbf6-49d4-b07d-34911ed773d8.csv".
User Moved Successfully: sip:kevin.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9c993314-4e0c-4f94-9396-20d2e4212548.csv".
User Moved Successfully: sip:mark.st@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4eec49a2-bdce-4ae5-b49b-84c00fb93038.csv".
User Moved Successfully: sip:scott.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6b9e27b3-59bd-49f6-9048-b5dd43572736.csv".
User Moved Successfully: sip:carmen.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2701e9e7-001e-4415-b7bf-83a3a984599a.csv".
User Moved Successfully: sip:justin.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4e476d3b-5892-40f5-84e7-d0d8c9ec7a38.csv".
User Moved Successfully: sip:john.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3449f989-7434-4d3d-9107-7795d19a9f35.csv".
User Moved Successfully: sip:sharyn.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2acc4a24-671d-41d2-998d-c1a3a0f7d93d.csv".
User Moved Successfully: sip:gayanne.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d438f980-782b-44a4-b762-3031624038b4.csv".
User Moved Successfully: sip:Catherine.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8929de7a-14fd-4793-9745-9c0cccfcc90a.csv".
User Moved Successfully: sip:andrew.cu@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1e92446d-b16b-4635-afae-0d8fcbe2a979.csv".
User Moved Successfully: sip:Kym.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a0862e12-053f-4b30-a2d8-f98a261448d2.csv".
User Moved Successfully: sip:patricia.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-46bc478d-7b38-435b-967b-2cd2b13a37e0.csv".
User Moved Successfully: sip:Anastasia.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-97582b2d-a17d-4054-85cf-dbb7d7a1fdd2.csv".
User Moved Successfully: sip:luke.v@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-424dbda4-4430-43ef-99c2-f2d0f00eb150.csv".
User Moved Successfully: sip:india.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-67a46317-5271-4279-865b-1cfdbc402b80.csv".
User Moved Successfully: sip:Amie.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f510ffc4-95dc-40d7-84fc-e637df3b0e96.csv".
User Moved Successfully: sip:noel.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1a147ebb-3c6d-4935-8186-762ca76f8b85.csv".
User Moved Successfully: sip:CRP5302@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4dae97ef-340e-465c-8381-285aee7e0ef5.csv".
User Moved Successfully: sip:linda.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a9baeba1-183a-4419-b77c-a855781aae39.csv".
User Moved Successfully: sip:dee.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ce44ce7d-0f2b-4b82-9aaa-a0bc4c8df983.csv".
User Moved Successfully: sip:Ellie.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5c8a1da0-0a5e-40bd-a218-9d8e1e447137.csv".
User Moved Successfully: sip:Santosh.KC@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2e6ce8a0-6d79-4d64-ac14-6181e54456f0.csv".
User Moved Successfully: sip:Belinda.J@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-317e70b4-43c5-40f5-ad65-5bfe285f71a8.csv".
User Moved Successfully: sip:kelmeny.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a6a8ca89-ee5a-41b6-ae1a-4ab2c49d4a3a.csv".
User Moved Successfully: sip:erin.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-715eeaa1-c9ba-46ea-98c1-93a04f6f5898.csv".
User Moved Successfully: sip:Deanna.F@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-730d1d15-a480-4e31-b286-f041ba2f4e5c.csv".
User Moved Successfully: sip:rebecca.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-970c20fa-ea20-48fb-ad08-a918c74e1bcc.csv".
User Moved Successfully: sip:billie.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b66a07e7-7454-4469-b9cc-d7e1171cc012.csv".
User Moved Successfully: sip:Andrew.Ma@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-97bcc59f-05c0-4f4d-b232-5ae605dae71d.csv".
User Moved Successfully: sip:marie.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9c70ede4-c54f-4caa-9c22-00d3d46d2fd5.csv".
User Moved Successfully: sip:mark.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-af219a19-7d88-4e5b-b1bb-d3354c5c071c.csv".
User Moved Successfully: sip:andrew.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8b8bb2ac-ceca-4a86-8ff7-6ba9a17d862d.csv".
User Moved Successfully: sip:amanda.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a044ba7f-6735-4364-b33d-134d17cb5664.csv".
User Moved Successfully: sip:drift.i@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4c18a114-f63f-4e60-8265-0ad6014e8569.csv".
User Moved Successfully: sip:daniel.mc@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-07d987c2-e1b0-463e-8bc1-a266d0527d0a.csv".
User Moved Successfully: sip:Kuda.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-af21a188-1aa9-4ce9-b876-a16c94496a6e.csv".
User Moved Successfully: sip:jon.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-97c8e6b7-fb78-46be-8299-7486a5720e5d.csv".
User Moved Successfully: sip:insync@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3543d6d9-b16b-4864-9cdd-c5082a8dd63f.csv".
User Moved Successfully: sip:joanne.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fbdb1d1a-4e14-4393-af92-a40c3ba70eb9.csv".
User Moved Successfully: sip:Leah.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fd19ca5e-9191-4d12-9fc8-473caee2f4f5.csv".
User Moved Successfully: sip:Nada.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a5231350-e92c-4f39-b74e-1206c9ee8abb.csv".
User Moved Successfully: sip:jared.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1adad20d-9523-4a44-a4a5-7985b1d9ed03.csv".
User Moved Successfully: sip:jordan.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9b936fd3-d373-44e0-9c36-12a458fc736b.csv".
User Moved Successfully: sip:frank.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5bb78ee5-3cc0-4b8e-baad-748b39911fdd.csv".
User Moved Successfully: sip:donna.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-513797b0-4432-4f8a-810e-d5b2ffbef487.csv".
User Moved Successfully: sip:Simon.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a1c622da-628e-467e-a8b9-1238e31c6bdb.csv".
User Moved Successfully: sip:adam.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-66aabc3b-b0b5-4326-885e-58f86e3508b8.csv".
User Moved Successfully: sip:mark.pa@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f2bbc7b4-5e15-4a9c-869f-74b644b77b8d.csv".
User Moved Successfully: sip:katrina.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-82b742c8-11f3-46a2-9c80-b83b3bdf61ab.csv".
User Moved Successfully: sip:shane.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-494b5c62-dde1-4432-899f-d905eb0982a3.csv".
User Moved Successfully: sip:jodie.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b8105a30-0ede-45f3-9b7b-b269e07ddbe6.csv".
User Moved Successfully: sip:Maverick.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-83755463-466a-4b08-8a26-b8a02974b9ea.csv".
User Moved Successfully: sip:shane.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1723eafc-2f47-4c3f-8fe5-5227789cf224.csv".
User Moved Successfully: sip:Jamie.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-16b6f133-381b-4ca3-b81e-d14a72149461.csv".
User Moved Successfully: sip:Jessica.D@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8ad7c1ab-7798-4e18-835e-03065124981a.csv".
User Moved Successfully: sip:sylvia.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4e001491-de4c-41b7-bf5d-ecae1954e9a7.csv".
User Moved Successfully: sip:Sarah.T@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-713a2ef4-4148-4b78-ad6a-8089c0ef9ae2.csv".
User Moved Successfully: sip:dean.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-87ef1fe0-e4a1-4a41-b6bf-5bbb4f83e3d5.csv".
User Moved Successfully: sip:Kobi.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6b09659d-944a-4254-a3a1-c6591e2fd17f.csv".
User Moved Successfully: sip:Wayne.ma@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-45d90974-eaa8-4278-803c-6c9bb2a8c999.csv".
User Moved Successfully: sip:Ben.O@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6b21cf38-8f22-4401-aadc-8822dbea23c4.csv".
User Moved Successfully: sip:Kirby.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0c28d5d0-cf29-4938-a376-280dc6658730.csv".
User Moved Successfully: sip:Robyn.F@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-51ebc38f-03ff-4730-a322-b2d4cfe38202.csv".
User Moved Successfully: sip:jenna.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e1516be0-9a50-44de-aaaf-56986285ce43.csv".
User Moved Successfully: sip:christy.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-463bc94d-08ba-4206-82c3-b1d5286eebb9.csv".
User Moved Successfully: sip:amanda.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3e3fe643-3941-4267-b56b-6663011afd85.csv".
User Moved Successfully: sip:jeff.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b1c2e806-42bb-42c1-8b22-f16ffab39fcc.csv".
User Moved Successfully: sip:virginia.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d2158ba4-9f8e-4287-b27c-3d8eebce3443.csv".
User Moved Successfully: sip:michael.e@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-14825ac7-4bd4-44f3-a5e9-edcaa154fb8d.csv".
User Moved Successfully: sip:marshall.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-19bc260a-7d7f-4ee4-a2d8-3665fbadbd52.csv".
User Moved Successfully: sip:duncan.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6ee1830e-0c24-4fcd-ab38-7554ae6da9a6.csv".
User Moved Successfully: sip:Brittany.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9a8686e0-e4b0-45dc-9f1b-887150c50c23.csv".
User Moved Successfully: sip:Tara.W@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-aced830e-48a9-4a03-85e7-15fb859beb85.csv".
User Moved Successfully: sip:mark.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7ed7ed29-8087-417a-aa62-b696179024e2.csv".
User Moved Successfully: sip:craig.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5be4327c-67aa-4973-8e13-671d65c94582.csv".
User Moved Successfully: sip:Sarah.F@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b8a21884-195f-403b-a904-356b6a1ac540.csv".
User Moved Successfully: sip:Shaun.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3a407bf0-5f95-4c35-a26e-b3a69afa5e8c.csv".
User Moved Successfully: sip:anthony.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0fbc5fdd-cb67-4f85-b3cb-3f1615140bcd.csv".
User Moved Successfully: sip:MR3D@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c562dd17-acf6-4f75-a900-3ac7d2d40936.csv".
User Moved Successfully: sip:Jo.J@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5eba3795-3923-4b1f-9649-c57354e43739.csv".
User Moved Successfully: sip:Grace.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-532aed35-6781-4ea1-be82-d5e8894e0c9f.csv".
User Moved Successfully: sip:john.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3227af31-2ec5-4380-af36-e4b617aa6f27.csv".
User Moved Successfully: sip:Kate.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a3f2289f-c514-4ea5-bf5e-5da0d637d734.csv".
User Moved Successfully: sip:Shane.G@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1eabda56-119a-4671-b704-4ea11c048e00.csv".
User Moved Successfully: sip:luchia.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-76670a47-cdbc-40a6-be43-51ddeed20ded.csv".
User Moved Successfully: sip:phil.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1ba9e383-5cd0-4bda-8689-2d19cd141d79.csv".
User Moved Successfully: sip:Allen.N@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e19caf84-4c0b-4e3e-afa7-7c68efcb8ddf.csv".
User Moved Successfully: sip:cassandra.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c547fd5a-bc02-4921-beb9-d58929e7e6bd.csv".
User Moved Successfully: sip:miriam.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2510c4ba-573a-4e55-9e50-e84c06838d72.csv".
User Moved Successfully: sip:stephen.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-dafeeeda-bc91-4542-aa93-d4f258e85e5e.csv".
User Moved Successfully: sip:scott.o@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-535bacd9-d9b9-4f77-8f9b-4ede8ca3c127.csv".
User Moved Successfully: sip:linda.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-66da2e8a-4c79-4a3b-9851-c4036adc8493.csv".
User Moved Successfully: sip:leisa.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-bec8f3dc-9488-41ca-8e6d-96717af9e62a.csv".
User Moved Successfully: sip:jodie.v@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ca65043c-808f-4333-8df6-ac27db1cdbf3.csv".
User Moved Successfully: sip:steve.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0b709c7b-9a3c-4655-92a8-70d308494a42.csv".
User Moved Successfully: sip:paula.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-591660a6-044e-4b97-b064-d2dbdb5aab1e.csv".
User Moved Successfully: sip:justin.st@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-89724bd4-4091-4e08-ba72-c6fb73fddd33.csv".
User Moved Successfully: sip:Helen.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-12a30a6a-d967-43a3-a17e-b1070159dc70.csv".
User Moved Successfully: sip:Brett.F@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8a7072e0-b7ca-4943-acd7-71741320679e.csv".
User Moved Successfully: sip:warren.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ef69fe17-6c41-4fd4-8f9d-430ec899fe85.csv".
User Moved Successfully: sip:raylene.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2984c73c-0645-42b7-a14c-5265aac7a3e5.csv".
User Moved Successfully: sip:tmfd5473@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-67bf6e9f-47af-4205-bf73-e21ae8a005db.csv".
User Moved Successfully: sip:cameron.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ca8dbc22-9053-4f6e-902e-b149069dff17.csv".
User Moved Successfully: sip:Matthew.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b208524b-0f76-46ff-bfa0-ed0f1140c5e8.csv".
User Moved Successfully: sip:Taylor.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-846698f6-b652-43ed-8d48-3df11901d9ab.csv".
User Moved Successfully: sip:Jo-Ann.A@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7f146833-880a-49d1-a2b3-3ca3769984ac.csv".
User Moved Successfully: sip:tegan.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-72b3725b-e70f-4d2d-bf9a-ecf1d135683a.csv".
User Moved Successfully: sip:jason.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-23adc9f4-9a5e-4aeb-a80d-005fe5854e9b.csv".
User Moved Successfully: sip:kyle.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-012b1342-1b7b-4ae0-8d2f-1d1d94085b40.csv".
User Moved Successfully: sip:daniel.sm@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-252d17d5-8732-4c89-989b-7e5b0632eb8d.csv".
User Moved Successfully: sip:nick.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c3d53799-a75d-4ef1-8603-44c3d0f4a757.csv".
User Moved Successfully: sip:craig.he@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1fcf0807-aad0-4ed0-b10a-c21252deae99.csv".
User Moved Successfully: sip:marisa.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-955a04f0-4337-463f-aeea-3934b05a7878.csv".
User Moved Successfully: sip:Christopher.G@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ef4e2cf5-74e4-4857-9936-d4c085478c02.csv".
User Moved Successfully: sip:Rayhan.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-60503b9c-fd63-46de-8b79-9a67e773f6ad.csv".
User Moved Successfully: sip:Timothy.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-df657348-fe2a-4988-ad7d-d480c077e635.csv".
User Moved Successfully: sip:Allyson.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f1be277b-026a-4950-ba32-8ee3cd7400b7.csv".
User Moved Successfully: sip:info_moogerah@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-867f76a0-d155-4368-abca-6b29315c6eb5.csv".
User Moved Successfully: sip:bronwyn.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f1fd382e-269f-4c38-930c-ecb90875c889.csv".
User Moved Successfully: sip:Heerah.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fde78dd0-a0fe-4d36-91f3-20a7ed415f7b.csv".
User Moved Successfully: sip:Katrina.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6e98144d-ebf9-47c3-8991-f58b1daa3f76.csv".
User Moved Successfully: sip:alisa.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3c958736-fd0c-42f4-99b2-a08286f031bd.csv".
User Moved Successfully: sip:Blake.B@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d33cbfb2-1afb-410d-a48e-c59cb0286a20.csv".
User Moved Successfully: sip:Deeanne.T@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7f192f35-078c-4c8e-94e6-3573906f7a64.csv".
User Moved Successfully: sip:robyn.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-882193c9-f852-4a3d-98c4-aba2def6b1e5.csv".
User Moved Successfully: sip:donnalee.o@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-00edbf61-904e-47cd-bd47-60f38c5227c0.csv".
User Moved Successfully: sip:Rebecca.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e114b2d8-1f68-4ca3-ab3e-7516b962f01f.csv".
User Moved Successfully: sip:adam.ma@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-485b4dcd-4d55-4233-a9d5-f03a16aca684.csv".
User Moved Successfully: sip:Marnie.Y@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-42a58134-919d-49ad-a015-479360e9dad9.csv".
User Moved Successfully: sip:Luke.A@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b8cc6f88-3f3d-45b3-bca0-3be61969233b.csv".
User Moved Successfully: sip:hr@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-75eeed29-2271-4536-8a4f-9b9edbd0ea2c.csv".
User Moved Successfully: sip:adrienne.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-20b46bc2-a286-4be0-97cd-ae9cd98c7865.csv".
User Moved Successfully: sip:leanne.bu@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f7432223-faf1-41b7-8c02-72b15b16fab6.csv".
User Moved Successfully: sip:Jacob.O@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-909384e8-1dfd-448e-a9d0-f2cbb732f97e.csv".
User Moved Successfully: sip:rylie.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-400d13c8-e120-4acf-a210-74f14b74d6c1.csv".
User Moved Successfully: sip:brad.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-80937c9e-22e3-4ab9-90a4-f13051aa1244.csv".
User Moved Successfully: sip:John.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-92510bf8-c8d3-4a8a-abac-84d83c6f24d7.csv".
User Moved Successfully: sip:damian.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-bf1df046-b0a3-4e35-9566-51d94b15a2bf.csv".
User Moved Successfully: sip:tony.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-70557301-8412-41c0-a315-5ae43637671d.csv".
User Moved Successfully: sip:mark.lu@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-efc2e05b-ca24-44b5-acc6-16b362a748af.csv".
User Moved Successfully: sip:Joanne.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-976f808d-96e7-4b2d-9b42-9ca5c78ed3b8.csv".
User Moved Successfully: sip:lauren.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-dbf9efad-4d54-4a96-965a-fe401987e41f.csv".
User Moved Successfully: sip:ldccroommanager@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9d2edf4a-ffd3-490a-a71d-cd0a8f4329b7.csv".
User Moved Successfully: sip:vivienne.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4f39e5ed-954c-4439-9bb9-8a106ab5702f.csv".
User Moved Successfully: sip:sarah.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-61d7ea13-37e9-404c-9b88-088ba94bfafb.csv".
User Moved Successfully: sip:jason.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-26e3e90e-035d-401d-8d0e-74702aabfe6f.csv".
User Moved Successfully: sip:danni.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-efddab53-1e99-4228-a6ef-33c459c29844.csv".
User Moved Successfully: sip:james.do@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b6618f34-18ae-40b3-a673-25be766e910a.csv".
User Moved Successfully: sip:timothy.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4ed53434-7e9a-4f2a-9ad7-9b4d2f46336c.csv".
User Moved Successfully: sip:judith.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-90b51b7c-c366-4410-8d82-fd2f471f2365.csv".
User Moved Successfully: sip:Sudheer.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-af67fa62-9139-4e57-935c-1a7a7a03ee97.csv".
User Moved Successfully: sip:amanda.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f3d90722-70ce-478e-b159-da1fe9c44be9.csv".
User Moved Successfully: sip:richard.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-662d6a48-f6cb-4b08-910d-7275832e6572.csv".
User Moved Successfully: sip:matt.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-899ccf43-2b73-41da-95e2-c80394bf99fe.csv".
User Moved Successfully: sip:jackie.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e4ab390d-4f32-4cde-8b59-fda6ac7fe245.csv".
User Moved Successfully: sip:James.OK@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-047c9bb0-cf1d-4e20-b2ce-df7aa47834e7.csv".
User Moved Successfully: sip:amy.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-03b8f31e-e42f-4ee3-94a9-3b2ba2500de4.csv".
User Moved Successfully: sip:nicole.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d3a811e2-f585-4290-b3f7-a94762072fa8.csv".
User Moved Successfully: sip:brenda.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c92e2d44-b8e9-488e-9754-af6ff05d71fb.csv".
User Moved Successfully: sip:cherece.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-df4e56e0-8f6e-46bd-8ecc-76160d7ccf68.csv".
User Moved Successfully: sip:claire.d@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fcf0b663-83a7-4aa5-95a9-cc47f0ca68c1.csv".
User Moved Successfully: sip:owen.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2049d8e3-98c3-475c-b2c6-d02d42962c63.csv".
User Moved Successfully: sip:shaun.wr@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2eeadc63-5156-4371-9581-0ec26dd6f68e.csv".
User Moved Successfully: sip:terry.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-442cb7ee-19e3-4c30-b9b8-fbf2910aa90f.csv".
User Moved Successfully: sip:jane.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4ab415d7-2e8d-4d9c-9f59-77bd98abbf88.csv".
User Moved Successfully: sip:nichole.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8b7cf86e-6219-49f2-b5da-dcb6de460e64.csv".
User Moved Successfully: sip:catherine.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-bbeda5ce-9cb0-4546-b6f2-095eaf0a7ca4.csv".
User Moved Successfully: sip:peter.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-948c1514-ff91-48ef-ab18-60c95369b9c4.csv".
User Moved Successfully: sip:jan.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7a487412-cf99-4df2-afbd-13cb66efcaea.csv".
User Moved Successfully: sip:Amelia.J@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-057a998a-e655-4d61-8e9e-746abc43ef72.csv".
User Moved Successfully: sip:Olivia.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c02b25a9-4132-4caf-a4f4-d683d9f14d8e.csv".
User Moved Successfully: sip:skype.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-85f8567a-d23e-4740-b68a-ff71d73e3b5a.csv".
User Moved Successfully: sip:Debbie.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cfb33d44-4d20-42d6-84f1-a0f18615b56b.csv".
User Moved Successfully: sip:Joanne.H@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-09bed745-6ca5-4e06-a752-6f763e404566.csv".
User Moved Successfully: sip:byron.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2ec31419-6200-45e3-adaf-207ad2bac50b.csv".
User Moved Successfully: sip:jeremey.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a1c14151-b9e9-4f12-b35b-7c875bb023ba.csv".
User Moved Successfully: sip:sarita.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cf6b989c-0abe-40bc-abdb-3edb768263c2.csv".
User Moved Successfully: sip:Carly.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-41ec13df-e345-43b8-b2e7-dcbd1a8ccebe.csv".
User Moved Successfully: sip:bill.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0933c9a1-2397-40e8-86e9-feb9bd98534e.csv".
User Moved Successfully: sip:Madi.L@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-93c1bfb3-114c-4926-80c4-930a860f9971.csv".
User Moved Successfully: sip:Chris.C@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b2c8b7ad-a6ec-4f17-ba22-086b146c6069.csv".
User Moved Successfully: sip:lisa.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8b7da2de-de51-4e36-ac81-bd5f915cf157.csv".
User Moved Successfully: sip:Lily.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-444328ea-b4d5-453c-9ac2-6ad57dbfbfb5.csv".
User Moved Successfully: sip:doug.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a783926b-8762-457e-8f60-009cc0cc01c7.csv".
User Moved Successfully: sip:Viral.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cd09ec7b-37fe-4716-a4bf-4edb83185303.csv".
User Moved Successfully: sip:nicole.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b7b62b8f-0fea-476a-ac21-50e3df800eab.csv".
User Moved Successfully: sip:amanda.v@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ef4e689a-44fd-4c6f-8bfc-12c7497c7ca5.csv".
User Moved Successfully: sip:Mark.Sl@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1f7cae6e-c3b3-4b22-8f3a-b31d3ac1fb4b.csv".
User Moved Successfully: sip:isabel.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4a33c3e5-a28d-4d67-9de4-fbff8531605d.csv".
User Moved Successfully: sip:katie.n@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c6a066f7-f99d-4acc-a647-efee3402c94b.csv".
User Moved Successfully: sip:kelly.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b28d9b7d-28db-4911-82a1-8f95db62995a.csv".
User Moved Successfully: sip:amanda.f@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-43c436fc-1064-4b07-88de-eb57b77c3901.csv".
User Moved Successfully: sip:anne.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8ddaa594-ae31-43c0-bfe1-3bb1ddc2b7bd.csv".
User Moved Successfully: sip:desley.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e3204838-2756-4294-8ef6-eb34e66c3acf.csv".
User Moved Successfully: sip:stephen.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-45bbd27b-2132-4cdb-b4b7-771b7053f3bf.csv".
User Moved Successfully: sip:melissa.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3acd7635-2101-4664-bc22-f0f06d6e3cab.csv".
User Moved Successfully: sip:jarrod.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f0427f28-cd93-4939-a8df-3c0292319f31.csv".
User Moved Successfully: sip:carolann.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f7843430-05a3-406e-bd21-e4343f1b11e0.csv".
User Moved Successfully: sip:rachel.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-9d21c1b3-e68f-40bd-ab84-798dd7ae5a94.csv".
User Moved Successfully: sip:julie.o@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-32150d9e-2cd7-424b-8801-0e69efe7229f.csv".
User Moved Successfully: sip:georgina.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-99bc3d51-4b12-4630-9f5a-fe9875a10ba4.csv".
User Moved Successfully: sip:jodie.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5351bf8e-3cb0-4c8a-8827-01494b44b43a.csv".
User Moved Successfully: sip:alisha.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6d6ef17e-4a07-4eb5-890f-d077a581f43c.csv".
User Moved Successfully: sip:kris.v@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-272cb9bf-4940-4e79-be6e-3f8d82509fbb.csv".
User Moved Successfully: sip:ldccadmin@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-ec974a1b-a533-4ac9-a6ac-f714e14d6ded.csv".
User Moved Successfully: sip:ldcclogistics@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d56a3cbf-dd88-49dd-bf54-ba696437ea25.csv".
User Moved Successfully: sip:james.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4f06c8f2-4be7-410b-bba0-64ecda048225.csv".
User Moved Successfully: sip:asiful.a@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4505d74c-5a4f-4732-a64a-c88c3ada7c4b.csv".
User Moved Successfully: sip:ldc@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f533110a-fa25-43a7-a36c-a359db87e79d.csv".
User Moved Successfully: sip:ldccmedia@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-a126442d-1811-49f5-9419-69a9f9fe4e93.csv".
User Moved Successfully: sip:Ian.M@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0cce6ce0-f03d-418f-9b60-483d6042e93f.csv".
User Moved Successfully: sip:ldccoperations@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-33e467b6-4fa1-4751-bb3d-5ad97699ef6a.csv".
User Moved Successfully: sip:Renee.Wa@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-458dbca7-616e-458a-8c98-020a5238db5a.csv".
User Moved Successfully: sip:ldccplanning@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cc4567a9-3960-4be2-bd8d-c1b7c72668fa.csv".
User Moved Successfully: sip:ldccplanning1@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-40b083fd-8b23-4763-856a-901830632e64.csv".
User Moved Successfully: sip:paul.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c15d099a-46da-4119-8926-4dc4a17dc12e.csv".
User Moved Successfully: sip:David.A@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-de77314b-ca03-4585-b914-556c420b4f71.csv".
User Moved Successfully: sip:rhiannon.t@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-b05c9e05-05fb-4865-a1e9-932380e29671.csv".
User Moved Successfully: sip:Hiral.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f68a7502-dff2-4373-aa0e-f0b6fe557a04.csv".
User Moved Successfully: sip:Yoni.R@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c8629847-56e7-41f0-9b6d-2d05aae5bfbf.csv".
User Moved Successfully: sip:craig.mc@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-81bc9f46-3be8-4809-a9e0-e6edf73a0f0b.csv".
User Moved Successfully: sip:ormnorth.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-eab60a55-43a7-40f8-8061-54b0df0581fe.csv".
User Moved Successfully: sip:krystal.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-fb9e48a1-a329-4c65-87b5-68e68471d080.csv".
User Moved Successfully: sip:rebecca.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-79316fbc-6b55-40c6-a8f5-c714f8be18cb.csv".
User Moved Successfully: sip:tickets.bd@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0acbb518-be91-4b81-9599-2751ce1de7e0.csv".
User Moved Successfully: sip:kelly.l@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-acff8f38-38ab-4c2e-812d-26844e4a46ea.csv".
User Moved Successfully: sip:anna.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-76a3f5cb-ff8f-4d1f-aa88-2afd0eac607d.csv".
User Moved Successfully: sip:terence.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f2d34c5c-95b4-4a35-bf86-e348eb37c373.csv".
User Moved Successfully: sip:gerald.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f10448e2-cd2c-430b-b019-2af266d8a540.csv".
User Moved Successfully: sip:Jane.S@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-e0659ca3-5c24-4eaf-81af-cc647cc846c8.csv".
User Moved Successfully: sip:shaun.w@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d51730f5-b4d8-4cf5-bde9-f8e533f1e780.csv".
User Moved Successfully: sip:lisa.h@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4d12e552-99b8-440e-aeb4-d0b196da5979.csv".
User Moved Successfully: sip:michael.g@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0296ece1-e399-4f82-9b62-3d0054eedce2.csv".
User Moved Successfully: sip:sonja.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5c33b34b-04f5-4ef5-93ba-1b4eb09e015d.csv".
User Moved Successfully: sip:linda.p@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-c9437c76-a474-49f3-af70-a5ee93ab33dd.csv".
User Moved Successfully: sip:daniel.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3b31aaa0-1d4f-4cfb-b988-b1a2897ee54b.csv".
User Moved Successfully: sip:caroline.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d172616b-3309-4500-9086-2ff1f9853a07.csv".
User Moved Successfully: sip:justin.k@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-cf320a7a-b855-44e9-ae44-7e767fd20b14.csv".
User Moved Successfully: sip:Jo.Jo@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-21528bc1-9c04-4fe8-8359-248f0a9d23b6.csv".
User Moved Successfully: sip:emily.b@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0c06f1b4-fa65-47d4-bf67-919477a3b01e.csv".
User Moved Successfully: sip:lisa.s@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d6eaef17-fed2-4df0-b705-b1e6457fd5aa.csv".
User Moved Successfully: sip:Malav.P@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-6fc3e387-5114-4c1f-b816-7df4bbb43443.csv".
User Moved Successfully: sip:justin.si@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-8d45f5c2-8181-4db9-8cba-cdc65adb70bc.csv".
User Moved Successfully: sip:andrew.r@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3689f279-57b7-4d90-b8cd-f8b6c74dfbf3.csv".
User Moved Successfully: sip:Julia.K@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-963d16f1-7747-42cf-ab09-d1801d7a4540.csv".
User Moved Successfully: sip:106@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-bc779661-2f5c-498d-b328-43c461782371.csv".
User Moved Successfully: sip:andrew.c@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0f4d5892-be9c-47d5-8ab2-250e8ed27995.csv".
User Moved Successfully: sip:andrew.j@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-3c3102a9-b294-498c-801d-2e812b8d2b53.csv".
User Moved Successfully: sip:clf@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-0d2db63e-ef70-4465-87c7-c85455239f01.csv".
User Moved Successfully: sip:clinton.k@scenicrim.qld.gov.au
Move-CsUser : {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to
Teams.","faultCode":5,"faultSubCode":513,"args":[]}
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=David Laegel...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], Exception
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-70bff1c1-3353-4dc3-9435-a6eb079bd6e8.csv".
Failed due to {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to Teams.","faultC
ode":5,"faultSubCode":513,"args":[]}
Move-CsUser : {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to
Teams.","faultCode":5,"faultSubCode":513,"args":[]}
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=EOC1,OU=Disa...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], Exception
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-5a69b184-34a9-4a85-abd1-1bc09c738f22.csv".
Failed due to {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to Teams.","faultC
ode":5,"faultSubCode":513,"args":[]}
Move-CsUser : {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to
Teams.","faultCode":5,"faultSubCode":513,"args":[]}
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=insync onpre...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], Exception
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-65723c09-0977-4140-b43c-21e44722ec71.csv".
Failed due to {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to Teams.","faultC
ode":5,"faultSubCode":513,"args":[]}
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-73027ff6-884c-412c-bd08-a56a855b127a.csv".
User Moved Successfully: sip:integrity@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-f8660e24-06b0-4270-a886-33762def5a26.csv".
User Moved Successfully: sip:IT@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-7dfb38cc-a539-4bf0-81d9-ee86b1f682ba.csv".
User Moved Successfully: sip:nicholas.m@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-312ce4fb-b305-478f-a347-85b1ed7b21de.csv".
User Moved Successfully: sip:Quentin.P@scenicrim.qld.gov.au
Move-CsUser : {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to
Teams.","faultCode":5,"faultSubCode":513,"args":[]}
At C:\Users\a_stephenb\Downloads\SRRC-Bulk-Move-CsUser.ps1:83 char:9
+ Move-CsUser -Identity $upn -Target sipfed.online.lync.com -Cr ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: (CN=SRRC_CC_AH,O...ld,DC=gov,DC=au:OCSADUser) [Move-CsUser], Exception
+ FullyQualifiedErrorId : MoveError,Microsoft.Rtc.Management.AD.Cmdlets.MoveOcsUserCmdlet
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-2243b201-06f8-436a-9ef0-f8833f3adeb8.csv".
Failed due to {"description":"The user could not be moved because he or she has not been an assigned a Team license in Office 365. Users must be licensed before they can be moved to Teams.","faultC
ode":5,"faultSubCode":513,"args":[]}
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-d64f211e-a265-42f3-b71c-88ad22de0819.csv".
User Moved Successfully: sip:tickets.bh@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-1e5286bb-0635-4928-ac6b-cacb02de2c0f.csv".
User Moved Successfully: sip:tony.b@scenicrim.qld.gov.au
Completed processing
Script Duration: 01:02:56.7735240 HH:MM:SS
Start Time: 10/13/2023 20:37:07
Finish Time: 10/13/2023 21:40:04
Users Processed: 389 of 395
Number of Errors: 6

## LogA
Bulk Move SfB users to Teams
============================
Start Time: 10/13/2023 19:48:01
Importing file: C:\temp\SRRC-Move-CsUsersA.csv
Total Users to move: 2
=========================================
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-4f2e97a6-0f51-4c28-871a-e14f0897af59.csv".
User Moved Successfully: sip:SESEOC2@scenicrim.qld.gov.au
Results from this operation can be found at "C:\Users\a_stephenb\AppData\Local\Temp\MoveResults-602fc129-43ed-4a6a-a0f5-a023a145637c.csv".
User Moved Successfully: sip:seslocalcontroller@scenicrim.qld.gov.au
Completed processing
Script Duration: 00:00:22.3292745 HH:MM:SS
Start Time: 10/13/2023 19:48:01
Finish Time: 10/13/2023 19:48:24
Users Processed: 2 of 2
Number of Errors:

## #AssignLog
Bulk Assign numbers to users
============================
Start Time: 10/13/2023 23:53:34
Importing file: C:\temp\SRRC-Move-CsUsersB.csv
Total phonenumber assignments to process: 395
=========================================
1. Assigning sip:Boonah.FrontDesk2@scenicrim.qld.gov.au 61754633035 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user 'sip:Boonah.FrontDesk2@scenicrim.qld.gov.au' is
not found
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : NotFound,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
1. # Assigning Error sip:Boonah.FrontDesk2@scenicrim.qld.gov.au 61754633035 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
2. Assigning sip:Boonah.FrontDesk1@scenicrim.qld.gov.au 61754633042 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user 'sip:Boonah.FrontDesk1@scenicrim.qld.gov.au' is
not found
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : NotFound,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
2. # Assigning Error sip:Boonah.FrontDesk1@scenicrim.qld.gov.au 61754633042 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
3. Assigning sip:craig.p@scenicrim.qld.gov.au 61754633047 3. Assigned sip:craig.p@scenicrim.qld.gov.au 61754633047 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
4. Assigning sip:darren.l@scenicrim.qld.gov.au 61754633057 4. Assigned sip:darren.l@scenicrim.qld.gov.au 61754633057 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
5. Assigning sip:charlie.w@scenicrim.qld.gov.au 61754633058 5. Assigned sip:charlie.w@scenicrim.qld.gov.au 61754633058 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
6. Assigning sip:debra.t@scenicrim.qld.gov.au 61754633060 6. Assigned sip:debra.t@scenicrim.qld.gov.au 61754633060 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
7. Assigning sip:ingrid.l@scenicrim.qld.gov.au 61754633061 7. Assigned sip:ingrid.l@scenicrim.qld.gov.au 61754633061 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
8. Assigning sip:racheal.m@scenicrim.qld.gov.au 61754633066 8. Assigned sip:racheal.m@scenicrim.qld.gov.au 61754633066 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
9. Assigning sip:jodie.ma@scenicrim.qld.gov.au 61754633084 9. Assigned sip:jodie.ma@scenicrim.qld.gov.au 61754633084 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
10. Assigning sip:lacey.s@scenicrim.qld.gov.au 61755405014 10. Assigned sip:lacey.s@scenicrim.qld.gov.au 61755405014 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
11. Assigning sip:kathy.f@scenicrim.qld.gov.au 61755405015 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Failed to acquire token with unknown exception
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : InternalServerError,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
11. # Assigning Error sip:kathy.f@scenicrim.qld.gov.au 61755405015 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
12. Assigning sip:Michael.Wo@scenicrim.qld.gov.au 61755405016 12. Assigned sip:Michael.Wo@scenicrim.qld.gov.au 61755405016 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
13. Assigning sip:Jason.G@scenicrim.qld.gov.au 61755405043 13. Assigned sip:Jason.G@scenicrim.qld.gov.au 61755405043 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
14. Assigning sip:bcc5051@scenicrim.qld.gov.au 61755405051 14. Assigned sip:bcc5051@scenicrim.qld.gov.au 61755405051 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
15. Assigning sip:lea.s@scenicrim.qld.gov.au 61755405053 15. Assigned sip:lea.s@scenicrim.qld.gov.au 61755405053 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
16. Assigning sip:irene.g@scenicrim.qld.gov.au 61755405055 16. Assigned sip:irene.g@scenicrim.qld.gov.au 61755405055 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
17. Assigning sip:Julien.P@scenicrim.qld.gov.au 61755405056 17. Assigned sip:Julien.P@scenicrim.qld.gov.au 61755405056 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
18. Assigning sip:bcc5060@scenicrim.qld.gov.au 61755405060 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user 'sip:bcc5060@scenicrim.qld.gov.au' is not found
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : NotFound,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
18. # Assigning Error sip:bcc5060@scenicrim.qld.gov.au 61755405060 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
19. Assigning sip:jairo.c@scenicrim.qld.gov.au 61755405061 19. Assigned sip:jairo.c@scenicrim.qld.gov.au 61755405061 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
20. Assigning sip:liz.r@scenicrim.qld.gov.au 61755405071 20. Assigned sip:liz.r@scenicrim.qld.gov.au 61755405071 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
21. Assigning sip:Minh-Man.N@scenicrim.qld.gov.au 61755405072 21. Assigned sip:Minh-Man.N@scenicrim.qld.gov.au 61755405072 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
22. Assigning sip:Jaime.M@scenicrim.qld.gov.au 61755405073 22. Assigned sip:Jaime.M@scenicrim.qld.gov.au 61755405073 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
23. Assigning sip:Hera.L@scenicrim.qld.gov.au 61755405074 23. Assigned sip:Hera.L@scenicrim.qld.gov.au 61755405074 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
24. Assigning sip:Lara.S@scenicrim.qld.gov.au 61755405075 24. Assigned sip:Lara.S@scenicrim.qld.gov.au 61755405075 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
25. Assigning sip:Donna.C@scenicrim.qld.gov.au 61755405076 25. Assigned sip:Donna.C@scenicrim.qld.gov.au 61755405076 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
26. Assigning sip:Clyde.P@scenicrim.qld.gov.au 61755405080 26. Assigned sip:Clyde.P@scenicrim.qld.gov.au 61755405080 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
27. Assigning sip:robyn.c@scenicrim.qld.gov.au 61755405082 27. Assigned sip:robyn.c@scenicrim.qld.gov.au 61755405082 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
28. Assigning sip:Noni.H@scenicrim.qld.gov.au 61755405093 28. Assigned sip:Noni.H@scenicrim.qld.gov.au 61755405093 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
29. Assigning sip:Lau.c@scenicrim.qld.gov.au 61755405094 29. Assigned sip:Lau.c@scenicrim.qld.gov.au 61755405094 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
30. Assigning sip:david.k@scenicrim.qld.gov.au 61755405100 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user is hosted in an on-premises deployment of Skype for Busi
ness Server. This user's number must be changed in the
on-premises environment and then synchronized to the cloud.
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
30. # Assigning Error sip:david.k@scenicrim.qld.gov.au 61755405100 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
31. Assigning sip:greg.c@scenicrim.qld.gov.au 61755405105 31. Assigned sip:greg.c@scenicrim.qld.gov.au 61755405105 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
32. Assigning sip:Luke.C@scenicrim.qld.gov.au 61755405107 32. Assigned sip:Luke.C@scenicrim.qld.gov.au 61755405107 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
33. Assigning sip:Dean.K@scenicrim.qld.gov.au 61755405114 33. Assigned sip:Dean.K@scenicrim.qld.gov.au 61755405114 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
34. Assigning sip:kylee.m@scenicrim.qld.gov.au 61755405115 34. Assigned sip:kylee.m@scenicrim.qld.gov.au 61755405115 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
35. Assigning sip:Blake.H@scenicrim.qld.gov.au 61755405117 35. Assigned sip:Blake.H@scenicrim.qld.gov.au 61755405117 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
36. Assigning sip:julia.m@scenicrim.qld.gov.au 61755405118 36. Assigned sip:julia.m@scenicrim.qld.gov.au 61755405118 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
37. Assigning sip:lyle.v@scenicrim.qld.gov.au 61755405123 37. Assigned sip:lyle.v@scenicrim.qld.gov.au 61755405123 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
38. Assigning sip:oliver.p@scenicrim.qld.gov.au 61755405125 38. Assigned sip:oliver.p@scenicrim.qld.gov.au 61755405125 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
39. Assigning sip:nicky.h@scenicrim.qld.gov.au 61755405126 39. Assigned sip:nicky.h@scenicrim.qld.gov.au 61755405126 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
40. Assigning sip:lisa.ke@scenicrim.qld.gov.au 61755405127 40. Assigned sip:lisa.ke@scenicrim.qld.gov.au 61755405127 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
41. Assigning sip:kate.jo@scenicrim.qld.gov.au 61755405129 41. Assigned sip:kate.jo@scenicrim.qld.gov.au 61755405129 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
42. Assigning sip:Laura.M@scenicrim.qld.gov.au 61755405130 42. Assigned sip:Laura.M@scenicrim.qld.gov.au 61755405130 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
43. Assigning sip:libby.m@scenicrim.qld.gov.au 61755405132 43. Assigned sip:libby.m@scenicrim.qld.gov.au 61755405132 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
44. Assigning sip:Pravin.M@scenicrim.qld.gov.au 61755405133 44. Assigned sip:Pravin.M@scenicrim.qld.gov.au 61755405133 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
45. Assigning sip:Adrian.C@scenicrim.qld.gov.au 61755405134 45. Assigned sip:Adrian.C@scenicrim.qld.gov.au 61755405134 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
46. Assigning sip:renaee.j@scenicrim.qld.gov.au 61755405135 46. Assigned sip:renaee.j@scenicrim.qld.gov.au 61755405135 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
47. Assigning sip:ross.k@scenicrim.qld.gov.au 61755405138 47. Assigned sip:ross.k@scenicrim.qld.gov.au 61755405138 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
48. Assigning sip:nikki.b@scenicrim.qld.gov.au 61755405139 48. Assigned sip:nikki.b@scenicrim.qld.gov.au 61755405139 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
49. Assigning sip:Karen.Br@scenicrim.qld.gov.au 61755405140 49. Assigned sip:Karen.Br@scenicrim.qld.gov.au 61755405140 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
50. Assigning sip:Trevor.D@scenicrim.qld.gov.au 61755405141 50. Assigned sip:Trevor.D@scenicrim.qld.gov.au 61755405141 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
51. Assigning sip:bdl5142@scenicrim.qld.gov.au 61755405142 51. Assigned sip:bdl5142@scenicrim.qld.gov.au 61755405142 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
52. Assigning sip:Genevieve.L@scenicrim.qld.gov.au 61755405143 52. Assigned sip:Genevieve.L@scenicrim.qld.gov.au 61755405143 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
53. Assigning sip:Lyndal.C@scenicrim.qld.gov.au 61755405146 53. Assigned sip:Lyndal.C@scenicrim.qld.gov.au 61755405146 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
54. Assigning sip:ann.g@scenicrim.qld.gov.au 61755405151 54. Assigned sip:ann.g@scenicrim.qld.gov.au 61755405151 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
55. Assigning sip:Julie.S@scenicrim.qld.gov.au 61755405152 55. Assigned sip:Julie.S@scenicrim.qld.gov.au 61755405152 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
56. Assigning sip:Joseph.K@scenicrim.qld.gov.au 61755405153 56. Assigned sip:Joseph.K@scenicrim.qld.gov.au 61755405153 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
57. Assigning sip:Velda.M@scenicrim.qld.gov.au 61755405156 57. Assigned sip:Velda.M@scenicrim.qld.gov.au 61755405156 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
58. Assigning sip:daadmin@scenicrim.qld.gov.au 61755405158 58. Assigned sip:daadmin@scenicrim.qld.gov.au 61755405158 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
59. Assigning sip:Shona.V@scenicrim.qld.gov.au 61755405159 59. Assigned sip:Shona.V@scenicrim.qld.gov.au 61755405159 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
60. Assigning sip:cheryl.h@scenicrim.qld.gov.au 61755405160 60. Assigned sip:cheryl.h@scenicrim.qld.gov.au 61755405160 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
61. Assigning sip:Hazel.M@scenicrim.qld.gov.au 61755405162 61. Assigned sip:Hazel.M@scenicrim.qld.gov.au 61755405162 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
62. Assigning sip:Carleen.O@scenicrim.qld.gov.au 61755405163 62. Assigned sip:Carleen.O@scenicrim.qld.gov.au 61755405163 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
63. Assigning sip:jeff.b@scenicrim.qld.gov.au 61755405164 63. Assigned sip:jeff.b@scenicrim.qld.gov.au 61755405164 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
64. Assigning sip:bridget.p@scenicrim.qld.gov.au 61755405166 64. Assigned sip:bridget.p@scenicrim.qld.gov.au 61755405166 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
65. Assigning sip:melissa.m@scenicrim.qld.gov.au 61755405168 65. Assigned sip:melissa.m@scenicrim.qld.gov.au 61755405168 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
66. Assigning sip:matthew.c@scenicrim.qld.gov.au 61755405169 66. Assigned sip:matthew.c@scenicrim.qld.gov.au 61755405169 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
67. Assigning sip:Joel.S@scenicrim.qld.gov.au 61755405171 67. Assigned sip:Joel.S@scenicrim.qld.gov.au 61755405171 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
68. Assigning sip:emma.th@scenicrim.qld.gov.au 61755405172 68. Assigned sip:emma.th@scenicrim.qld.gov.au 61755405172 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
69. Assigning sip:brad.f@scenicrim.qld.gov.au 61755405173 69. Assigned sip:brad.f@scenicrim.qld.gov.au 61755405173 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
70. Assigning sip:Raj.K@scenicrim.qld.gov.au 61755405176 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user is hosted in an on-premises deployment of Skype for Busine
ss Server. This user's number must be changed in the
on-premises environment and then synchronized to the cloud.
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
70. # Assigning Error sip:Raj.K@scenicrim.qld.gov.au 61755405176 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
71. Assigning sip:shaun.a@scenicrim.qld.gov.au 61755405177 71. Assigned sip:shaun.a@scenicrim.qld.gov.au 61755405177 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
72. Assigning sip:megan.g@scenicrim.qld.gov.au 61755405179 72. Assigned sip:megan.g@scenicrim.qld.gov.au 61755405179 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
73. Assigning sip:Melissa.R@scenicrim.qld.gov.au 61755405180 73. Assigned sip:Melissa.R@scenicrim.qld.gov.au 61755405180 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
74. Assigning sip:melissa.me@scenicrim.qld.gov.au 61755405182 74. Assigned sip:melissa.me@scenicrim.qld.gov.au 61755405182 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
75. Assigning sip:rick.h@scenicrim.qld.gov.au 61755405184 75. Assigned sip:rick.h@scenicrim.qld.gov.au 61755405184 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
76. Assigning sip:vili.m@scenicrim.qld.gov.au 61755405185 76. Assigned sip:vili.m@scenicrim.qld.gov.au 61755405185 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
77. Assigning sip:greg.h@scenicrim.qld.gov.au 61755405186 77. Assigned sip:greg.h@scenicrim.qld.gov.au 61755405186 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
78. Assigning sip:terry.r@scenicrim.qld.gov.au 61755405187 78. Assigned sip:terry.r@scenicrim.qld.gov.au 61755405187 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
79. Assigning sip:brian.a@scenicrim.qld.gov.au 61755405188 79. Assigned sip:brian.a@scenicrim.qld.gov.au 61755405188 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
80. Assigning sip:graham.a@scenicrim.qld.gov.au 61755405190 80. Assigned sip:graham.a@scenicrim.qld.gov.au 61755405190 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
81. Assigning sip:david.r@scenicrim.qld.gov.au 61755405191 81. Assigned sip:david.r@scenicrim.qld.gov.au 61755405191 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
82. Assigning sip:john.ke@scenicrim.qld.gov.au 61755405193 82. Assigned sip:john.ke@scenicrim.qld.gov.au 61755405193 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
83. Assigning sip:margie.j@scenicrim.qld.gov.au 61755405196 83. Assigned sip:margie.j@scenicrim.qld.gov.au 61755405196 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
84. Assigning sip:gavin.g@scenicrim.qld.gov.au 61755405198 84. Assigned sip:gavin.g@scenicrim.qld.gov.au 61755405198 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
85. Assigning sip:annmarie.w@scenicrim.qld.gov.au 61755405199 85. Assigned sip:annmarie.w@scenicrim.qld.gov.au 61755405199 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
86. Assigning sip:Monica.M@scenicrim.qld.gov.au 61755405202 86. Assigned sip:Monica.M@scenicrim.qld.gov.au 61755405202 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
87. Assigning sip:Chloe.E@scenicrim.qld.gov.au 61755405204 87. Assigned sip:Chloe.E@scenicrim.qld.gov.au 61755405204 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
88. Assigning sip:heather.n@scenicrim.qld.gov.au 61755405205 88. Assigned sip:heather.n@scenicrim.qld.gov.au 61755405205 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
89. Assigning sip:Holly.H@scenicrim.qld.gov.au 61755405206 89. Assigned sip:Holly.H@scenicrim.qld.gov.au 61755405206 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
90. Assigning sip:andrew.s@scenicrim.qld.gov.au 61755405209 90. Assigned sip:andrew.s@scenicrim.qld.gov.au 61755405209 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
91. Assigning sip:Natika.D@scenicrim.qld.gov.au 61755405213 91. Assigned sip:Natika.D@scenicrim.qld.gov.au 61755405213 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
92. Assigning sip:Ray.K@scenicrim.qld.gov.au 61755405216 92. Assigned sip:Ray.K@scenicrim.qld.gov.au 61755405216 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
93. Assigning sip:lynne.b@scenicrim.qld.gov.au 61755405218 93. Assigned sip:lynne.b@scenicrim.qld.gov.au 61755405218 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
94. Assigning sip:Jennifer.St@scenicrim.qld.gov.au 61755405219 94. Assigned sip:Jennifer.St@scenicrim.qld.gov.au 61755405219 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
95. Assigning sip:melissa.q@scenicrim.qld.gov.au 61755405220 95. Assigned sip:melissa.q@scenicrim.qld.gov.au 61755405220 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
96. Assigning sip:scott.ob@scenicrim.qld.gov.au 61755405223 96. Assigned sip:scott.ob@scenicrim.qld.gov.au 61755405223 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
97. Assigning sip:Lana.L@scenicrim.qld.gov.au 61755405224 97. Assigned sip:Lana.L@scenicrim.qld.gov.au 61755405224 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
98. Assigning sip:Susan.P@scenicrim.qld.gov.au 61755405225 98. Assigned sip:Susan.P@scenicrim.qld.gov.au 61755405225 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
99. Assigning sip:polly.w@scenicrim.qld.gov.au 61755405226 99. Assigned sip:polly.w@scenicrim.qld.gov.au 61755405226 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
100. Assigning sip:carmel.d@scenicrim.qld.gov.au 61755405229 100. Assigned sip:carmel.d@scenicrim.qld.gov.au 61755405229 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
101. Assigning sip:Matthew.F@scenicrim.qld.gov.au 61755405231 101. Assigned sip:Matthew.F@scenicrim.qld.gov.au 61755405231 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
102. Assigning sip:Alana.B@scenicrim.qld.gov.au 61755405233 102. Assigned sip:Alana.B@scenicrim.qld.gov.au 61755405233 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
103. Assigning sip:Tara.M@scenicrim.qld.gov.au 61755405234 103. Assigned sip:Tara.M@scenicrim.qld.gov.au 61755405234 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
104. Assigning sip:jeremy.p@scenicrim.qld.gov.au 61755405235 104. Assigned sip:jeremy.p@scenicrim.qld.gov.au 61755405235 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
105. Assigning sip:Carolyn.G@scenicrim.qld.gov.au 61755405236 105. Assigned sip:Carolyn.G@scenicrim.qld.gov.au 61755405236 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
106. Assigning sip:peter.b@scenicrim.qld.gov.au 61755405238 106. Assigned sip:peter.b@scenicrim.qld.gov.au 61755405238 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
107. Assigning sip:tia.b@scenicrim.qld.gov.au 61755405239 107. Assigned sip:tia.b@scenicrim.qld.gov.au 61755405239 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
108. Assigning sip:mark.l@scenicrim.qld.gov.au 61755405241 108. Assigned sip:mark.l@scenicrim.qld.gov.au 61755405241 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
109. Assigning sip:chantal.b@scenicrim.qld.gov.au 61755405243 109. Assigned sip:chantal.b@scenicrim.qld.gov.au 61755405243 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
110. Assigning sip:Jodi.W@scenicrim.qld.gov.au 61755405245 110. Assigned sip:Jodi.W@scenicrim.qld.gov.au 61755405245 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
111. Assigning sip:colin.m@scenicrim.qld.gov.au 61755405246 111. Assigned sip:colin.m@scenicrim.qld.gov.au 61755405246 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
112. Assigning sip:kylie.a@scenicrim.qld.gov.au 61755405247 112. Assigned sip:kylie.a@scenicrim.qld.gov.au 61755405247 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
113. Assigning sip:Pedro.P@scenicrim.qld.gov.au 61755405249 113. Assigned sip:Pedro.P@scenicrim.qld.gov.au 61755405249 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
114. Assigning sip:susan.w@scenicrim.qld.gov.au 61755405251 114. Assigned sip:susan.w@scenicrim.qld.gov.au 61755405251 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
115. Assigning sip:Judy.J@scenicrim.qld.gov.au 61755405252 115. Assigned sip:Judy.J@scenicrim.qld.gov.au 61755405252 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
116. Assigning sip:liam.c@scenicrim.qld.gov.au 61755405253 116. Assigned sip:liam.c@scenicrim.qld.gov.au 61755405253 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
117. Assigning sip:cindy.w@scenicrim.qld.gov.au 61755405254 117. Assigned sip:cindy.w@scenicrim.qld.gov.au 61755405254 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
118. Assigning sip:debra.h@scenicrim.qld.gov.au 61755405255 118. Assigned sip:debra.h@scenicrim.qld.gov.au 61755405255 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
119. Assigning sip:Leanne.S@scenicrim.qld.gov.au 61755405256 119. Assigned sip:Leanne.S@scenicrim.qld.gov.au 61755405256 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
120. Assigning sip:Melanie.B@scenicrim.qld.gov.au 61755405257 120. Assigned sip:Melanie.B@scenicrim.qld.gov.au 61755405257 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
121. Assigning sip:Miranda.C@scenicrim.qld.gov.au 61755405259 121. Assigned sip:Miranda.C@scenicrim.qld.gov.au 61755405259 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
122. Assigning sip:clare.n@scenicrim.qld.gov.au 61755405261 122. Assigned sip:clare.n@scenicrim.qld.gov.au 61755405261 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
123. Assigning sip:justin.a@scenicrim.qld.gov.au 61755405262 123. Assigned sip:justin.a@scenicrim.qld.gov.au 61755405262 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
124. Assigning sip:kelli.r@scenicrim.qld.gov.au 61755405263 124. Assigned sip:kelli.r@scenicrim.qld.gov.au 61755405263 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
125. Assigning sip:Narendra.s@scenicrim.qld.gov.au 61755405264 125. Assigned sip:Narendra.s@scenicrim.qld.gov.au 61755405264 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
126. Assigning sip:peter.k@scenicrim.qld.gov.au 61755405265 126. Assigned sip:peter.k@scenicrim.qld.gov.au 61755405265 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
127. Assigning sip:richard.s@scenicrim.qld.gov.au 61755405266 127. Assigned sip:richard.s@scenicrim.qld.gov.au 61755405266 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
128. Assigning sip:Shantel.T@scenicrim.qld.gov.au 61755405267 128. Assigned sip:Shantel.T@scenicrim.qld.gov.au 61755405267 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
129. Assigning sip:zane.b@scenicrim.qld.gov.au 61755405268 129. Assigned sip:zane.b@scenicrim.qld.gov.au 61755405268 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
130. Assigning sip:Jason.Y@scenicrim.qld.gov.au 61755405270 130. Assigned sip:Jason.Y@scenicrim.qld.gov.au 61755405270 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
131. Assigning sip:Gail.K@scenicrim.qld.gov.au 61755405271 131. Assigned sip:Gail.K@scenicrim.qld.gov.au 61755405271 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
132. Assigning sip:Jasmine.S@scenicrim.qld.gov.au 61755405272 132. Assigned sip:Jasmine.S@scenicrim.qld.gov.au 61755405272 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
133. Assigning sip:Jason.Ca@scenicrim.qld.gov.au 61755405273 133. Assigned sip:Jason.Ca@scenicrim.qld.gov.au 61755405273 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
134. Assigning sip:Amy.R@scenicrim.qld.gov.au 61755405274 134. Assigned sip:Amy.R@scenicrim.qld.gov.au 61755405274 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
135. Assigning sip:elva.s@scenicrim.qld.gov.au 61755405276 135. Assigned sip:elva.s@scenicrim.qld.gov.au 61755405276 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
136. Assigning sip:kevin.d@scenicrim.qld.gov.au 61755405277 136. Assigned sip:kevin.d@scenicrim.qld.gov.au 61755405277 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
137. Assigning sip:mark.st@scenicrim.qld.gov.au 61755405278 137. Assigned sip:mark.st@scenicrim.qld.gov.au 61755405278 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
138. Assigning sip:scott.w@scenicrim.qld.gov.au 61755405279 138. Assigned sip:scott.w@scenicrim.qld.gov.au 61755405279 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
139. Assigning sip:carmen.h@scenicrim.qld.gov.au 61755405281 139. Assigned sip:carmen.h@scenicrim.qld.gov.au 61755405281 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
140. Assigning sip:justin.s@scenicrim.qld.gov.au 61755405282 140. Assigned sip:justin.s@scenicrim.qld.gov.au 61755405282 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
141. Assigning sip:john.p@scenicrim.qld.gov.au 61755405283 141. Assigned sip:john.p@scenicrim.qld.gov.au 61755405283 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
142. Assigning sip:sharyn.k@scenicrim.qld.gov.au 61755405284 142. Assigned sip:sharyn.k@scenicrim.qld.gov.au 61755405284 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
143. Assigning sip:gayanne.k@scenicrim.qld.gov.au 61755405288 143. Assigned sip:gayanne.k@scenicrim.qld.gov.au 61755405288 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
144. Assigning sip:Catherine.M@scenicrim.qld.gov.au 61755405289 144. Assigned sip:Catherine.M@scenicrim.qld.gov.au 61755405289 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locat
ionSchema
145. Assigning sip:andrew.cu@scenicrim.qld.gov.au 61755405290 145. Assigned sip:andrew.cu@scenicrim.qld.gov.au 61755405290 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
146. Assigning sip:Kym.L@scenicrim.qld.gov.au 61755405293 146. Assigned sip:Kym.L@scenicrim.qld.gov.au 61755405293 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
147. Assigning sip:patricia.r@scenicrim.qld.gov.au 61755405294 147. Assigned sip:patricia.r@scenicrim.qld.gov.au 61755405294 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
148. Assigning sip:Anastasia.R@scenicrim.qld.gov.au 61755405295 148. Assigned sip:Anastasia.R@scenicrim.qld.gov.au 61755405295 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locat
ionSchema
149. Assigning sip:luke.v@scenicrim.qld.gov.au 61755405296 149. Assigned sip:luke.v@scenicrim.qld.gov.au 61755405296 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
150. Assigning sip:india.b@scenicrim.qld.gov.au 61755405298 150. Assigned sip:india.b@scenicrim.qld.gov.au 61755405298 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
151. Assigning sip:Amie.P@scenicrim.qld.gov.au 61755405299 151. Assigned sip:Amie.P@scenicrim.qld.gov.au 61755405299 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
152. Assigning sip:noel.t@scenicrim.qld.gov.au 61755405301 152. Assigned sip:noel.t@scenicrim.qld.gov.au 61755405301 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
153. Assigning sip:CRP5302@scenicrim.qld.gov.au 61755405302 Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user 'sip:CRP5302@scenicrim.qld.gov.au' is not found
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : NotFound,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
153. # Assigning Error sip:CRP5302@scenicrim.qld.gov.au 61755405302 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
154. Assigning sip:linda.r@scenicrim.qld.gov.au 61755405303 154. Assigned sip:linda.r@scenicrim.qld.gov.au 61755405303 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
155. Assigning sip:dee.c@scenicrim.qld.gov.au 61755405308 155. Assigned sip:dee.c@scenicrim.qld.gov.au 61755405308 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
156. Assigning sip:Ellie.B@scenicrim.qld.gov.au 61755405309 156. Assigned sip:Ellie.B@scenicrim.qld.gov.au 61755405309 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
157. Assigning sip:Santosh.KC@scenicrim.qld.gov.au 61755405310 157. Assigned sip:Santosh.KC@scenicrim.qld.gov.au 61755405310 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
158. Assigning sip:Belinda.J@scenicrim.qld.gov.au 61755405313 158. Assigned sip:Belinda.J@scenicrim.qld.gov.au 61755405313 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
159. Assigning sip:kelmeny.f@scenicrim.qld.gov.au 61755405315 159. Assigned sip:kelmeny.f@scenicrim.qld.gov.au 61755405315 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
160. Assigning sip:erin.p@scenicrim.qld.gov.au 61755405316 160. Assigned sip:erin.p@scenicrim.qld.gov.au 61755405316 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
161. Assigning sip:Deanna.F@scenicrim.qld.gov.au 61755405317 161. Assigned sip:Deanna.F@scenicrim.qld.gov.au 61755405317 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
162. Assigning sip:rebecca.d@scenicrim.qld.gov.au 61755405318 162. Assigned sip:rebecca.d@scenicrim.qld.gov.au 61755405318 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
163. Assigning sip:billie.p@scenicrim.qld.gov.au 61755405319 163. Assigned sip:billie.p@scenicrim.qld.gov.au 61755405319 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
164. Assigning sip:Andrew.Ma@scenicrim.qld.gov.au 61755405320 164. Assigned sip:Andrew.Ma@scenicrim.qld.gov.au 61755405320 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
165. Assigning sip:marie.s@scenicrim.qld.gov.au 61755405321 165. Assigned sip:marie.s@scenicrim.qld.gov.au 61755405321 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
166. Assigning sip:mark.d@scenicrim.qld.gov.au 61755405327 166. Assigned sip:mark.d@scenicrim.qld.gov.au 61755405327 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
167. Assigning sip:andrew.h@scenicrim.qld.gov.au 61755405328 167. Assigned sip:andrew.h@scenicrim.qld.gov.au 61755405328 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
168. Assigning sip:amanda.l@scenicrim.qld.gov.au 61755405329 168. Assigned sip:amanda.l@scenicrim.qld.gov.au 61755405329 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
169. Assigning sip:drift.i@scenicrim.qld.gov.au 61755405330 169. Assigned sip:drift.i@scenicrim.qld.gov.au 61755405330 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
170. Assigning sip:daniel.mc@scenicrim.qld.gov.au 61755405331 170. Assigned sip:daniel.mc@scenicrim.qld.gov.au 61755405331 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
171. Assigning sip:Kuda.P@scenicrim.qld.gov.au 61755405332 171. Assigned sip:Kuda.P@scenicrim.qld.gov.au 61755405332 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
172. Assigning sip:jon.r@scenicrim.qld.gov.au 61755405336 172. Assigned sip:jon.r@scenicrim.qld.gov.au 61755405336 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
173. Assigning sip:insync@scenicrim.qld.gov.au 61755405337 173. Assigned sip:insync@scenicrim.qld.gov.au 61755405337 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
174. Assigning sip:joanne.d@scenicrim.qld.gov.au 61755405342 174. Assigned sip:joanne.d@scenicrim.qld.gov.au 61755405342 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
175. Assigning sip:Leah.S@scenicrim.qld.gov.au 61755405343 175. Assigned sip:Leah.S@scenicrim.qld.gov.au 61755405343 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
176. Assigning sip:Nada.M@scenicrim.qld.gov.au 61755405344 176. Assigned sip:Nada.M@scenicrim.qld.gov.au 61755405344 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
177. Assigning sip:jared.k@scenicrim.qld.gov.au 61755405345 177. Assigned sip:jared.k@scenicrim.qld.gov.au 61755405345 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
178. Assigning sip:jordan.t@scenicrim.qld.gov.au 61755405346 178. Assigned sip:jordan.t@scenicrim.qld.gov.au 61755405346 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
179. Assigning sip:frank.a@scenicrim.qld.gov.au 61755405347 179. Assigned sip:frank.a@scenicrim.qld.gov.au 61755405347 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
180. Assigning sip:donna.r@scenicrim.qld.gov.au 61755405348 180. Assigned sip:donna.r@scenicrim.qld.gov.au 61755405348 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
181. Assigning sip:Simon.H@scenicrim.qld.gov.au 61755405349 181. Assigned sip:Simon.H@scenicrim.qld.gov.au 61755405349 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
182. Assigning sip:adam.j@scenicrim.qld.gov.au 61755405350 182. Assigned sip:adam.j@scenicrim.qld.gov.au 61755405350 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
183. Assigning sip:mark.pa@scenicrim.qld.gov.au 61755405351 183. Assigned sip:mark.pa@scenicrim.qld.gov.au 61755405351 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
184. Assigning sip:katrina.r@scenicrim.qld.gov.au 61755405358 184. Assigned sip:katrina.r@scenicrim.qld.gov.au 61755405358 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
185. Assigning sip:shane.r@scenicrim.qld.gov.au 61755405359 185. Assigned sip:shane.r@scenicrim.qld.gov.au 61755405359 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
186. Assigning sip:jodie.m@scenicrim.qld.gov.au 61755405360 186. Assigned sip:jodie.m@scenicrim.qld.gov.au 61755405360 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
187. Assigning sip:Maverick.w@scenicrim.qld.gov.au 61755405361 187. Assigned sip:Maverick.w@scenicrim.qld.gov.au 61755405361 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
188. Assigning sip:shane.m@scenicrim.qld.gov.au 61755405362 188. Assigned sip:shane.m@scenicrim.qld.gov.au 61755405362 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
189. Assigning sip:Jamie.B@scenicrim.qld.gov.au 61755405368 189. Assigned sip:Jamie.B@scenicrim.qld.gov.au 61755405368 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
190. Assigning sip:Jessica.D@scenicrim.qld.gov.au 61755405370 190. Assigned sip:Jessica.D@scenicrim.qld.gov.au 61755405370 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
191. Assigning sip:sylvia.s@scenicrim.qld.gov.au 61755405372 191. Assigned sip:sylvia.s@scenicrim.qld.gov.au 61755405372 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
192. Assigning sip:Sarah.T@scenicrim.qld.gov.au 61755405376 192. Assigned sip:Sarah.T@scenicrim.qld.gov.au 61755405376 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
193. Assigning sip:dean.w@scenicrim.qld.gov.au 61755405377 193. Assigned sip:dean.w@scenicrim.qld.gov.au 61755405377 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
194. Assigning sip:Kobi.L@scenicrim.qld.gov.au 61755405380 194. Assigned sip:Kobi.L@scenicrim.qld.gov.au 61755405380 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
195. Assigning sip:Wayne.ma@scenicrim.qld.gov.au 61755405388 195. Assigned sip:Wayne.ma@scenicrim.qld.gov.au 61755405388 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
196. Assigning sip:Ben.O@scenicrim.qld.gov.au 61755405392 196. Assigned sip:Ben.O@scenicrim.qld.gov.au 61755405392 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
197. Assigning sip:Kirby.M@scenicrim.qld.gov.au 61755405394 197. Assigned sip:Kirby.M@scenicrim.qld.gov.au 61755405394 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
198. Assigning sip:Robyn.F@scenicrim.qld.gov.au 61755405396 198. Assigned sip:Robyn.F@scenicrim.qld.gov.au 61755405396 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
199. Assigning sip:jenna.t@scenicrim.qld.gov.au 61755405398 199. Assigned sip:jenna.t@scenicrim.qld.gov.au 61755405398 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
200. Assigning sip:christy.s@scenicrim.qld.gov.au 61755405399 200. Assigned sip:christy.s@scenicrim.qld.gov.au 61755405399 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
201. Assigning sip:amanda.h@scenicrim.qld.gov.au 61755405401 201. Assigned sip:amanda.h@scenicrim.qld.gov.au 61755405401 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
202. Assigning sip:jeff.m@scenicrim.qld.gov.au 61755405402 202. Assigned sip:jeff.m@scenicrim.qld.gov.au 61755405402 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
203. Assigning sip:virginia.w@scenicrim.qld.gov.au 61755405403 203. Assigned sip:virginia.w@scenicrim.qld.gov.au 61755405403 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
204. Assigning sip:michael.e@scenicrim.qld.gov.au 61755405404 204. Assigned sip:michael.e@scenicrim.qld.gov.au 61755405404 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
205. Assigning sip:marshall.c@scenicrim.qld.gov.au 61755405405 205. Assigned sip:marshall.c@scenicrim.qld.gov.au 61755405405 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
206. Assigning sip:duncan.m@scenicrim.qld.gov.au 61755405406 206. Assigned sip:duncan.m@scenicrim.qld.gov.au 61755405406 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
207. Assigning sip:Brittany.H@scenicrim.qld.gov.au 61755405410 207. Assigned sip:Brittany.H@scenicrim.qld.gov.au 61755405410 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
208. Assigning sip:Tara.W@scenicrim.qld.gov.au 61755405418 208. Assigned sip:Tara.W@scenicrim.qld.gov.au 61755405418 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
209. Assigning sip:mark.c@scenicrim.qld.gov.au 61755405419 209. Assigned sip:mark.c@scenicrim.qld.gov.au 61755405419 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
210. Assigning sip:craig.h@scenicrim.qld.gov.au 61755405420 210. Assigned sip:craig.h@scenicrim.qld.gov.au 61755405420 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
211. Assigning sip:Sarah.F@scenicrim.qld.gov.au 61755405421 211. Assigned sip:Sarah.F@scenicrim.qld.gov.au 61755405421 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
212. Assigning sip:Shaun.C@scenicrim.qld.gov.au 61755405422 212. Assigned sip:Shaun.C@scenicrim.qld.gov.au 61755405422 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
213. Assigning sip:anthony.m@scenicrim.qld.gov.au 61755405423 213. Assigned sip:anthony.m@scenicrim.qld.gov.au 61755405423 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
214. Assigning sip:MR3D@scenicrim.qld.gov.au 61755405424 214. Assigned sip:MR3D@scenicrim.qld.gov.au 61755405424 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
215. Assigning sip:Jo.J@scenicrim.qld.gov.au 61755405425 215. Assigned sip:Jo.J@scenicrim.qld.gov.au 61755405425 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
216. Assigning sip:Grace.R@scenicrim.qld.gov.au 61755405426 216. Assigned sip:Grace.R@scenicrim.qld.gov.au 61755405426 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
217. Assigning sip:john.m@scenicrim.qld.gov.au 61755405427 217. Assigned sip:john.m@scenicrim.qld.gov.au 61755405427 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
218. Assigning sip:Kate.C@scenicrim.qld.gov.au 61755405428 218. Assigned sip:Kate.C@scenicrim.qld.gov.au 61755405428 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
219. Assigning sip:Shane.G@scenicrim.qld.gov.au 61755405429 219. Assigned sip:Shane.G@scenicrim.qld.gov.au 61755405429 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
220. Assigning sip:luchia.w@scenicrim.qld.gov.au 61755405430 220. Assigned sip:luchia.w@scenicrim.qld.gov.au 61755405430 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
221. Assigning sip:phil.d@scenicrim.qld.gov.au 61755405431 221. Assigned sip:phil.d@scenicrim.qld.gov.au 61755405431 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
222. Assigning sip:Allen.N@scenicrim.qld.gov.au 61755405432 222. Assigned sip:Allen.N@scenicrim.qld.gov.au 61755405432 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
223. Assigning sip:cassandra.n@scenicrim.qld.gov.au 61755405434 223. Assigned sip:cassandra.n@scenicrim.qld.gov.au 61755405434 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locat
ionSchema
224. Assigning sip:miriam.n@scenicrim.qld.gov.au 61755405436 224. Assigned sip:miriam.n@scenicrim.qld.gov.au 61755405436 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
225. Assigning sip:stephen.m@scenicrim.qld.gov.au 61755405438 225. Assigned sip:stephen.m@scenicrim.qld.gov.au 61755405438 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
226. Assigning sip:scott.o@scenicrim.qld.gov.au 61755405439 226. Assigned sip:scott.o@scenicrim.qld.gov.au 61755405439 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
227. Assigning sip:linda.k@scenicrim.qld.gov.au 61755405441 227. Assigned sip:linda.k@scenicrim.qld.gov.au 61755405441 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
228. Assigning sip:leisa.f@scenicrim.qld.gov.au 61755405448 228. Assigned sip:leisa.f@scenicrim.qld.gov.au 61755405448 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
229. Assigning sip:jodie.v@scenicrim.qld.gov.au 61755405452 229. Assigned sip:jodie.v@scenicrim.qld.gov.au 61755405452 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
230. Assigning sip:steve.a@scenicrim.qld.gov.au 61755405453 230. Assigned sip:steve.a@scenicrim.qld.gov.au 61755405453 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
231. Assigning sip:paula.l@scenicrim.qld.gov.au 61755405455 231. Assigned sip:paula.l@scenicrim.qld.gov.au 61755405455 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
232. Assigning sip:justin.st@scenicrim.qld.gov.au 61755405456 232. Assigned sip:justin.st@scenicrim.qld.gov.au 61755405456 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
233. Assigning sip:Helen.R@scenicrim.qld.gov.au 61755405458 233. Assigned sip:Helen.R@scenicrim.qld.gov.au 61755405458 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
234. Assigning sip:Brett.F@scenicrim.qld.gov.au 61755405459 234. Assigned sip:Brett.F@scenicrim.qld.gov.au 61755405459 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
235. Assigning sip:warren.n@scenicrim.qld.gov.au 61755405469 235. Assigned sip:warren.n@scenicrim.qld.gov.au 61755405469 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
236. Assigning sip:raylene.j@scenicrim.qld.gov.au 61755405472 236. Assigned sip:raylene.j@scenicrim.qld.gov.au 61755405472 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
237. Assigning sip:tmfd5473@scenicrim.qld.gov.au 61755405473 237. Assigned sip:tmfd5473@scenicrim.qld.gov.au 61755405473 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
238. Assigning sip:cameron.t@scenicrim.qld.gov.au 61755405474 238. Assigned sip:cameron.t@scenicrim.qld.gov.au 61755405474 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
239. Assigning sip:Matthew.B@scenicrim.qld.gov.au 61755405475 239. Assigned sip:Matthew.B@scenicrim.qld.gov.au 61755405475 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
240. Assigning sip:Taylor.K@scenicrim.qld.gov.au 61755405477 240. Assigned sip:Taylor.K@scenicrim.qld.gov.au 61755405477 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
241. Assigning sip:Jo-Ann.A@scenicrim.qld.gov.au 61755405478 241. Assigned sip:Jo-Ann.A@scenicrim.qld.gov.au 61755405478 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
242. Assigning sip:tegan.s@scenicrim.qld.gov.au 61755405481 242. Assigned sip:tegan.s@scenicrim.qld.gov.au 61755405481 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
243. Assigning sip:jason.t@scenicrim.qld.gov.au 61755405483 243. Assigned sip:jason.t@scenicrim.qld.gov.au 61755405483 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
244. Assigning sip:kyle.r@scenicrim.qld.gov.au 61755405485 244. Assigned sip:kyle.r@scenicrim.qld.gov.au 61755405485 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
245. Assigning sip:daniel.sm@scenicrim.qld.gov.au 61755405486 245. Assigned sip:daniel.sm@scenicrim.qld.gov.au 61755405486 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
246. Assigning sip:nick.p@scenicrim.qld.gov.au 61755405487 246. Assigned sip:nick.p@scenicrim.qld.gov.au 61755405487 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
247. Assigning sip:craig.he@scenicrim.qld.gov.au 61755405489 247. Assigned sip:craig.he@scenicrim.qld.gov.au 61755405489 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
248. Assigning sip:marisa.p@scenicrim.qld.gov.au 61755405493 248. Assigned sip:marisa.p@scenicrim.qld.gov.au 61755405493 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
249. Assigning sip:Christopher.G@scenicrim.qld.gov.au 61755405494 249. Assigned sip:Christopher.G@scenicrim.qld.gov.au 61755405494 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.L
ocationSchema
250. Assigning sip:Rayhan.S@scenicrim.qld.gov.au 61755405496 250. Assigned sip:Rayhan.S@scenicrim.qld.gov.au 61755405496 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
251. Assigning sip:Timothy.S@scenicrim.qld.gov.au 61755405498 251. Assigned sip:Timothy.S@scenicrim.qld.gov.au 61755405498 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
252. Assigning sip:Allyson.H@scenicrim.qld.gov.au 61755405499 252. Assigned sip:Allyson.H@scenicrim.qld.gov.au 61755405499 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
253. Assigning sip:info_moogerah@scenicrim.qld.gov.au 61755405600 253. Assigned sip:info_moogerah@scenicrim.qld.gov.au 61755405600 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.L
ocationSchema
254. Assigning sip:bronwyn.c@scenicrim.qld.gov.au 61755405601 254. Assigned sip:bronwyn.c@scenicrim.qld.gov.au 61755405601 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
255. Assigning sip:Heerah.K@scenicrim.qld.gov.au 61755405602 255. Assigned sip:Heerah.K@scenicrim.qld.gov.au 61755405602 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
256. Assigning sip:Katrina.C@scenicrim.qld.gov.au 61755405603 256. Assigned sip:Katrina.C@scenicrim.qld.gov.au 61755405603 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
257. Assigning sip:alisa.t@scenicrim.qld.gov.au 61755405604 257. Assigned sip:alisa.t@scenicrim.qld.gov.au 61755405604 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
258. Assigning sip:Blake.B@scenicrim.qld.gov.au 61755405605 258. Assigned sip:Blake.B@scenicrim.qld.gov.au 61755405605 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
259. Assigning sip:Deeanne.T@scenicrim.qld.gov.au 61755405606 259. Assigned sip:Deeanne.T@scenicrim.qld.gov.au 61755405606 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
260. Assigning sip:robyn.r@scenicrim.qld.gov.au 61755405607 260. Assigned sip:robyn.r@scenicrim.qld.gov.au 61755405607 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
261. Assigning sip:donnalee.o@scenicrim.qld.gov.au 61755405608 261. Assigned sip:donnalee.o@scenicrim.qld.gov.au 61755405608 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
262. Assigning sip:Rebecca.f@scenicrim.qld.gov.au 61755405609 262. Assigned sip:Rebecca.f@scenicrim.qld.gov.au 61755405609 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
263. Assigning sip:adam.ma@scenicrim.qld.gov.au 61755405610 263. Assigned sip:adam.ma@scenicrim.qld.gov.au 61755405610 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
264. Assigning sip:Marnie.Y@scenicrim.qld.gov.au 61755405611 264. Assigned sip:Marnie.Y@scenicrim.qld.gov.au 61755405611 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
265. Assigning sip:Luke.A@scenicrim.qld.gov.au 61755405612 265. Assigned sip:Luke.A@scenicrim.qld.gov.au 61755405612 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
266. Assigning sip:hr@scenicrim.qld.gov.au 61755405613 266. Assigned sip:hr@scenicrim.qld.gov.au 61755405613 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
267. Assigning sip:adrienne.j@scenicrim.qld.gov.au 61755405614 267. Assigned sip:adrienne.j@scenicrim.qld.gov.au 61755405614 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
268. Assigning sip:leanne.bu@scenicrim.qld.gov.au 61755405617 268. Assigned sip:leanne.bu@scenicrim.qld.gov.au 61755405617 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationS
chema
269. Assigning sip:Jacob.O@scenicrim.qld.gov.au 61755405622 269. Assigned sip:Jacob.O@scenicrim.qld.gov.au 61755405622 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
270. Assigning sip:rylie.a@scenicrim.qld.gov.au 61755405623 270. Assigned sip:rylie.a@scenicrim.qld.gov.au 61755405623 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
271. Assigning sip:brad.w@scenicrim.qld.gov.au 61755405625 271. Assigned sip:brad.w@scenicrim.qld.gov.au 61755405625 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
272. Assigning sip:John.L@scenicrim.qld.gov.au 61755405627 272. Assigned sip:John.L@scenicrim.qld.gov.au 61755405627 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
273. Assigning sip:damian.t@scenicrim.qld.gov.au 61755405628 273. Assigned sip:damian.t@scenicrim.qld.gov.au 61755405628 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
274. Assigning sip:tony.s@scenicrim.qld.gov.au 61755405629 274. Assigned sip:tony.s@scenicrim.qld.gov.au 61755405629 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
275. Assigning sip:mark.lu@scenicrim.qld.gov.au 61755405630 275. Assigned sip:mark.lu@scenicrim.qld.gov.au 61755405630 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchem
a
276. Assigning sip:Joanne.M@scenicrim.qld.gov.au 61755405631 276. Assigned sip:Joanne.M@scenicrim.qld.gov.au 61755405631 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
277. Assigning sip:lauren.b@scenicrim.qld.gov.au 61755405632 277. Assigned sip:lauren.b@scenicrim.qld.gov.au 61755405632 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSch
ema
278. Assigning sip:ldccroommanager@scenicrim.qld.gov.au 61755405633 278. Assigned sip:ldccroommanager@scenicrim.qld.gov.au 61755405633 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Mode
ls.LocationSchema
279. Assigning sip:vivienne.m@scenicrim.qld.gov.au 61755405634 279. Assigned sip:vivienne.m@scenicrim.qld.gov.au 61755405634 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.Locatio
nSchema
280. Assigning sip:sarah.b@scenicrim.qld.gov.au 61755405635 280. Assigned sip:sarah.b@scenicrim.qld.gov.au 61755405635 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
281. Assigning sip:jason.h@scenicrim.qld.gov.au 61755405639 281. Assigned sip:jason.h@scenicrim.qld.gov.au 61755405639 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
282. Assigning sip:danni.m@scenicrim.qld.gov.au 61755405641 282. Assigned sip:danni.m@scenicrim.qld.gov.au 61755405641 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
283. Assigning sip:james.do@scenicrim.qld.gov.au 61755405643 283. Assigned sip:james.do@scenicrim.qld.gov.au 61755405643 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
284. Assigning sip:timothy.b@scenicrim.qld.gov.au 61755405644 284. Assigned sip:timothy.b@scenicrim.qld.gov.au 61755405644 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
285. Assigning sip:judith.h@scenicrim.qld.gov.au 61755405645 285. Assigned sip:judith.h@scenicrim.qld.gov.au 61755405645 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
286. Assigning sip:Sudheer.P@scenicrim.qld.gov.au 61755405647 286. Assigned sip:Sudheer.P@scenicrim.qld.gov.au 61755405647 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
287. Assigning sip:amanda.d@scenicrim.qld.gov.au 61755405650 287. Assigned sip:amanda.d@scenicrim.qld.gov.au 61755405650 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
288. Assigning sip:richard.h@scenicrim.qld.gov.au 61755405651 288. Assigned sip:richard.h@scenicrim.qld.gov.au 61755405651 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
289. Assigning sip:matt.a@scenicrim.qld.gov.au 61755405653 289. Assigned sip:matt.a@scenicrim.qld.gov.au 61755405653 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
290. Assigning sip:jackie.l@scenicrim.qld.gov.au 61755405655 290. Assigned sip:jackie.l@scenicrim.qld.gov.au 61755405655 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
291. Assigning sip:James.OK@scenicrim.qld.gov.au 61755405656 291. Assigned sip:James.OK@scenicrim.qld.gov.au 61755405656 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
292. Assigning sip:amy.w@scenicrim.qld.gov.au 61755405658 292. Assigned sip:amy.w@scenicrim.qld.gov.au 61755405658 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
293. Assigning sip:nicole.w@scenicrim.qld.gov.au 61755405659 293. Assigned sip:nicole.w@scenicrim.qld.gov.au 61755405659 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
294. Assigning sip:brenda.w@scenicrim.qld.gov.au 61755405660 294. Assigned sip:brenda.w@scenicrim.qld.gov.au 61755405660 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
295. Assigning sip:cherece.j@scenicrim.qld.gov.au 61755405661 295. Assigned sip:cherece.j@scenicrim.qld.gov.au 61755405661 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
296. Assigning sip:claire.d@scenicrim.qld.gov.au 61755405662 296. Assigned sip:claire.d@scenicrim.qld.gov.au 61755405662 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
297. Assigning sip:owen.s@scenicrim.qld.gov.au 61755405663 297. Assigned sip:owen.s@scenicrim.qld.gov.au 61755405663 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
298. Assigning sip:shaun.wr@scenicrim.qld.gov.au 61755405664 298. Assigned sip:shaun.wr@scenicrim.qld.gov.au 61755405664 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
299. Assigning sip:terry.h@scenicrim.qld.gov.au 61755405665 299. Assigned sip:terry.h@scenicrim.qld.gov.au 61755405665 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
300. Assigning sip:jane.g@scenicrim.qld.gov.au 61755405667 300. Assigned sip:jane.g@scenicrim.qld.gov.au 61755405667 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
301. Assigning sip:nichole.m@scenicrim.qld.gov.au 61755405670 301. Assigned sip:nichole.m@scenicrim.qld.gov.au 61755405670 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
302. Assigning sip:catherine.k@scenicrim.qld.gov.au 61755405681 302. Assigned sip:catherine.k@scenicrim.qld.gov.au 61755405681 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
303. Assigning sip:peter.a@scenicrim.qld.gov.au 61755405683 303. Assigned sip:peter.a@scenicrim.qld.gov.au 61755405683 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
304. Assigning sip:jan.h@scenicrim.qld.gov.au 61755405684 304. Assigned sip:jan.h@scenicrim.qld.gov.au 61755405684 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
305. Assigning sip:Amelia.J@scenicrim.qld.gov.au 61755405686 305. Assigned sip:Amelia.J@scenicrim.qld.gov.au 61755405686 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
306. Assigning sip:Olivia.P@scenicrim.qld.gov.au 61755405688 306. Assigned sip:Olivia.P@scenicrim.qld.gov.au 61755405688 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
307. Assigning sip:skype.t@scenicrim.qld.gov.au 61755405689 307. Assigned sip:skype.t@scenicrim.qld.gov.au 61755405689 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
308. Assigning sip:Debbie.S@scenicrim.qld.gov.au 61755405690 308. Assigned sip:Debbie.S@scenicrim.qld.gov.au 61755405690 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
309. Assigning sip:Joanne.H@scenicrim.qld.gov.au 61755405691 309. Assigned sip:Joanne.H@scenicrim.qld.gov.au 61755405691 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
310. Assigning sip:byron.s@scenicrim.qld.gov.au 61755405692 310. Assigned sip:byron.s@scenicrim.qld.gov.au 61755405692 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
311. Assigning sip:jeremey.r@scenicrim.qld.gov.au 61755405693 311. Assigned sip:jeremey.r@scenicrim.qld.gov.au 61755405693 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
312. Assigning sip:sarita.k@scenicrim.qld.gov.au 61755405694 312. Assigned sip:sarita.k@scenicrim.qld.gov.au 61755405694 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
313. Assigning sip:Carly.L@scenicrim.qld.gov.au 61755405695 313. Assigned sip:Carly.L@scenicrim.qld.gov.au 61755405695 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
314. Assigning sip:bill.k@scenicrim.qld.gov.au 61755405696 314. Assigned sip:bill.k@scenicrim.qld.gov.au 61755405696 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
315. Assigning sip:Madi.L@scenicrim.qld.gov.au 61755405697 315. Assigned sip:Madi.L@scenicrim.qld.gov.au 61755405697 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
316. Assigning sip:Chris.C@scenicrim.qld.gov.au 61755405698 316. Assigned sip:Chris.C@scenicrim.qld.gov.au 61755405698 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
317. Assigning sip:lisa.c@scenicrim.qld.gov.au 61755405699 317. Assigned sip:lisa.c@scenicrim.qld.gov.au 61755405699 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
318. Assigning sip:Lily.M@scenicrim.qld.gov.au 61755405901 318. Assigned sip:Lily.M@scenicrim.qld.gov.au 61755405901 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
319. Assigning sip:doug.h@scenicrim.qld.gov.au 61755405902 319. Assigned sip:doug.h@scenicrim.qld.gov.au 61755405902 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
320. Assigning sip:Viral.P@scenicrim.qld.gov.au 61755405903 320. Assigned sip:Viral.P@scenicrim.qld.gov.au 61755405903 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
321. Assigning sip:nicole.a@scenicrim.qld.gov.au 61755405904 321. Assigned sip:nicole.a@scenicrim.qld.gov.au 61755405904 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
322. Assigning sip:amanda.v@scenicrim.qld.gov.au 61755405905 322. Assigned sip:amanda.v@scenicrim.qld.gov.au 61755405905 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
323. Assigning sip:Mark.Sl@scenicrim.qld.gov.au 61755405907 323. Assigned sip:Mark.Sl@scenicrim.qld.gov.au 61755405907 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
324. Assigning sip:isabel.f@scenicrim.qld.gov.au 61755405909 324. Assigned sip:isabel.f@scenicrim.qld.gov.au 61755405909 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
325. Assigning sip:katie.n@scenicrim.qld.gov.au 61755405910 325. Assigned sip:katie.n@scenicrim.qld.gov.au 61755405910 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
326. Assigning sip:kelly.r@scenicrim.qld.gov.au 61755405911 326. Assigned sip:kelly.r@scenicrim.qld.gov.au 61755405911 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
327. Assigning sip:amanda.f@scenicrim.qld.gov.au 61755405912 327. Assigned sip:amanda.f@scenicrim.qld.gov.au 61755405912 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
328. Assigning sip:anne.b@scenicrim.qld.gov.au 61755405913 328. Assigned sip:anne.b@scenicrim.qld.gov.au 61755405913 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
329. Assigning sip:desley.a@scenicrim.qld.gov.au 61755405914 329. Assigned sip:desley.a@scenicrim.qld.gov.au 61755405914 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
330. Assigning sip:stephen.b@scenicrim.qld.gov.au 61755405915 330. Assigned sip:stephen.b@scenicrim.qld.gov.au 61755405915 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
331. Assigning sip:melissa.c@scenicrim.qld.gov.au 61755405916 331. Assigned sip:melissa.c@scenicrim.qld.gov.au 61755405916 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
332. Assigning sip:jarrod.h@scenicrim.qld.gov.au 61755405917 332. Assigned sip:jarrod.h@scenicrim.qld.gov.au 61755405917 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
333. Assigning sip:carolann.b@scenicrim.qld.gov.au 61755405920 333. Assigned sip:carolann.b@scenicrim.qld.gov.au 61755405920 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
334. Assigning sip:rachel.b@scenicrim.qld.gov.au 61755405921 334. Assigned sip:rachel.b@scenicrim.qld.gov.au 61755405921 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
335. Assigning sip:julie.o@scenicrim.qld.gov.au 61755405922 335. Assigned sip:julie.o@scenicrim.qld.gov.au 61755405922 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
336. Assigning sip:georgina.w@scenicrim.qld.gov.au 61755405923 336. Assigned sip:georgina.w@scenicrim.qld.gov.au 61755405923 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
337. Assigning sip:jodie.s@scenicrim.qld.gov.au 61755405925 337. Assigned sip:jodie.s@scenicrim.qld.gov.au 61755405925 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
338. Assigning sip:alisha.p@scenicrim.qld.gov.au 61755405927 338. Assigned sip:alisha.p@scenicrim.qld.gov.au 61755405927 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
339. Assigning sip:kris.v@scenicrim.qld.gov.au 61755405928 339. Assigned sip:kris.v@scenicrim.qld.gov.au 61755405928 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
340. Assigning sip:ldccadmin@scenicrim.qld.gov.au 61755405934 340. Assigned sip:ldccadmin@scenicrim.qld.gov.au 61755405934 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
341. Assigning sip:ldcclogistics@scenicrim.qld.gov.au 61755405936 341. Assigned sip:ldcclogistics@scenicrim.qld.gov.au 61755405936 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
342. Assigning sip:james.w@scenicrim.qld.gov.au 61755405938 342. Assigned sip:james.w@scenicrim.qld.gov.au 61755405938 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
343. Assigning sip:asiful.a@scenicrim.qld.gov.au 61755405939 343. Assigned sip:asiful.a@scenicrim.qld.gov.au 61755405939 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
344. Assigning sip:ldc@scenicrim.qld.gov.au 61755405940 344. Assigned sip:ldc@scenicrim.qld.gov.au 61755405940 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
345. Assigning sip:ldccmedia@scenicrim.qld.gov.au 61755405941 345. Assigned sip:ldccmedia@scenicrim.qld.gov.au 61755405941 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
346. Assigning sip:Ian.M@scenicrim.qld.gov.au 61755405942 346. Assigned sip:Ian.M@scenicrim.qld.gov.au 61755405942 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
347. Assigning sip:ldccoperations@scenicrim.qld.gov.au 61755405943 347. Assigned sip:ldccoperations@scenicrim.qld.gov.au 61755405943 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
348. Assigning sip:Renee.Wa@scenicrim.qld.gov.au 61755405945 348. Assigned sip:Renee.Wa@scenicrim.qld.gov.au 61755405945 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
349. Assigning sip:ldccplanning@scenicrim.qld.gov.au 61755405946 349. Assigned sip:ldccplanning@scenicrim.qld.gov.au 61755405946 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
350. Assigning sip:ldccplanning1@scenicrim.qld.gov.au 61755405947 350. Assigned sip:ldccplanning1@scenicrim.qld.gov.au 61755405947 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
351. Assigning sip:paul.g@scenicrim.qld.gov.au 61755405949 351. Assigned sip:paul.g@scenicrim.qld.gov.au 61755405949 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
352. Assigning sip:David.A@scenicrim.qld.gov.au 61755405951 352. Assigned sip:David.A@scenicrim.qld.gov.au 61755405951 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
353. Assigning sip:rhiannon.t@scenicrim.qld.gov.au 61755405952 353. Assigned sip:rhiannon.t@scenicrim.qld.gov.au 61755405952 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
354. Assigning sip:Hiral.P@scenicrim.qld.gov.au 61755405953 354. Assigned sip:Hiral.P@scenicrim.qld.gov.au 61755405953 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
355. Assigning sip:Yoni.R@scenicrim.qld.gov.au 61755405954 355. Assigned sip:Yoni.R@scenicrim.qld.gov.au 61755405954 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
356. Assigning sip:craig.mc@scenicrim.qld.gov.au 61755405956 356. Assigned sip:craig.mc@scenicrim.qld.gov.au 61755405956 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
357. Assigning sip:ormnorth.l@scenicrim.qld.gov.au 61755405957 357. Assigned sip:ormnorth.l@scenicrim.qld.gov.au 61755405957 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
358. Assigning sip:krystal.b@scenicrim.qld.gov.au 61755405962 358. Assigned sip:krystal.b@scenicrim.qld.gov.au 61755405962 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
359. Assigning sip:rebecca.r@scenicrim.qld.gov.au 61755405963 359. Assigned sip:rebecca.r@scenicrim.qld.gov.au 61755405963 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
360. Assigning sip:tickets.bd@scenicrim.qld.gov.au 61755405965 360. Assigned sip:tickets.bd@scenicrim.qld.gov.au 61755405965 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
361. Assigning sip:kelly.l@scenicrim.qld.gov.au 61755405966 361. Assigned sip:kelly.l@scenicrim.qld.gov.au 61755405966 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
362. Assigning sip:anna.s@scenicrim.qld.gov.au 61755405968 362. Assigned sip:anna.s@scenicrim.qld.gov.au 61755405968 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
363. Assigning sip:terence.h@scenicrim.qld.gov.au 61755405969 363. Assigned sip:terence.h@scenicrim.qld.gov.au 61755405969 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
364. Assigning sip:gerald.p@scenicrim.qld.gov.au 61755405970 364. Assigned sip:gerald.p@scenicrim.qld.gov.au 61755405970 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
365. Assigning sip:Jane.S@scenicrim.qld.gov.au 61755405972 365. Assigned sip:Jane.S@scenicrim.qld.gov.au 61755405972 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
366. Assigning sip:shaun.w@scenicrim.qld.gov.au 61755405973 366. Assigned sip:shaun.w@scenicrim.qld.gov.au 61755405973 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
367. Assigning sip:lisa.h@scenicrim.qld.gov.au 61755405974 367. Assigned sip:lisa.h@scenicrim.qld.gov.au 61755405974 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
368. Assigning sip:michael.g@scenicrim.qld.gov.au 61755405975 368. Assigned sip:michael.g@scenicrim.qld.gov.au 61755405975 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
369. Assigning sip:sonja.r@scenicrim.qld.gov.au 61755405976 369. Assigned sip:sonja.r@scenicrim.qld.gov.au 61755405976 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
370. Assigning sip:linda.p@scenicrim.qld.gov.au 61755405978 370. Assigned sip:linda.p@scenicrim.qld.gov.au 61755405978 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
371. Assigning sip:daniel.s@scenicrim.qld.gov.au 61755405979 371. Assigned sip:daniel.s@scenicrim.qld.gov.au 61755405979 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
372. Assigning sip:caroline.m@scenicrim.qld.gov.au 61755405980 372. Assigned sip:caroline.m@scenicrim.qld.gov.au 61755405980 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
373. Assigning sip:justin.k@scenicrim.qld.gov.au 61755405981 373. Assigned sip:justin.k@scenicrim.qld.gov.au 61755405981 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
374. Assigning sip:Jo.Jo@scenicrim.qld.gov.au 61755405984 374. Assigned sip:Jo.Jo@scenicrim.qld.gov.au 61755405984 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
375. Assigning sip:emily.b@scenicrim.qld.gov.au 61755405985 375. Assigned sip:emily.b@scenicrim.qld.gov.au 61755405985 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
376. Assigning sip:lisa.s@scenicrim.qld.gov.au 61755405986 376. Assigned sip:lisa.s@scenicrim.qld.gov.au 61755405986 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
377. Assigning sip:Malav.P@scenicrim.qld.gov.au 61755405988 377. Assigned sip:Malav.P@scenicrim.qld.gov.au 61755405988 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
378. Assigning sip:justin.si@scenicrim.qld.gov.au 61755405989 378. Assigned sip:justin.si@scenicrim.qld.gov.au 61755405989 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
379. Assigning sip:andrew.r@scenicrim.qld.gov.au 61755405991 379. Assigned sip:andrew.r@scenicrim.qld.gov.au 61755405991 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
380. Assigning sip:Julia.K@scenicrim.qld.gov.au 61755405994 380. Assigned sip:Julia.K@scenicrim.qld.gov.au 61755405994 LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
381. Assigning sip:106@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
381. # Assigning Error sip:106@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
382. Assigning sip:andrew.c@scenicrim.qld.gov.au 382. # Assigning Error sip:andrew.c@scenicrim.qld.gov.au LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
383. Assigning sip:andrew.j@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
383. # Assigning Error sip:andrew.j@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
384. Assigning sip:clf@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
384. # Assigning Error sip:clf@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
385. Assigning sip:clinton.k@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
385. # Assigning Error sip:clinton.k@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
386. Assigning sip:david.l@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
386. # Assigning Error sip:david.l@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
387. Assigning sip:eoc1@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
387. # Assigning Error sip:eoc1@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
388. Assigning sip:insync.onprem2@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
388. # Assigning Error sip:insync.onprem2@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
389. Assigning sip:integrity@scenicrim.qld.gov.au 389. # Assigning Error sip:integrity@scenicrim.qld.gov.au LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
390. Assigning sip:IT@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
390. # Assigning Error sip:IT@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
391. Assigning sip:nicholas.m@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
391. # Assigning Error sip:nicholas.m@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
392. Assigning sip:Quentin.P@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
392. # Assigning Error sip:Quentin.P@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
393. Assigning sip:SRRC_CC_AH@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : The user 'sip:SRRC_CC_AH@scenicrim.qld.gov.au' is not found
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : NotFound,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
393. # Assigning Error sip:SRRC_CC_AH@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
394. Assigning sip:tickets.bh@scenicrim.qld.gov.au 394. # Assigning Error sip:tickets.bh@scenicrim.qld.gov.au LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
395. Assigning sip:tony.b@scenicrim.qld.gov.au No number required Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set-CsPhoneNumberAssignment : Telephone number 'No number required' is invalid
At C:\Program Files\WindowsPowerShell\Modules\MicrosoftTeams\5.6.0\custom\Merged_custom_PsExt.ps1:1341 char:13
+ $result = Microsoft.Teams.ConfigAPI.Cmdlets.internal\Set- ...
+ ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~
+ CategoryInfo : InvalidOperation: ({ Identity = si...iceEnabled = }:<>f__AnonymousType107`7) [Set-CsPhoneNumberAssignment_Set], Exception
+ FullyQualifiedErrorId : BadRequest,Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Cmdlets.SetCsPhoneNumberAssignment_Set
395. # Assigning Error sip:tony.b@scenicrim.qld.gov.au No number required LocationID: Microsoft.Teams.ConfigAPI.Cmdlets.Generated.Models.LocationSchema
Completed processing
Script Duration: 01:04:59.2775774 HH:MM:SS
Start Time: 10/13/2023 23:53:34
Finish Time: 10/14/2023 00:58:34
Numbers Assigned: 373 of 395
Number of Errors: 22